## SUMMARY
BRECKRIDGE INVESTMENTS
Pickstone Peerless Mine
Daily Production Summary
Month: | 2025-08-01
Day: | 6
GRADE LEGEND |  |  | KEY
< 0.60 Waste |  |  | Above Budget
0.60 - 1.60 Low Grade |  |  | Below Budget
1.60 - 2.00 Medium Grade
> 2.00 High Grade
Shifts |  | MTD |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
DATE |  | Actual | Plan | Var. | % Var. | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
Projects | Dewatering (m) | 2.9 | 9 | -6.1 | -67.78% | 2025-08-01: 0.4; 2025-08-02: 0.4; 2025-08-03: 0.5; 2025-08-04: 0.5; 2025-08-05: 0.4; 2025-08-06: 0.7
| SW Stripping (m) | 0.3 | 0.3 | 0 | 0% | 2025-08-01: 0.05; 2025-08-02: 0.05; 2025-08-03: 0.05; 2025-08-04: 0.05; 2025-08-05: 0.05; 2025-08-06: 0.05
Meters | D. Drilling (m) | 262.8 | 248 | 14.8 | 5.968% | 2025-08-01: 68; 2025-08-02: 54.7; 2025-08-03: 39.5; 2025-08-04: 51; 2025-08-05: 49.6
| Development (m) | 180.3 | 184.3 | -4 | -2.17% | 2025-08-01: 38.9; 2025-08-02: 39.6; 2025-08-03: 2.9; 2025-08-04: 38.9; 2025-08-05: 38.9; 2025-08-06: 21.1
Benching | Tonnes (t) | 5713 | 5460 | 253 | 4.634% | 2025-08-01: 926; 2025-08-02: 879; 2025-08-03: 965; 2025-08-04: 977; 2025-08-05: 979; 2025-08-06: 987
| Grade (g/t) | 2.924 | 2.2564 | 0.66758 | 29.59% | 2025-08-01: 3.5549; 2025-08-02: 3.3304; 2025-08-03: 2.9584; 2025-08-04: 3.4358; 2025-08-05: 1.5282; 2025-08-06: 2.8142
| Gold (kg) | 16.7046 | 12.3198 | 4.3848 | 35.59% | 2025-08-01: 3.2919; 2025-08-02: 2.9274; 2025-08-03: 2.8548; 2025-08-04: 3.3567; 2025-08-05: 1.4961; 2025-08-06: 2.7777
Tramming | Tonnes (t) | 4925 | 5460 | -535 | -9.799% | 2025-08-01: 758; 2025-08-02: 1006; 2025-08-03: 960; 2025-08-04: 795.5; 2025-08-05: 947.5; 2025-08-06: 458
| Grade (g/t) | 2.6412 | 2.1988 | 0.44235 | 20.12% | 2025-08-01: 2.2936; 2025-08-02: 3.3518; 2025-08-03: 3.1195; 2025-08-04: 2.8487; 2025-08-05: 2.7826; 2025-08-06: 0
| Gold (kg) | 13.0078 | 12.0057 | 1.0022 | 8.348% | 2025-08-01: 1.7386; 2025-08-02: 3.3719; 2025-08-03: 2.9947; 2025-08-04: 2.2661; 2025-08-05: 2.6365; 2025-08-06: 0
Hoisting | Tonnes (t) | 5350 | 4990 | 360 | 7.214% | 2025-08-01: 782; 2025-08-02: 952; 2025-08-03: 907; 2025-08-04: 812; 2025-08-05: 931; 2025-08-06: 966
| Grade (g/t) | 1.7739 | 2.2344 | -0.46046 | -20.61% | 2025-08-01: 1.99; 2025-08-02: 2.13; 2025-08-03: 1.67; 2025-08-04: 1.82; 2025-08-05: 3.13; 2025-08-06: 0
| Gold (kg) | 9.4905 | 11.1496 | -1.6591 | -14.88% | 2025-08-01: 1.5562; 2025-08-02: 2.0278; 2025-08-03: 1.5147; 2025-08-04: 1.4778; 2025-08-05: 2.914; 2025-08-06: 0
Crushing | Tonnes (t) | 4285.2205 | 6456.2916 | -2171.0711 | -33.63% | 2025-08-01: 1078.5736; 2025-08-02: 1066.0176; 2025-08-03: 648.2984; 2025-08-04: 753.7309; 2025-08-05: 738.6; 2025-08-06: 0
| Grade (g/t) | 2.0179 | 2.1847 | -0.16685 | -7.637% | 2025-08-01: 1.4864; 2025-08-02: 1.8517; 2025-08-03: 2.7927; 2025-08-04: 1.7003; 2025-08-05: 2.6778; 2025-08-06: 0
| Gold (kg) | 8.647 | 14.1052 | -5.4582 | -38.7% | 2025-08-01: 1.6032; 2025-08-02: 1.9739; 2025-08-03: 1.8105; 2025-08-04: 1.2816; 2025-08-05: 1.9778; 2025-08-06: 0
Milling | Tonnes (t) | 5244.8029 | 6456.2916 | -1211.4887 | -18.76% | 2025-08-01: 1244.3207; 2025-08-02: 1143.296; 2025-08-03: 665.4402; 2025-08-04: 1124.527; 2025-08-05: 1067.219; 2025-08-06: 0
| Grade (g/t) | 1.8025 | 2.1847 | -0.38221 | -17.49% | 2025-08-01: 1.3227; 2025-08-02: 1.9326; 2025-08-03: 2.1524; 2025-08-04: 1.7907; 2025-08-05: 2.0169; 2025-08-06: 0
| Gold (kg) | 9.4539 | 14.1052 | -4.6514 | -32.98% | 2025-08-01: 1.6459; 2025-08-02: 2.2095; 2025-08-03: 1.4323; 2025-08-04: 2.0137; 2025-08-05: 2.1525; 2025-08-06: 0
CIL Feed | Grade (g/t) | 2.1626 | 2.1847 | -0.022087 | -1.011% | 2025-08-01: 1.8464; 2025-08-02: 2.0515; 2025-08-03: 2.722; 2025-08-04: 2.296; 2025-08-05: 2.1612; 2025-08-06: 0
| Gold (kg) | 11.3426 | 14.1052 | -2.7626 | -19.59% | 2025-08-01: 2.2975; 2025-08-02: 2.3455; 2025-08-03: 1.8113; 2025-08-04: 2.5819; 2025-08-05: 2.3064; 2025-08-06: 0
Tails | Grade (g/t) | 0.31384 | 0.26666 | 0.047182 | 17.69% | 2025-08-01: 0.26984; 2025-08-02: 0.29961; 2025-08-03: 0.39; 2025-08-04: 0.34393; 2025-08-05: 0.30121; 2025-08-06: 0
| Gold (kg) | 1.6461 | 1.7217 | -0.075599 | -4.391% | 2025-08-01: 0.33577; 2025-08-02: 0.34255; 2025-08-03: 0.25952; 2025-08-04: 0.38676; 2025-08-05: 0.32145; 2025-08-06: 0
[6 empty] | Meters | Actual - Daily | Plan - Daily | Actual - MTD | Plan - MTD
[6 empty] | Diamond Drilling |  |  | 262.8 | 248
[6 empty] | Development | 21.1 | 0 | 180.3 | 184.3
[7 empty] | TONNES (t) |  | GRADE (g/t) |  | GOLD (kg) |  | TONNES (t) |  | GRADE (g/t) |  | GOLD (kg)
[6 empty] | PROD | Actual - Daily | Plan - Daily | Actual - Daily | Plan - Daily | Actual - Daily | Plan - Daily | Actual - MTD | Plan - MTD | Actual - MTD | Plan - MTD | Actual - MTD | Plan - MTD
[6 empty] | Broken | 987 | 910 | 2.8142 | 2.2564 | 2.7777 | 2.0533 | 5713 | 5460 | 2.924 | 2.2564 | 16.7046 | 12.3198
[6 empty] | Trammed | 458 | 910 | 0 | 2.2564 | 0 | 2.0533 | 4925 | 5460 | 2.6412 | 2.1988 | 13.0078 | 12.0057
[6 empty] | Hoisted | 966 | 850 | 0 | 2.2399 | 0 | 1.9039 | 5350 | 4990 | 1.7739 | 2.2344 | 9.4905 | 11.1496
[6 empty] | Crushed | 0 | 1173.8712 | 0 | 2.2355 | 0 | 2.6242 | 4285.2205 | 6456.2916 | 2.0179 | 2.1847 | 8.647 | 14.1052
[6 empty] | Milled | 0 | 1173.8712 | 0 | 2.2355 | 0 | 2.6242 | 5244.8029 | 6456.2916 | 1.8025 | 2.1847 | 9.4539 | 14.1052
[6 empty] | CIL Head | 0 | 1173.8712 | 0 | 2.2355 | 0 | 2.6242 | 5244.8029 | 6456.2916 | 2.1626 | 2.1847 | 11.3426 | 14.1052
[6 empty] | Tails | 0 | 1173.8712 | 0 | 0.26392 | 0 | 0.30981 | 5244.8029 | 6456.2916 | 0.31384 | 0.26666 | 1.6461 | 1.7217

## KPIs
BRECKRIDGE INVESTMENTS
Pickstone Underground Mine
Daily KPIs
Month: | 2025-08-01
Day: | 6
|  |  | Daily |  |  |  | MTD
1 | Equiping | UoM | Actual | Plan | Var | Var % | Actual | Plan | Var | Var %
1.1 | Southwell Shaft | m | #REF! | #REF! | 0 | 0% |  |  | 0 | 0%
2 | Diamond Drilling
2.1 | Surface | m |  |  | 0 | 0% |  |  | 0 | 0%
2.2 | Underground | m |  |  | 0 | 0% |  |  | 0 | 0%
2.3 | Total | m | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
3 | Development
3.1 | CAPEX | m | 3.8 | 4.9 | -1.1 | -22.45% | 25.1 | 19.3 | 5.8 | 30.05%
3.2 | ROM | m | 17.3 | 33.9 | -16.6 | -48.97% | 155.2 | 165 | -9.8 | -5.939%
3.3 | Total | m | 21.1 | 38.8 | -17.7 | -45.62% | 180.3 | 184.3 | -4 | -2.17%
4 | Tonnes
4.1 | Broken | t | 987 | 910 | 77 | 8.462% | 5713 | 5460 | 253 | 4.634%
4.2 | Trammed | t | 458 | 910 | -452 | -49.67% | 4925 | 5460 | -535 | -9.799%
4.3 | Hoisted | t | 966 | 850 | 116 | 13.65% | 5350 | 4990 | 360 | 7.214%
4.4 | Crushed | t | 0 | 1173.8712 | -1173.8712 | -100% | 4285.2205 | 6456.2916 | -2171.0711 | -33.63%
4.5 | Milled | t | 0 | 1173.8712 | -1173.8712 | -100% | 5244.8029 | 6456.2916 | -1211.4887 | -18.76%
5 | Grade
5.1 | Broken | g/t | 2.8142 | 2.2564 | 0.55786 | 24.72% | 2.924 | 2.2564 | 0.66758 | 29.59%
5.2 | Trammed | g/t | 0 | 2.2564 | -2.2564 | -100% | 2.6412 | 2.1988 | 0.44235 | 20.12%
5.3 | Hoisted | g/t | 0 | 2.2399 | -2.2399 | -100% | 1.7739 | 2.2399 | -0.46597 | -20.8%
5.4 | Crushed | g/t |  | 2.2355 | 0 | 0% | 2.0179 | 2.1847 | -0.16685 | -7.637%
5.5 | Milled | g/t |  | 2.2355 | 0 | 0% | 1.8025 | 2.1847 | -0.38221 | -17.49%
5.6 | CIL Feed | g/t |  | 2.2355 | 0 | 0% | 2.1626 | 2.1847 | -0.022087 | -1.011%
6 | Gold
6.1 | Broken | kg | 2.7777 | 2.0533 | 0.72435 | 35.28% | 16.7046 | 12.3198 | 4.3848 | 35.59%
6.2 | Trammed | kg | 0 | 2.0533 | -2.0533 | -100% | 13.0078 | 12.0057 | 1.0022 | 8.348%
6.3 | Hoisted | kg | 0 | 1.9039 | -1.9039 | -100% | 9.4905 | 11.1496 | -1.6591 | -14.88%
6.4 | Crushed | kg | 0 | 2.6242 | -2.6242 | -100% | 8.647 | 14.1052 | -5.4582 | -38.7%
6.5 | Milled | kg | 0 | 2.6242 | -2.6242 | -100% | 9.4539 | 14.1052 | -4.6514 | -32.98%
6.6 | CIL Feed | kg | 0 | 2.6242 | -2.6242 | -100% | 11.3426 | 14.1052 | -2.7626 | -19.59%
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
Southwell Shaft Equiping
| Actual | 2025-08-01: #REF!; 2025-08-02: #REF!; 2025-08-03: #REF!; 2025-08-04: #REF!; 2025-08-05: #REF!; 2025-08-06: #REF!
| Cum. Actual | 2025-08-01: #REF!
| Plan | 2025-08-01: #REF!; 2025-08-02: #REF!; 2025-08-03: #REF!; 2025-08-04: #REF!; 2025-08-05: #REF!; 2025-08-06: #REF!
| Cum. Plan | 2025-08-01: #REF!
Surface Diamond Drilling
| Actual | 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0
| Cum. Actual | 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0
| Plan | 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0
| Cum. Plan | 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0
Underground Diamond Drilling
| Actual | 2025-08-01: 68; 2025-08-02: 54.7; 2025-08-03: 39.5; 2025-08-04: 51; 2025-08-05: 49.6
| Cum. Actual | 2025-08-01: 68; 2025-08-02: 122.7; 2025-08-03: 162.2; 2025-08-04: 213.2; 2025-08-05: 262.8
| Plan | 2025-08-01: 38; 2025-08-02: 38; 2025-08-03: 48; 2025-08-04: 66; 2025-08-05: 58
| Cum. Plan | 2025-08-01: 38; 2025-08-02: 76; 2025-08-03: 124; 2025-08-04: 190; 2025-08-05: 248
Total Diamond Drilling
| Actual | 2025-08-01: 68; 2025-08-02: 54.7; 2025-08-03: 39.5; 2025-08-04: 51; 2025-08-05: 49.6
| Cum. Actual | 2025-08-01: 68; 2025-08-02: 122.7; 2025-08-03: 162.2; 2025-08-04: 213.2; 2025-08-05: 262.8
| Plan | 2025-08-01: 38; 2025-08-02: 38; 2025-08-03: 48; 2025-08-04: 66; 2025-08-05: 58
| Cum. Plan | 2025-08-01: 38; 2025-08-02: 76; 2025-08-03: 124; 2025-08-04: 190; 2025-08-05: 248
CAPEX Development
| Actual | 2025-08-01: 5.7; 2025-08-02: 4.9; 2025-08-03: 2.9; 2025-08-04: 3.8; 2025-08-05: 4; 2025-08-06: 3.8
| Cum. Actual | 2025-08-01: 5.7; 2025-08-02: 10.6; 2025-08-03: 13.5; 2025-08-04: 17.3; 2025-08-05: 21.3; 2025-08-06: 25.1
| Plan | 2025-08-01: 3.6; 2025-08-02: 3.6; 2025-08-03: 0.9; 2025-08-04: 3.6; 2025-08-05: 2.7; 2025-08-06: 4.9
| Cum. Plan | 2025-08-01: 3.6; 2025-08-02: 7.2; 2025-08-03: 8.1; 2025-08-04: 11.7; 2025-08-05: 14.4; 2025-08-06: 19.3
ROM Development
| Actual | 2025-08-01: 33.2; 2025-08-02: 34.7; 2025-08-03: 0; 2025-08-04: 35.1; 2025-08-05: 34.9; 2025-08-06: 17.3
| Cum. Actual | 2025-08-01: 33.2; 2025-08-02: 67.9; 2025-08-03: 67.9; 2025-08-04: 103; 2025-08-05: 137.9; 2025-08-06: 155.2
| Plan | 2025-08-01: 32.1; 2025-08-02: 32.1; 2025-08-03: 0; 2025-08-04: 33; 2025-08-05: 33.9; 2025-08-06: 33.9
| Cum. Plan | 2025-08-01: 32.1; 2025-08-02: 64.2; 2025-08-03: 64.2; 2025-08-04: 97.2; 2025-08-05: 131.1; 2025-08-06: 165
Total Development
| Actual | 2025-08-01: 38.9; 2025-08-02: 39.6; 2025-08-03: 2.9; 2025-08-04: 38.9; 2025-08-05: 38.9; 2025-08-06: 21.1
| Cum. Actual | 2025-08-01: 38.9; 2025-08-02: 78.5; 2025-08-03: 81.4; 2025-08-04: 120.3; 2025-08-05: 159.2; 2025-08-06: 180.3
| Plan | 2025-08-01: 35.7; 2025-08-02: 35.7; 2025-08-03: 0.9; 2025-08-04: 36.6; 2025-08-05: 36.6; 2025-08-06: 38.8
| Cum. Plan | 2025-08-01: 35.7; 2025-08-02: 71.4; 2025-08-03: 72.3; 2025-08-04: 108.9; 2025-08-05: 145.5; 2025-08-06: 184.3
Broken Tonnes
| Actual | 2025-08-01: 926; 2025-08-02: 879; 2025-08-03: 965; 2025-08-04: 977; 2025-08-05: 979; 2025-08-06: 987
| Cum. Actual | 2025-08-01: 926; 2025-08-02: 1805; 2025-08-03: 2770; 2025-08-04: 3747; 2025-08-05: 4726; 2025-08-06: 5713
| Plan | 2025-08-01: 910; 2025-08-02: 910; 2025-08-03: 910; 2025-08-04: 910; 2025-08-05: 910; 2025-08-06: 910
| Cum. Plan | 2025-08-01: 910; 2025-08-02: 1820; 2025-08-03: 2730; 2025-08-04: 3640; 2025-08-05: 4550; 2025-08-06: 5460
Trammed Tonnes
| Actual | 2025-08-01: 758; 2025-08-02: 1006; 2025-08-03: 960; 2025-08-04: 795.5; 2025-08-05: 947.5; 2025-08-06: 458
| Cum. Actual | 2025-08-01: 758; 2025-08-02: 1764; 2025-08-03: 2724; 2025-08-04: 3519.5; 2025-08-05: 4467; 2025-08-06: 4925
| Plan | 2025-08-01: 910; 2025-08-02: 910; 2025-08-03: 910; 2025-08-04: 910; 2025-08-05: 910; 2025-08-06: 910
| Cum. Plan | 2025-08-01: 910; 2025-08-02: 1820; 2025-08-03: 2730; 2025-08-04: 3640; 2025-08-05: 4550; 2025-08-06: 5460
Hoisted Tonnes
| Actual | 2025-08-01: 782; 2025-08-02: 952; 2025-08-03: 907; 2025-08-04: 812; 2025-08-05: 931; 2025-08-06: 966
| Cum. Actual | 2025-08-01: 782; 2025-08-02: 1734; 2025-08-03: 2641; 2025-08-04: 3453; 2025-08-05: 4384; 2025-08-06: 5350
| Plan | 2025-08-01: 740; 2025-08-02: 850; 2025-08-03: 850; 2025-08-04: 850; 2025-08-05: 850; 2025-08-06: 850
| Cum. Plan | 2025-08-01: 740; 2025-08-02: 1590; 2025-08-03: 2440; 2025-08-04: 3290; 2025-08-05: 4140; 2025-08-06: 4990
Crushed Tonnes
| Actual | 2025-08-01: 1078.5736; 2025-08-02: 1066.0176; 2025-08-03: 648.2984; 2025-08-04: 753.7309; 2025-08-05: 738.6; 2025-08-06: 0
| Cum. Actual | 2025-08-01: 1078.5736; 2025-08-02: 2144.5912; 2025-08-03: 2792.8896; 2025-08-04: 3546.6205; 2025-08-05: 4285.2205; 2025-08-06: 4285.2205
| Plan | 2025-08-01: 1173.8712; 2025-08-02: 1173.8712; 2025-08-03: 1173.8712; 2025-08-04: 1173.8712; 2025-08-05: 586.9356; 2025-08-06: 1173.8712
| Cum. Plan | 2025-08-01: 1173.8712; 2025-08-02: 2347.7424; 2025-08-03: 3521.6136; 2025-08-04: 4695.4848; 2025-08-05: 5282.4204; 2025-08-06: 6456.2916
Milled Tonnes
| Actual | 2025-08-01: 1244.3207; 2025-08-02: 1143.296; 2025-08-03: 665.4402; 2025-08-04: 1124.527; 2025-08-05: 1067.219; 2025-08-06: 0
| Cum. Actual | 2025-08-01: 1244.3207; 2025-08-02: 2387.6167; 2025-08-03: 3053.0569; 2025-08-04: 4177.5839; 2025-08-05: 5244.8029; 2025-08-06: 5244.8029
| Plan | 2025-08-01: 1173.8712; 2025-08-02: 1173.8712; 2025-08-03: 1173.8712; 2025-08-04: 1173.8712; 2025-08-05: 586.9356; 2025-08-06: 1173.8712
| Cum. Plan | 2025-08-01: 1173.8712; 2025-08-02: 2347.7424; 2025-08-03: 3521.6136; 2025-08-04: 4695.4848; 2025-08-05: 5282.4204; 2025-08-06: 6456.2916
Broken Grade
| Actual | 2025-08-01: 3.5549; 2025-08-02: 3.3304; 2025-08-03: 2.9584; 2025-08-04: 3.4358; 2025-08-05: 1.5282; 2025-08-06: 2.8142
| Cum. Actual | 2025-08-01: 3.5549; 2025-08-02: 3.4456; 2025-08-03: 3.2759; 2025-08-04: 3.3176; 2025-08-05: 2.9469; 2025-08-06: 2.924
| Plan | 2025-08-01: 2.2564; 2025-08-02: 2.2564; 2025-08-03: 2.2564; 2025-08-04: 2.2564; 2025-08-05: 2.2564; 2025-08-06: 2.2564
| Cum. Plan | 2025-08-01: 2.2564; 2025-08-02: 2.2564; 2025-08-03: 2.2564; 2025-08-04: 2.2564; 2025-08-05: 2.2564; 2025-08-06: 2.2564
Trammed Grade
| Actual | 2025-08-01: 2.2936; 2025-08-02: 3.3518; 2025-08-03: 3.1195; 2025-08-04: 2.8487; 2025-08-05: 2.7826; 2025-08-06: 0
| Cum. Actual | 2025-08-01: 2.2936; 2025-08-02: 2.8971; 2025-08-03: 2.9755; 2025-08-04: 2.9468; 2025-08-05: 2.912; 2025-08-06: 2.6412
| Plan | 2025-08-01: 1.9111; 2025-08-02: 2.2564; 2025-08-03: 2.2564; 2025-08-04: 2.2564; 2025-08-05: 2.2564; 2025-08-06: 2.2564
| Cum. Plan | 2025-08-01: 1.9111; 2025-08-02: 2.0838; 2025-08-03: 2.1413; 2025-08-04: 2.1701; 2025-08-05: 2.1873; 2025-08-06: 2.1988
Hoisted Grade
| Actual | 2025-08-01: 1.99; 2025-08-02: 2.13; 2025-08-03: 1.67; 2025-08-04: 1.82; 2025-08-05: 3.13; 2025-08-06: 0
| Cum. Actual | 2025-08-01: 1.99; 2025-08-02: 2.0669; 2025-08-03: 1.9306; 2025-08-04: 1.9046; 2025-08-05: 2.1648; 2025-08-06: 1.7739
| Plan | 2025-08-01: 2.2027; 2025-08-02: 2.2399; 2025-08-03: 2.2399; 2025-08-04: 2.2399; 2025-08-05: 2.2399; 2025-08-06: 2.2399
| Cum. Plan | 2025-08-01: 2.2027; 2025-08-02: 2.2226; 2025-08-03: 2.2286; 2025-08-04: 2.2315; 2025-08-05: 2.2333; 2025-08-06: 2.2344
Crushed Grade
| Actual | 2025-08-01: 1.4864; 2025-08-02: 1.8517; 2025-08-03: 2.7927; 2025-08-04: 1.7003; 2025-08-05: 2.6778
| Cum. Actual | 2025-08-01: 1.4864; 2025-08-02: 1.668; 2025-08-03: 1.9291; 2025-08-04: 1.8804; 2025-08-05: 2.0179; 2025-08-06: 2.0179
| Plan | 2025-08-01: 2.3; 2025-08-02: 2.3; 2025-08-03: 1.832; 2025-08-04: 2.2315; 2025-08-05: 2.2339; 2025-08-06: 2.2355
| Cum. Plan | 2025-08-01: 2.3; 2025-08-02: 2.3; 2025-08-03: 2.144; 2025-08-04: 2.1659; 2025-08-05: 2.1734; 2025-08-06: 2.1847
Milled Grade
| Actual | 2025-08-01: 1.3227; 2025-08-02: 1.9326; 2025-08-03: 2.1524; 2025-08-04: 1.7907; 2025-08-05: 2.0169
| Cum. Actual | 2025-08-01: 1.3227; 2025-08-02: 1.6147; 2025-08-03: 1.7319; 2025-08-04: 1.7478; 2025-08-05: 1.8025; 2025-08-06: 1.8025
| Plan | 2025-08-01: 2.3; 2025-08-02: 2.3; 2025-08-03: 1.832; 2025-08-04: 2.2315; 2025-08-05: 2.2339; 2025-08-06: 2.2355
| Cum. Plan | 2025-08-01: 2.3; 2025-08-02: 2.3; 2025-08-03: 2.144; 2025-08-04: 2.1659; 2025-08-05: 2.1734; 2025-08-06: 2.1847
CIL Feed Grade
| Actual | 2025-08-01: 1.8464; 2025-08-02: 2.0515; 2025-08-03: 2.722; 2025-08-04: 2.296; 2025-08-05: 2.1612
| Cum. Actual | 2025-08-01: 1.8464; 2025-08-02: 1.9446; 2025-08-03: 2.114; 2025-08-04: 2.163; 2025-08-05: 2.1626; 2025-08-06: 2.1626
| Plan | 2025-08-01: 2.3; 2025-08-02: 2.3; 2025-08-03: 1.832; 2025-08-04: 2.2315; 2025-08-05: 2.2339; 2025-08-06: 2.2355
| Cum. Plan | 2025-08-01: 2.3; 2025-08-02: 2.3; 2025-08-03: 2.144; 2025-08-04: 2.1659; 2025-08-05: 2.1734; 2025-08-06: 2.1847
Broken Gold
| Actual | 2025-08-01: 3.2919; 2025-08-02: 2.9274; 2025-08-03: 2.8548; 2025-08-04: 3.3567; 2025-08-05: 1.4961; 2025-08-06: 2.7777
| Cum. Actual | 2025-08-01: 3.2919; 2025-08-02: 6.2193; 2025-08-03: 9.0741; 2025-08-04: 12.4309; 2025-08-05: 13.927; 2025-08-06: 16.7046
| Plan | 2025-08-01: 2.0533; 2025-08-02: 2.0533; 2025-08-03: 2.0533; 2025-08-04: 2.0533; 2025-08-05: 2.0533; 2025-08-06: 2.0533
| Cum. Plan | 2025-08-01: 2.0533; 2025-08-02: 4.1066; 2025-08-03: 6.1599; 2025-08-04: 8.2132; 2025-08-05: 10.2665; 2025-08-06: 12.3198
Trammed Gold
| Actual | 2025-08-01: 1.7386; 2025-08-02: 3.3719; 2025-08-03: 2.9947; 2025-08-04: 2.2661; 2025-08-05: 2.6365; 2025-08-06: 0
| Cum. Actual | 2025-08-01: 1.7386; 2025-08-02: 5.1105; 2025-08-03: 8.1052; 2025-08-04: 10.3713; 2025-08-05: 13.0078; 2025-08-06: 13.0078
| Plan | 2025-08-01: 1.7391; 2025-08-02: 2.0533; 2025-08-03: 2.0533; 2025-08-04: 2.0533; 2025-08-05: 2.0533; 2025-08-06: 2.0533
| Cum. Plan | 2025-08-01: 1.7391; 2025-08-02: 3.7924; 2025-08-03: 5.8457; 2025-08-04: 7.899; 2025-08-05: 9.9523; 2025-08-06: 12.0057
Hoisted Gold
| Actual | 2025-08-01: 1.5562; 2025-08-02: 2.0278; 2025-08-03: 1.5147; 2025-08-04: 1.4778; 2025-08-05: 2.914; 2025-08-06: 0
| Cum. Actual | 2025-08-01: 1.5562; 2025-08-02: 3.5839; 2025-08-03: 5.0986; 2025-08-04: 6.5765; 2025-08-05: 9.4905; 2025-08-06: 9.4905
| Plan | 2025-08-01: 1.63; 2025-08-02: 1.9039; 2025-08-03: 1.9039; 2025-08-04: 1.9039; 2025-08-05: 1.9039; 2025-08-06: 1.9039
| Cum. Plan | 2025-08-01: 1.63; 2025-08-02: 3.5339; 2025-08-03: 5.4378; 2025-08-04: 7.3418; 2025-08-05: 9.2457; 2025-08-06: 11.1496
Crushed Gold
| Actual | 2025-08-01: 1.6032; 2025-08-02: 1.9739; 2025-08-03: 1.8105; 2025-08-04: 1.2816; 2025-08-05: 1.9778; 2025-08-06: 0
| Cum. Actual | 2025-08-01: 1.6032; 2025-08-02: 3.5771; 2025-08-03: 5.3876; 2025-08-04: 6.6692; 2025-08-05: 8.647; 2025-08-06: 8.647
| Plan | 2025-08-01: 2.6999; 2025-08-02: 2.6999; 2025-08-03: 2.1505; 2025-08-04: 2.6195; 2025-08-05: 1.3112; 2025-08-06: 2.6242
| Cum. Plan | 2025-08-01: 2.6999; 2025-08-02: 5.3998; 2025-08-03: 7.5503; 2025-08-04: 10.1699; 2025-08-05: 11.481; 2025-08-06: 14.1052
Milled Gold
| Actual | 2025-08-01: 1.6459; 2025-08-02: 2.2095; 2025-08-03: 1.4323; 2025-08-04: 2.0137; 2025-08-05: 2.1525; 2025-08-06: 0
| Cum. Actual | 2025-08-01: 1.6459; 2025-08-02: 3.8554; 2025-08-03: 5.2877; 2025-08-04: 7.3014; 2025-08-05: 9.4539; 2025-08-06: 9.4539
| Plan | 2025-08-01: 2.6999; 2025-08-02: 2.6999; 2025-08-03: 2.1505; 2025-08-04: 2.6195; 2025-08-05: 1.3112; 2025-08-06: 2.6242
| Cum. Plan | 2025-08-01: 2.6999; 2025-08-02: 5.3998; 2025-08-03: 7.5503; 2025-08-04: 10.1699; 2025-08-05: 11.481; 2025-08-06: 14.1052
CIL Feed Gold
| Actual | 2025-08-01: 2.2975; 2025-08-02: 2.3455; 2025-08-03: 1.8113; 2025-08-04: 2.5819; 2025-08-05: 2.3064; 2025-08-06: 0
| Cum. Actual | 2025-08-01: 2.2975; 2025-08-02: 4.643; 2025-08-03: 6.4543; 2025-08-04: 9.0362; 2025-08-05: 11.3426; 2025-08-06: 11.3426
| Plan | 2025-08-01: 2.6999; 2025-08-02: 2.6999; 2025-08-03: 2.1505; 2025-08-04: 2.6195; 2025-08-05: 1.3112; 2025-08-06: 2.6242
| Cum. Plan | 2025-08-01: 2.6999; 2025-08-02: 5.3998; 2025-08-03: 7.5503; 2025-08-04: 10.1699; 2025-08-05: 11.481; 2025-08-06: 14.1052

## Actions
BRECKRIDGE INVESTMENTS |  |  |  | Actions
Pickstone Peerless Mine |  |  |  | Total Actions | 1
Daily Action Tracker |  |  |  | Completed | 0 | 0%
2025-08-01 |  |  |  | Open | 1 | 100%
|  |  |  | Overdue | 0 | 0%
Action No | Agreed Action | Responsible Person | Date Raised | Due Date | Revised Date | Days (Age) | Date Closed | Status | Memo/Notes
24 | Transportation of loader at 7 level through subvertical shaft. | M.Dicha | 2025-03-26 | 2025-04-14 | 2025-06-10 |  |  | K | Awaiting bigger winch procurement.
| Reducing the number of cables in the shaft and introducing a ring feed for power isolation in case of breakdowns. | A. Bimha | 2025-04-07 | 2025-04-30 | 2025-08-31 |  |  | K | Southwell & Burnett Shaft redundant cables identified & reclammation is in progress. Ring Network Installation & commissioning to be completed by 30th of August 2025.
| Installation of a Weightometer on the Southwell Conveyor Belt | E. Mavhondo | 2025-05-07 | 2025-05-20 | 2025-08-31 |  |  | K | PO250425. Weightometer asssembly/wiring in progress. Waiting for delivey of PLC Cooling Fan. Installation expected in the week ending 30th of August 2025.
| Retrain people on isolation procedure | N.Dondo | 2025-07-29 | 2025-07-30 |  |  |  | K | Closed
| Come up with a system to eliminate misfires | V.Tsoriyo | 2025-07-29 | 2025-08-15 |  |  |  | K
| Install Subvertical Shaft Signals | M.Dicha | 2025-07-29 |  |  |  |  | K

## Activities
BRECKRIDGE INVESTMENTS
Pickstone Underground Mine
Daily Activity Log Sheet
Month: | 2025-08-01
Day: | 6
| Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Number of Machines | Plan | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0
|  | Actual | 1: 26; 2: 25; 3: 3; 4: 22; 5: 27; 6: 26
Priority | Stope / End Name | Activity | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
| 1L_W28_STOPE | Lashed
Sampled
Reef Marked
# of Machines - Actual
# of Machines - Plan
Comments
| 2L_W23_STOPE | Lashed | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Sampled | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Reef Marked | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | # of Machines - Actual | 1: 3; 2: 2; 4: 2; 5: 2; 6: 2
# of Machines - Plan
|  | Comments | 1: benching; 2: benching; 4: benching; 5: benching; 6: benching
| 3L_W23_STOPE | Lashed | 1: yes; 2: yes; 4: yes; 5: yes; 6: no
|  | Sampled | 1: yes; 2: yes; 4: yes; 5: yes; 6: no
|  | Reef Marked | 1: yes; 2: yes; 4: yes; 5: yes; 6: no
|  | # of Machines - Actual | 1: 1; 2: 1; 4: 1; 5: 1; 6: 0
# of Machines - Plan
|  | Comments | 1: slyping; 2: slyping; 4: benching; 5: benching; 6: no activity
| 3L_W24_STOPE | Lashed
Sampled
Reef Marked
# of Machines - Actual
# of Machines - Plan
Comments
| 4L_W25_STOPE | Lashed | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Sampled | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Reef Marked | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | # of Machines - Actual | 1: 1; 2: 1; 4: 2; 5: 2; 6: 2
# of Machines - Plan
|  | Comments | 1: benching; 2: benching; 4: benching; 5: benching; 6: benching
| 5L_W8_STOPE | Lashed | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Sampled | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Reef Marked | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | # of Machines - Actual | 1: 3; 2: 3; 4: 3; 5: 3; 6: 3
# of Machines - Plan
|  | Comments | 1: benching; 2: benching; 4: benching; 5: benching; 6: benching
| 5W11_Conning | Lashed | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Sampled | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Reef Marked | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | # of Machines - Actual | 1: 2; 2: 2; 4: 2; 5: 2; 6: 2
# of Machines - Plan
|  | Comments | 1: slyping; 2: slyping; 4: slyping; 5: conning; 6: conning
| 6L_E1_STOPE | Lashed | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Sampled | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Reef Marked | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
# of Machines - Actual | bar: 1 to 2; 4 to 6
# of Machines - Plan
|  | Comments | 1: benching; 2: benching; 4: benching; 5: benching; 6: benching
| 6L_W1_STOPE | Lashed
Sampled
Reef Marked
# of Machines - Actual
# of Machines - Plan
Comments
| 6L_W2_STOPE | Lashed | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Sampled | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Reef Marked | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | # of Machines - Actual | 1: 5; 2: 5; 4: 5; 5: 5; 6: 5
# of Machines - Plan
|  | Comments | 1: benching; 2: benching; 4: benching, support; 5: benching; 6: benching
| 6L_W3_STOPE | Lashed
Sampled
Reef Marked
# of Machines - Actual
# of Machines - Plan
Comments
| 6L_W4_STOPE | Lashed | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Sampled | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Reef Marked | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | # of Machines - Actual | 1: 4; 2: 4; 4: 2; 5: 3; 6: 3
# of Machines - Plan
|  | Comments | 1: benching; 2: benching; 4: benching; 5: benching; 6: benching
| 6L_W8_STOPE | Lashed | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Sampled | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | Reef Marked | 1: yes; 2: yes; 4: yes; 5: yes; 6: yes
|  | # of Machines - Actual | 1: 3; 2: 3; 4: 0; 5: 3; 6: 3
# of Machines - Plan
|  | Comments | 1: benching; 2: benching; 4: misfire; 5: benching; 6: benching
| 6L_W14_STOPE | Lashed | 4: yes; 5: yes; 6: yes
|  | Sampled | 4: yes; 5: yes; 6: yes
|  | Reef Marked | 4: yes; 5: yes; 6: yes
# of Machines - Actual | bar: 4 to 6
# of Machines - Plan
|  | Comments | 4: slyping; 5: slyping; 6: slyping
| 6L_W15_STOPE | Lashed | 1: yes; 2: yes; 3: yes; 4: yes; 5: yes; 6: yes
|  | Sampled | 1: yes; 2: yes; 3: yes; 4: yes; 5: yes; 6: yes
|  | Reef Marked | 1: yes; 2: yes; 3: yes; 4: yes; 5: yes; 6: yes
|  | # of Machines - Actual | 1: 2; 2: 2; 3: 2; 4: 2; 5: 3; 6: 3
# of Machines - Plan
|  | Comments | 1: slyping; 2: slyping, benching; 3: slyping, support; 4: benching; 5: benching; 6: benching
| 6L_W18_STOPE | Lashed | 1: yes; 2: yes; 3: yes; 4: yes; 5: yes; 6: yes
|  | Sampled | 1: yes; 2: yes; 3: yes; 4: yes; 5: yes; 6: yes
|  | Reef Marked | 1: yes; 2: yes; 3: yes; 4: yes; 5: yes; 6: yes
# of Machines - Actual | bar: 1 to 6
# of Machines - Plan
|  | Comments | 1: slyping; 2: slyping; 3: benching; 4: benching; 5: slyping; 6: slyping
Lashed
Sampled
Reef Marked
# of Machines - Actual
# of Machines - Plan
Comments
Lashed
Sampled
Reef Marked
# of Machines - Actual
# of Machines - Plan
Comments
Lashed
Sampled
Reef Marked
# of Machines - Actual
# of Machines - Plan
Comments
Lashed
Sampled
Reef Marked
# of Machines - Actual
# of Machines - Plan
Comments
Lashed
Sampled
Reef Marked
# of Machines - Actual
# of Machines - Plan
Comments
Lashed
Sampled
Reef Marked
# of Machines - Actual
# of Machines - Plan
Comments | bar: 6

## Ore Accounting Actions
Underground Mining Ore Accounting Action List
Action No | Issue | Action | Category | Responsible Person | Due Date | Date Closed | Status | Memo/ Notes | Actions
1 | Lack of visibility of trucks | Install cameras at strategic points to cover PUG gate, Gate 2 and ROMPAD |  | Stephen | 2025-08-01 | 2025-08-12 | K | In progress: Mufaro and Courage have been tasked to look into the issue. Feedback expected 25/07 | Total Actions | 14
2 | Lack of accuracy on crushing weightometer | Increase calibration frequency for the crushing weightometer |  | Fidelis | 2025-07-03 |  | J | Monitorring and callibration being done if there's a +/-3% callibration. | Completed | 9 | 64.29%
3 | Improved accuracy of hoisted tonnes | Assess loading flask instrumentation- (load cells, flopper gate) |  | Deon | 2025-07-03 |  | J | System is water tight. Callibration of load cells to be done every month. | In progress | 5 | 35.71%
4 | Improved accuracy of hoisted tonnes | Review methods of automating measurement of hoisted tonnes using rope tension |  | Deon | 2025-07-03 | 2025-08-12 | K | Awaiting quote | Overdue | 0 | 0%
5 | Improve accuracy on accounting of tonnage | Survey to conduct weekly measurements of mined stopes |  | Vincent | 2025-08-01 | 2025-08-11 | K | Survey should start weekly reconciliations on areas they can, to start mine wide recon on 1 Aug | Not yet due | 0 | 0%
6 | Lack of accuracy on trammed tonnes | Review Smartrail technology for measurement of trammed tonnes |  | Vincent | 2025-07-25 | 2025-08-15 | K | Revisit and document decision on Smartrail
7 | Inconsistencies between trammed and hoisted tonnage | Introduce a system of accounting for number of cocopans correctly |  | Stephen | 2025-07-20 | 2025-07-21 | J | Cocopan factor revised to 1.2 and trammed tonnage now being reconciled with hoisted tonnage. Variance of 511t as of 21/07 and this is attributed to Lobe Shaft spillage.
8 | Inconsistencies between trammed and hoisted tonnage | Verify cocopan fill factor |  | Stephen | 2025-07-05 | 2025-07-05 | J | Cocopan fill factor revised to 1.2
9 | Lack of accuracy on hoisted tonnes | Install underground surface conveyor weightometer |  | Artwell | 2025-07-17 | 2025-08-30 | K | PO250425. Weightometer asssembly/wiring in progress. Waiting for delivey of PLC Cooling Fan. Installation expected in the week ending 30th of August 2025.
10 | Lack of accuracy on delivered tonnes | Survey to conduct measurements of stockpiles |  | Vincent | 2025-07-03 | 2025-07-04 | J | Stockpile measurements are being done and updated weekly (Every Friday).
11 | Lack of accuracy on reported figures | To make people aware that accuracy is non-negotiable |  | Stephen | 2025-07-03 | 2025-07-05 | J | Trainnings conducted
12 | Improve accuracy on accounting of tonnage | Verifying skip factor and truck fill factor |  | Stephen | 2025-07-03 | 2025-07-08 | J | Trucks being sent to the weigh bridge for verification. (Average of 31t per load)
13 | Inconsistencies of truck counts-(Mining, Geology, Security) | Conduct daily reconciliation of trucks |  | Vincent | 2025-07-04 |  | J | Survey is now responsible for dailly recons starting 7 July. Ticketing system has been introduced for trucks ex-Southwell.
14 | Inconsistencies between broken and hoisted tonnes | Introduce a system of accounting broken tonnage correctly |  | Stephen | 2025-07-05 | 2025-07-08 | J | Bench measurements are ongoing daily, survey now confirming measurements on a weekly bases
|  | Confirm project start date |  | Obed | 2021-02-17 |  | J | Start date will be 1st of March 2021

## D_Drilling
BRECKRIDGE INVESTMENTS | [5 empty] | KEY |  |  | Reason if Actual is RED
Pickstone Underground Mine | [5 empty] | Above Budget |  |  | Planned Maintenance - PM
DIAMOND DRILLING DAILY CONTROL SHEET | [5 empty] | Below Budget |  |  | Breakdown - BD; Flooding - FLD
No Electricity / Water / comp. Air - NE / NW / NCA
Month: | 2025-08-01 | [7 empty] | Standby - SB; Off Duty - OD
Day: | 5 | [7 empty] | Hard / Broken Formation - HF / BF
MTD | Budget | Actual | Variance |  | Shifts | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Surface (m) | 0 | 0 | 0% |  | Surface Budget (m) | 0 | 0 | 0 | 0 | 0
Underground (m) | 248 | 262.8 | 5.968% |  | Surface Actual (m) | 0 | 0 | 0 | 0 | 0
TOTAL METERS (m) | 248 | 262.8 | 5.968% |  | UG Budget (m) | 38 | 38 | 48 | 66 | 58
[5 empty] | UG Actual (m) | 68 | 54.7 | 39.5 | 51 | 49.6
[5 empty] | Budget Meters (m) | 38 | 38 | 48 | 66 | 58
[5 empty] | Actual Meters (m) | 68 | 54.7 | 39.5 | 51 | 49.6
LOCATION | OPERATOR | RIG # |  | MTD | MTD Var | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | Comments
SURFACE | Tandamanzi | #REF! | Budget (m) | 0
|  |  | Actual (m) | 0 | 0%
Reason if Actual is RED
|  | #REF! | Budget (m) | 0
|  |  | Actual (m) | 0 | 0%
Reason if Actual is RED
|  | TMD 13 | Budget (m) | 0
|  |  | Actual (m) | 0 | 0%
Reason if Actual is RED
|  | TOTAL - TMD | TMD - Budget (m) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TMD - Actual (m) | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNDERGROUND | Breckridge | BDU 400 | Budget (m) | 0
|  |  | Actual (m) | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Reason if Actual is RED |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | U2-AW | Budget (m) | 32 |  | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | Actual (m) | 41.3 | 29.06% | 9 | 8.2 | 7 | 8 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reason if Actual is RED
|  | U3-9BQ | Budget (m) | 50 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10
|  |  | Actual (m) | 39.5 | -21% | 15.5 | 11.5 | 8.5 | 3.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reason if Actual is RED
|  | U3-9BQ2 | Budget (m) | 20 |  | Moving | Comissioning | Comissioning | 10 | 10 | Moving | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | PM | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | PM | Moving
|  |  | Actual (m) | 25 | 25% | 0 | 2 | 5.5 | 12.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reason if Actual is RED
|  | U3-9BQ3 | Budget (m) | 30 |  | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10
|  |  | Actual (m) | 0 | -100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reason if Actual is RED
|  | TOTAL - BRK | BRK - Budget (m) | 132 |  | 18 | 18 | 28 | 38 | 30 | 20 | 38 | 38 | 28 | 38 | 30 | 38 | 28 | 38 | 48 | 38 | 28 | 28 | 30 | 28 | 38 | 38 | 38 | 38 | 28 | 38 | 28 | 38 | 38 | 28 | 28
|  |  | BRK - Actual (m) | 105.8 | -19.85% | 24.5 | 21.7 | 21 | 24 | 14.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HBF
| JBC | JBC 01 | Budget (m) | 50 |  | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0
|  |  | Actual (m) | 61 | 22% | 9.5 | 13 | 10.5 | 12 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Reason if Actual is RED |  |  |  | NCA
|  | JBC 02 | Budget (m) | 50 |  | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  |  | Actual (m) | 47 | -6% | 20 | 11 | 3 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reason if Actual is RED
|  | JBC 03 | Budget (m) | 32 |  | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8
|  |  | Actual (m) | 49 | 53.12% | 14 | 9 | 5 | 9 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reason if Actual is RED
|  | TOTAL - JBC | JBC - Budget (m) | 132 |  | 28 | 28 | 20 | 28 | 28 | 28 | 8 | 28 | 28 | 28 | 20 | 28 | 28 | 8 | 18 | 28 | 28 | 28 | 20 | 20 | 28 | 18 | 28 | 18 | 28 | 28 | 28 | 20 | 28 | 18 | 8
|  |  | JBC - Actual (m) | 157 | 18.94% | 43.5 | 33 | 18.5 | 27 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on J34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilling fractured rock formation.
Note on J37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No water for 2 hours (fixing stuffing box and burst water hose).
Note on K37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilling in fractured rock formation.
Note on L37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stuck rods (drilling in fractured rock formation).
Note on L40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No water for 5 hours and low compressed air for 1 hour.
Note on L43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Site not ready.
Note on J52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The rig was under maintenance (rubber buffer breakdown).
Note on K52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilling in hard and fractured rock formation.
Note on L52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilling in hard and fractured rock formation.

## Development
| BRECKRIDGE INVESTMENTS |  |  |  |  | KEY
| Pickstone Underground Mine |  |  |  |  | Above Budget
| Development |  |  |  |  | Below Budget |  |  | Post a COMMENT with REASON if Actual is RED
| Month: | 2025-08-01 |  |  | Shifts | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Day: | 6 |  |  | Budget ROM Meters (m) | 32.1 | 32.1 | 0 | 33 | 33.9 | 33.9
[5 empty] | Actual ROM Meters (m) | 33.2 | 34.7 | 0 | 35.1 | 34.9 | 17.3
| MTD | Budget | Actual | Variance | Budget CAPEX Meters (m) | 3.6 | 3.6 | 0.9 | 3.6 | 2.7 | 4.9
| ROM Metres (m) | 165 | 155.2 | -5.939% | Actual CAPEX Meters (m) | 5.7 | 4.9 | 2.9 | 3.8 | 4 | 3.8
| CAPEX Meters (m) | 19.3 | 25.1 | 30.05% | Budget Meters (m) | 35.7 | 35.7 | 0.9 | 36.6 | 36.6 | 38.8
| TOTAL METERS (m) | 184.3 | 180.3 | -2.17% | Actual Meters (m) | 38.9 | 39.6 | 2.9 | 38.9 | 38.9 | 21.1
| Number of Blasts | 151 | 148 | -1.987% | Budget # of Blasts | 29 | 29 | 1 | 30 | 30 | 32
| Advance per Blast (m) | 1.0927 | 1.0486 | -4.033% | Actual # of Blasts | 34 | 32 | 3 | 30 | 31 | 18
[5 empty] | Budget Advance (m/blst) | 1.1069 | 1.1069 | 0 | 1.1 | 1.13 | 1.0594
[5 empty] | Ave. Advance (m/blst) | 0.97647 | 1.0844 | 0 | 1.17 | 1.1258 | 0.96111
45 | PRIORITY | Development_ends |  | METERS | MTD | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | Comments
| 1 | 3L_E9_HAULAGE_EAST |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 6.1 | 1.4 | 1.3 |  | 1.7 | 1.7
|  |  |  | Variance (%) | -23.75%
| 2 | 3L_W28_SL_2_EAST |  | Budget (m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
| 2 | 3L_W29_RAISE |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 3.4 | 0.7 | 0.9 |  | 0.9 | 0.9
|  |  |  | Variance (%) | -24.44%
| 1 | 4L_E13_HAULAGE |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 7.1 | 1.7 | 1.8 |  | 1.8 | 1.8
|  |  |  | Variance (%) | -11.25%
| 1 | 4L_W29_HAULAGE |  | Budget (m) | 6.5 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 0 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 1.13 | 1.3 | 1.3 | 1.3 | 1.3 | 0
|  |  |  | Actual (m) | 4.1 | 1.3 | 1.4 |  |  | 1.4
|  |  |  | Variance (%) | -36.92%
| 2 | 5L_W11_SL_1_WEST' |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 5.6 | 1.6 | 1.3 |  | 1.8 | 0.9
|  |  |  | Variance (%) | -30%
| 2 | 5L_W13_CROSS_CUT |  | Budget (m) | 6.5 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 0 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 4.8 | 0.8 | 1.3 |  | 1.4 | 1.3
|  |  |  | Variance (%) | -26.15%
| 2 | 5L_W14_CDRIVE_WEST |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 3.8 |  | 1.3 |  | 0.9 | 1.6
|  |  |  | Variance (%) | -52.5%
| 1 | 5L_W14_HAULAGE |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 6.5 | 1.6 | 1.6 |  | 1.7 | 1.6
|  |  |  | Variance (%) | -18.75%
| 1 | 5L_W2_CROSS_CUT |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 6.1 | 1.6 | 1.6 |  | 1.3 | 1.6
|  |  |  | Variance (%) | -23.75%
| 1 | 5L_W26_HOISTROOM |  | Budget (m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
| 2 | 6LA_W5_DRIVE_EAST |  | Budget (m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0
|  |  |  | Actual (m) | 1.6 | 1.6
|  |  |  | Variance (%) | 0%
| 2 | 6LA_W2_SL1_DRIVE |  | Budget (m) | 6.5 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 0 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0
|  |  |  | Actual (m) | 4.9 | 0.9 | 1.3 |  | 1.4 | 1.3
|  |  |  | Variance (%) | -24.62%
| 2 | 6LA_W4_DRIVE_EAST |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 4.8 |  | 1.6 |  | 1.6 | 1.6
|  |  |  | Variance (%) | -40%
| 2 | 6LA_W3_RAISE |  | Budget (m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
| 2 | 6L__W14_RAISE |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 4.4 | 0.9 | 1.3 |  | 1.3 | 0.9
|  |  |  | Variance (%) | -2.222%
| 2 | 6LA_W14_DRIVE_WEST |  | ` | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0
|  |  |  | Actual (m) | 0.8 | 0.8
|  |  |  | Variance (%) | 0%
| 2 | 6LA_W19_DRIVE_WEST |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 5.8 | 1.4 |  |  | 1.6 | 1.5 | 1.3
|  |  |  | Variance (%) | -27.5%
| 1 | 6LW24_BYPASS |  | Budget (m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
| 2 | 7L_E1_OREPASS |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 4.5 | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9
|  |  |  | Variance (%) | 0%
| 2 | 7L_E1_TWAY |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 5.7 | 0.9 | 1.5 |  | 0.9 | 0.9 | 1.5
|  |  |  | Variance (%) | 26.67%
| 2 | 7L_W2_SL_2_WEST |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 7.7 | 1.4 | 1.6 |  | 1.6 | 1.6 | 1.5
|  |  |  | Variance (%) | -3.75%
| 2 | 8L_W17_SL_2_WEST |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 7.1 | 0.9 | 1.6 |  | 1.6 | 1.5 | 1.5
|  |  |  | Variance (%) | -11.25%
| 2 | 8L_W14_TWAY |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 7.3 | 1.5 | 1.3 |  | 1.6 | 1.5 | 1.4
|  |  |  | Variance (%) | 62.22%
| 2 | 8L_W15_SL_3_WEST |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 7.8 | 1.6 | 1.6 |  | 1.6 | 1.6 | 1.4
|  |  |  | Variance (%) | -2.5%
| 2 | 8L_W15_SLOT |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 4.8 | 0.9 | 0.9 |  | 1 | 1 | 1
|  |  |  | Variance (%) | 6.667%
| 1 | 8L_W16_HUALAGE_WEST |  | Budget (m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 1.4 | 1.4
|  |  |  | Variance (%) | 0%
| 2 | 8L_W16_TWAY |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 4.5 | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9
|  |  |  | Variance (%) | 0%
| 2 | 8L_W16_SL_3_WEST |  | Budget (m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
| 2 | 8L_W16_OREPASS |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 1.8 | 0.9 |  |  |  |  | 0.9
|  |  |  | Variance (%) | -60%
| 2 | 8L_W14_OREPASS |  | Budget (m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 0.9 |  | 0.9
|  |  |  | Variance (%) | 0%
| 2 | 10L_E2_RAISE |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 2.7 | 0.9 | 0.9 |  | 0.9
|  |  |  | Variance (%) | -40%
| 2 | 10L_E2_C_DRIVE |  | Budget (m) | 8 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 7.8 | 1.6 | 1.4 |  | 1.6 | 1.6 | 1.6
|  |  |  | Variance (%) | -2.5%
| 2 | 10L_E1_RAISE |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 4.3 | 0.9 | 0.9 |  | 0.9 |  | 1.6
|  |  |  | Variance (%) | -4.444%
| 2 | 10L_W8_RAISE |  | Budget (m) | 2.7 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 4.5 | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9
|  |  |  | Variance (%) | 66.67%
| 2 | 10LW7_BOX_RSE |  | Budget (m) | 1.8 | 0 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 1.8 |  |  |  |  | 0.9 | 0.9
|  |  |  | Variance (%) | 0%
| 2 | 10LW7_CDRIVE_EAST |  | Budget (m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  | 4L_W7 WASTE PASS ACCESS |  | Budget (m) | 0
|  |  |  | Actual (m) | 5.1 | 1.3 | 1.1 |  | 1.7 | 1
|  |  |  | Variance (%) | 0%
|  | 10L_W7B_BOX RSE |  | Budget (m) | 0
|  |  |  | Actual (m) | 0.9 |  |  |  |  | 0.9
|  |  |  | Variance (%) | 0%
|  | 8L_W17_SL_1_WEST |  | Budget (m) | 0
|  |  |  | Actual (m) | 4.8 |  | 1.6 |  | 1.6 | 1.6
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  | #REF! |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  | #REF! |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
Whaleside
| 1 | 9L_E3_OREPASS |  | Budget (m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
| 1 | 9L_E3_WASTEPASS |  | Budget (m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
| 1 | 10L_E3_OREPASS |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 3.5 | 0.8 |  |  | 0.9 | 0.9 | 0.9
|  |  |  | Variance (%) | -22.22%
| 1 | 10L_E3_WASTEPAS |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
|  |  |  | Actual (m) | 5.4 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
|  |  |  | Variance (%) | 20%
| 1 | 10L_W15_OREPASS |  | Budget (m) | 3.6 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 4.4 | 0.9 | 0.9 |  | 0.8 | 0.9 | 0.9
|  |  |  | Variance (%) | 22.22%
| 1 | 10L_W15_WASTEPASS |  | Budget (m) | 0.9 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 1.8 | 0.9 | 0.9
|  |  |  | Variance (%) | 100%
| 1 | 10L_E7_DAM |  | Budget (m) | 1.3 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1.3 | 0 | 0 | 0 | 0 | 1.3 | 1.3 | 1.3 | 0 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 0 | 0
|  |  |  | Actual (m) | 7.4 | 1.3 | 1.3 | 1.2 | 1.2 | 1.3 | 1.1
|  |  |  | Variance (%) | 469.2%
| 1 | Venning Shaft Overrun |  | Budget (m) | 4.5 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (m) | 2.6 | 0.9 | 0.9 | 0.8
|  |  |  | Variance (%) | -42.22%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
|  |  |  | Budget (m) | 0
|  |  |  | Actual (m) | 0
|  |  |  | Variance (%) | 0%
Note on K32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Incomplete drilling due to SHEQ incident.
Note on L35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Replaced with 5L W13B Box raise which has a higher priority
Note on K41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved the machine to 5L W13B Box Raise
Note on L41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilled and blasted 6LA W14 DD cubby
Note on K47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short length drilled, end is turning to change direction.
Note on H56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5L W13 SL2 North
Note on L56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mined Hoist Chamber Crosscut
Note on H65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mined 5L W13 Box Raise
Note on I65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilling DD Cubbies
Note on K65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilling DD Cubbies
Note on L65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilling DD Cubbies
Note on H68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6LA W14 DD slyp
Note on L71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Poor advance
Note on M71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilled a 1.5m hole depth due to water challenges
Note on I80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mined 7L E1 condrive west
Note on M80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mined 7L E1 con drive
Note on M83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Poor advance
Note on H86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD cubby Slyping 8L W 17 SL2
Note on L86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mined 8L W 16 DD Cubby SL2
Note on M86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Poor advance
Note on K89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mined 8L W SL4 DW
Note on L89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mined 8L W SL4 DW
Note on M89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mined 8L W SL4 DW
Note on M92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Poor advance
Note on K107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Box construction in progress. Replaced the end with 8L W17 SL1 West.
Note on L107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Box construction in progress. Replaced the end with 8L W17 SL1 West.
Note on L113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mined 10L W 7B Raise
Note on M113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Machined slyped 10L W 4 DD Cubby
Note on L119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Incomplete drilling because of water challenges due to pipe burst in the Venning shaft
Note on M119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mined 10L E 2 C-drive east
Note on K216: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Second lashing shift.
Note on M216: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be confirmed. Lashing still in progress.

## Generation
BRECKRIDGE INVESTMENTS
| Pickstone Underground Mine |  |  | GRADE LEGEND
| Ore Generation |  |  | < 0.60 Waste
0.60 - 1.60 Low Grade
| Month: | 2025-08-01 |  | 1.60 - 2.00 Medium Grade
| Day: | 6 |  | > 2.00 High Grade
| BROKEN - MTD |  | Actual |  |  | Plan |  |  | Variance |  |  | % Variance to Plan
| Level | Stope ID | Tonnes(t) | Grade (g/t) | Gold (Kg) | Tonnes(t) | Grade (g/t) | Gold (Kg) | Tonnes(t) | Grade (g/t) | Gold (Kg) | Tonnes(t) | Grade (g/t) | Gold (Kg)
| 1 | 1L W28 STOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0%
|  | Total Section | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
| 3 | 3L_W23A STOPE | 201 | 1.1743 | 0.23603 | 210 | 1.986 | 0.41706 | -9 | -0.8117 | -0.18103 | -4.286% | -40.87% | -43.41%
|  | 3L_W23B STOPE | 717 | 2.5612 | 1.8364 | 420 | 1.986 | 0.83411 | 297 | 0.57522 | 1.0023 | 70.71% | 28.96% | 120.2%
|  | 3L_W24B STOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0%
|  | Total Section | 918 | 2.2575 | 2.0724 | 630 | 1.986 | 1.2512 | 288 | 0.27155 | 0.82124 | 45.71% | 13.67% | 65.64%
| 4 | 4L_W26 STOPE | 432 | 3.0038 | 1.2977 | 420 | 1.9463 | 0.81743 | 12 | 1.0576 | 0.48023 | 2.857% | 54.34% | 58.75%
[5 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0%
|  | Total Section | 432 | 3.0038 | 1.2977 | 420 | 1.9463 | 0.81743 | 12 | 1.0576 | 0.48023 | 2.857% | 54.34% | 58.75%
| 5 |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0%
|  | 5L_W11 STOPE | 450 | 1.9964 | 0.89837 | 420 | 1.7477 | 0.73402 | 30 | 0.24871 | 0.16435 | 7.143% | 14.23% | 22.39%
|  | 5L_W8 STOPE | 618 | 3.2246 | 1.9928 | 630 | 1.8271 | 1.1511 | -12 | 1.3975 | 0.84171 | -1.905% | 76.49% | 73.12%
|  | Total Section | 1068 | 2.7071 | 2.8911 | 1050 | 3.5748 | 1.8851 | 18 | 1.6462 | 1.0061 | 5.238% | 90.72% | 95.51%
| 6 | 6L_E1 STOPE | 320 | 3.5495 | 1.1358 | 210 | 3.1379 | 0.65895 | 110 | 0.41165 | 0.47689 | 52.38% | 13.12% | 72.37%
|  | 6L_W1 STOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
|  | 6L_W2 STOPE | 1049 | 4.6257 | 4.8524 | 840 | 2.5421 | 2.1353 | 209 | 2.0837 | 2.7171 | 24.88% | 81.97% | 127.2%
|  | 6L_W3 STOPE | 523 | 3.4429 | 1.8007 | 630 | 2.3832 | 1.5014 | -107 | 1.0597 | 0.29925 | -16.98% | 44.47% | 19.93%
|  | 6L_W4 STOPE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
|  | 6L_W8 STOPE | 527 | 1.6287 | 0.85834 | 630 | 2.7804 | 1.7516 | -103 | -1.1516 | -0.8933 | -16.35% | -41.42% | -51%
|  | 6L_W13 STOPE | 88 | 4.2881 | 0.37735 | 210 | 1.986 | 0.41706 | -122 | 2.3021 | -0.039706 | -58.1% | 115.9% | -9.521%
|  | 6L_W15_STOPE | 457 | 1.5617 | 0.71368 | 420 | 1.7477 | 0.73402 | 37 | -0.186 | -0.020339 | 8.81% | -10.64% | -2.771%
|  | 6L_W18_STOPE | 331 | 2.1303 | 0.70513 | 420 | 2.7804 | 1.1678 | -89 | -0.65007 | -0.46263 | -21.19% | -23.38% | -39.62%
|  | Total Section | 3295 | 3.1695 | 10.4434 | 3360 | 2.4899 | 8.3661 | -65 | 0.67954 | 2.0772 | -1.935% | 27.29% | 24.83%
| Grand Total |  | 5713 | 2.924 | 16.7046 | 5460 | 2.2564 | 12.3198 | 253 | 0.66758 | 4.3848 | 4.634% | 29.59% | 35.59%
`

## Stoping
| BRECKRIDGE INVESTMENTS | [5 empty] | KEY |  |  | GRADE LEGEND |  |  |  |  | Reason if Actual is RED
| Pickstone Underground Mine | [5 empty] | Above Budget |  |  | < 0.60 Waste |  |  |  |  | Misfire - MF
| Stoping | [5 empty] | Below Budget |  |  | 0.60 - 1.60 Low Grade |  |  |  |  | Internal Waste - IW
[10 empty] | 1.60 - 2.00 Medium Grade |  |  |  |  | Instope Scaling - IS
| Month: | 2025-08-01 | [7 empty] | > 2.00 High Grade |  |  |  |  | Reef Pinched - RP
| Day: | 6 | [12 empty] | Barren BIF - BB
| MTD | Budget | Actual | Variance |  | Shifts | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Tonnes Blasted | 5460 | 5713 | 4.634% |  | Daily Budget (t) | 910 | 910 | 910 | 910 | 910 | 910
| Grade (g/t) | 2.2564 | 2.924 | 29.59% |  | Daily Actual (t) | 926 | 879 | 965 | 977 | 979 | 987
| Gold (kg) | 12.3198 | 16.7046 | 35.59% |  | Daily Budget (g/t) | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564
[6 empty] | Daily Actual (g/t) | 3.5549 | 3.3304 | 2.9584 | 3.4358 | 1.5282 | 2.8142
[6 empty] | Daily Budget (kg) | 2.0533 | 2.0533 | 2.0533 | 2.0533 | 2.0533 | 2.0533
[6 empty] | Daily Actual (kg) | 3.2919 | 2.9274 | 2.8548 | 3.3567 | 1.4961 | 2.7777
16 | Priority | Stopes |  |  | MTD | MTD Var | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | Comments
| 1 | 1L W28 STOPE | Tonnes | Budget (t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (t) | 0 | 0%
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (g/t) | 0 | 0%
|  |  | Gold | Budget (kg) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 3L_W23A STOPE | Tonnes | Budget (t) | 210 |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
|  |  |  | Actual (t) | 201 | -4.286% | 44 | 39 | 40 | 39 | 39
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.986 |  | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 0 | 0 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986
|  |  |  | Actual (g/t) | 1.1743 | -40.87% | 1.02 | 1.61 | 1.61 | 1.36 | 0.28
|  |  | Gold | Budget (kg) | 0.41706 |  | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0 | 0 | 0.069509 | 0.069509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804
|  |  |  | Actual (kg) | 0.23603 | -43.41% | 0.04488 | 0.06279 | 0.0644 | 0.05304 | 0.01092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 3L_W23B STOPE | Tonnes | Budget (t) | 420 |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
|  |  |  | Actual (t) | 717 | 70.71% | 124 | 114 | 114 | 119 | 123 | 123
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.986 |  | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 0 | 0 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986
|  |  |  | Actual (g/t) | 2.5612 | 28.96% | 1.95 | 1.41 | 1.41 | 3.37 | 3.62 | 3.47
|  |  | Gold | Budget (kg) | 0.83411 |  | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0 | 0 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902
|  |  |  | Actual (kg) | 1.8364 | 120.2% | 0.2418 | 0.16074 | 0.16074 | 0.40103 | 0.44526 | 0.42681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 3L_W24B STOPE | Tonnes | Budget (t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (t) | 0 | 0% | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (g/t) | 0 | 0%
|  |  | Gold | Budget (kg) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 4L_W26 STOPE | Tonnes | Budget (t) | 420 |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
|  |  |  | Actual (t) | 432 | 2.857% | 42 | 75 | 76 | 71 | 87 | 81
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.9463 |  | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 0 | 0 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463
|  |  |  | Actual (g/t) | 3.0038 | 54.34% | 4.12 | 2.52 | 2.52 | 3.38 | 1.94 | 4.14
|  |  | Gold | Budget (kg) | 0.81743 |  | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0 | 0 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624
|  |  |  | Actual (kg) | 1.2977 | 58.75% | 0.17304 | 0.189 | 0.19152 | 0.23998 | 0.16878 | 0.33534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Tonnes | Budget (t) | 0
|  |  |  | Actual (t) | 0 | 0%
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 0
|  |  |  | Actual (g/t) | 0 | 0%
|  |  | Gold | Budget (kg) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Tonnes | Budget (t) | 0
|  |  |  | Actual (t) | 0 | 0%
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 0
|  |  |  | Actual (g/t) | 0 | 0%
|  |  | Gold | Budget (kg) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 5L_W11 STOPE | Tonnes | Budget (t) | 420 |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
|  |  |  | Actual (t) | 450 | 7.143% | 35 | 66 | 72 | 70 | 81 | 126
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.7477 |  | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 0 | 0 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477
|  |  |  | Actual (g/t) | 1.9964 | 14.23% | 1.46 | 4.54 | 4.54 | 2.98 | 0.15
|  |  | Gold | Budget (kg) | 0.73402 |  | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0 | 0 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234
|  |  |  | Actual (kg) | 0.89837 | 22.39% | 0.0511 | 0.29964 | 0.32688 | 0.2086 | 0.01215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 5L_W8 STOPE | Tonnes | Budget (t) | 630 |  | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 0 | 0 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
|  |  |  | Actual (t) | 618 | -1.905% | 127 | 122 | 108 | 106 | 79 | 76
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.8271 |  | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 0 | 0 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271
|  |  |  | Actual (g/t) | 3.2246 | 76.49% | 3.88 | 4.35 | 4.35 | 1.39 | 3.14 | 1.37
|  |  | Gold | Budget (kg) | 1.1511 |  | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0 | 0 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185
|  |  |  | Actual (kg) | 1.9928 | 73.12% | 0.49276 | 0.5307 | 0.4698 | 0.14734 | 0.24806 | 0.10412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_E1 STOPE | Tonnes | Budget (t) | 210 |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
|  |  |  | Actual (t) | 320 | 52.38% | 60 | 63 |  | 75 | 48 | 74
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 3.1379 |  | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 0 | 0 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379
|  |  |  | Actual (g/t) | 3.5495 | 13.12% | 1.71 | 3.57 |  | 5.71 | 0.95 | 4.52
|  |  | Gold | Budget (kg) | 0.65895 |  | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0 | 0 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.56 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982
|  |  |  | Actual (kg) | 1.1358 | 72.37% | 0.1026 | 0.22491 | 0 | 0.42825 | 0.0456 | 0.33448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W1 STOPE | Tonnes | Budget (t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (t) | 0 | 0%
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (g/t) | 0 | 0%
|  |  | Gold | Budget (kg) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W2 STOPE | Tonnes | Budget (t) | 840 |  | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 0 | 0 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
|  |  |  | Actual (t) | 1049 | 24.88% | 204 | 155 | 165 | 190 | 165 | 170
Reason if Actual is RED
|  |  |  | Budget (g/t) | 2.5421 |  | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 0 | 0 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421
|  |  |  | Actual (g/t) | 4.6257 | 81.97% | 6.9 | 5.96 | 5.96 | 3.86 | 1.34 | 3.43
|  |  | Gold | Budget (kg) | 2.1353 |  | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0 | 0 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589
|  |  |  | Actual (kg) | 4.8524 | 127.2% | 1.4076 | 0.9238 | 0.9834 | 0.7334 | 0.2211 | 0.5831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W3 STOPE | Tonnes | Budget (t) | 630 |  | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 0 | 0 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
|  |  |  | Actual (t) | 523 | -16.98% | 92 | 87 | 60 | 96 | 90 | 98
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 2.3832 |  | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 0 | 0 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832
|  |  |  | Actual (g/t) | 3.4429 | 44.47% | 4.58 | 3.33 | 3.33 | 2.02 | 2.32 | 4.97
|  |  | Gold | Budget (kg) | 1.5014 |  | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0 | 0 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023
|  |  |  | Actual (kg) | 1.8007 | 19.93% | 0.42136 | 0.28971 | 0.1998 | 0.19392 | 0.2088 | 0.48706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W4 STOPE | Tonnes | Budget (t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (t) | 0 | 0%
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (g/t) | 0 | 0%
|  |  | Gold | Budget (kg) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W8 STOPE | Tonnes | Budget (t) | 630 |  | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 0 | 0 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
|  |  |  | Actual (t) | 527 | -16.35% | 83 |  | 195 | 33 | 81 | 135
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 2.7804 |  | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 0 | 0 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804
|  |  |  | Actual (g/t) | 1.6287 | -41.42% | 2.39 | 1.27 | 1.27 | 1.67 | 0.86 | 2.13
|  |  | Gold | Budget (kg) | 1.7516 |  | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0 | 0 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194
|  |  |  | Actual (kg) | 0.85834 | -51% | 0.19837 | 0 | 0.24765 | 0.05511 | 0.06966 | 0.28755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W13 STOPE | Tonnes | Budget (t) | 210 |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
|  |  |  | Actual (t) | 88 | -58.1% |  |  |  | 51 | 37
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.986 |  | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 0 | 0 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986
|  |  |  | Actual (g/t) | 4.2881 | 115.9% |  |  |  | 7 | 0.55
|  |  | Gold | Budget (kg) | 0.41706 |  | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0 | 0 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509
|  |  |  | Actual (kg) | 0.37735 | -9.521% | 0 | 0 | 0 | 0.357 | 0.02035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W15_STOPE | Tonnes | Budget (t) | 420 |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
|  |  |  | Actual (t) | 457 | 8.81% | 78 | 88 | 82 | 53 | 96 | 60
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.7477 |  | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 0 | 0 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477
|  |  |  | Actual (g/t) | 1.5617 | -10.64% | 1.48 | 1.58 | 1.58 | 3.12 | 0.23 | 2.37
|  |  | Gold | Budget (kg) | 0.73402 |  | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0 | 0 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234
|  |  |  | Actual (kg) | 0.71368 | -2.771% | 0.11544 | 0.13904 | 0.12956 | 0.16536 | 0.02208 | 0.1422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 |  | Tonnes | Budget (t) | 420 |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
|  |  |  | Actual (t) | 331 | -21.19% | 37 | 70 | 53 | 74 | 53 | 44
Reason if Actual is RED
|  | 6L_W18_STOPE | Grade | Budget (g/t) | 2.7804 |  | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 0 | 0 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804
|  |  |  | Actual (g/t) | 2.1303 | -23.38% | 1.16 | 1.53 | 1.53 | 5.05 | 0.44 | 1.75
|  |  | Gold | Budget (kg) | 1.1678 |  | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0 | 0 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463
|  |  |  | Actual (kg) | 0.70513 | -39.62% | 0.04292 | 0.1071 | 0.08109 | 0.3737 | 0.02332 | 0.077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on H29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mining to pay zone after the collapse
Note on I29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Grade improving
Note on K29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Low grade patch
Note on I36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Low grade patch but grade to improve
Note on H71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Grade improving as we shape the cone
Note on L76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reduced bench area after first cut holed
Note on K78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waste inclusion of chlorite schist on the bench
Note on J83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Predrilled incomplete due to drilling water pipe
Note on H85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Grade affected by the sericite schist being mined to avoid ground collapses
Note on L85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Passing a lowly paying zone, grade to improve
Note on L99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: lowly mineralised zone, grade to improve going down
Note on K104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: reduced bench area due to reef pinching
Note on L104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reduced bench area, reef pinching
Note on I118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilled incomplete due to drilling water pipe breakdown at 1155
Note on K118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Machine moved to W13 due to grade complications, current mineralization not paying well
Note on L118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mineralized zone pinching, reduced number of machines
Note on I120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Low grade portion of the northern contact, grade to improve.
Note on K120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inclusion of chlorite schist middling
Note on L120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Slipping have reached pay limit
Note on J125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cone drive slyping starting on 04/08/25
Note on K127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: was sampled on the 17th of July and not drilled for blasting, the grade was 7g/t
Note on L127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Slipping catwalk to open up west bench before commencing eastern bench
Note on K132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6LW15 sub2 stopped due to sour grades, only one machine working in sub1 which is paying
Note on L132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sub2 stopped, poorly mineralized; only sub1 being worked
Note on H134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Opening a new bench cut by slyping to well mineralised zone
Note on I134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To stop mining sublevel 2 and continue with sublevel 1
Note on L134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Passing poorly mineralised zone
Note on H141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mining to pay zone as we shape the cone
Note on I141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Samples on repeat
Note on L141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Slipping stopped have reached pay limit

## Tramming
| BRECKRIDGE INVESTMENTS | [5 empty] | KEY |  |  | GRADE LEGEND |  |  |  |  | Reason if Actual is RED
| Pickstone Underground Mine | [5 empty] | Above Budget |  |  | < 0.60 Waste |  |  |  |  | Loco Breakdown - LcBD
| Tramming | [5 empty] | Below Budget |  |  | 0.60 - 1.60 Low Grade |  |  |  |  | Flooding - FLD
[10 empty] | 1.60 - 2.00 Medium Grade |  |  |  |  | Awaiting Assay Results - AAR
| Month: | 2025-08-01 | [7 empty] | > 2.00 High Grade |  |  |  |  | No Sample - NS
| Day: | 6 | [12 empty] | Reduced Draw - RD; Blockages - BLKG
| MTD | Budget | Actual | Variance |  | Shifts | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Trammed (t) | 5460 | 4925 | -9.799% |  | Daily Budget (t) | 910 | 910 | 910 | 910 | 910 | 910
| Grade (g/t) | 2.1988 | 2.6412 | 20.12% |  | Daily Actual (t) | 758 | 1006 | 960 | 795.5 | 947.5 | 458
| Gold (kg) | 12.0057 | 13.0078 | 8.348% |  | Daily Budget (g/t) | 1.9111 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564
[6 empty] | Daily Actual (g/t) | 2.2936 | 3.3518 | 3.1195 | 2.8487 | 2.7826 | 0
[6 empty] | Daily Budget (kg) | 1.7391 | 2.0533 | 2.0533 | 2.0533 | 2.0533 | 2.0533
[6 empty] | Daily Actual (kg) | 1.7386 | 3.3719 | 2.9947 | 2.2661 | 2.6365 | 0
15 | PRIORITY | BOX ID |  |  | MTD | MTD Var | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | COMMENTS
| 1 |  | Tonnes | Budget (t) | 0
|  |  |  | Actual (t) | 0 | 0% | [8 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 0
|  |  |  | Actual (g/t) | 0 | 0%
|  |  | Gold | Budget (kg) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 3L_W23B STOPE | Tonnes | Budget (t) | 420 |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
|  |  |  | Actual (t) | 0 | -100%
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.986 |  | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 0 | 0 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986
|  |  |  | Actual (g/t) | 0 | -100%
|  |  | Gold | Budget (kg) | 0.83411 |  | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0 | 0 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902 | 0.13902
|  |  |  | Actual (kg) | 0 | -100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 3L_W24B STOPE | Tonnes | Budget (t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (t) | 0 | 0%
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (g/t) | 0 | 0%
|  |  | Gold | Budget (kg) | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 4L_W26 STOPE | Tonnes | Budget (t) | 420 |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
|  |  |  | Actual (t) |  | -100% | 216 | 228 | 234 | 228 | 198 | 240
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.9463 |  | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 0 | 0 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463
|  |  |  | Actual (g/t) | 0 | -100% | 1.94 | 1.47 | 1.97 | 2.82 | 1.36
|  |  | Gold | Budget (kg) | 0.81743 |  | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0 | 0 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624 | 0.13624
|  |  |  | Actual (kg) | 2.1274 | 160.3% | 0.41904 | 0.33516 | 0.46098 | 0.64296 | 0.26928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 3L_W23A STOPE | Tonnes | Budget (t) | 210 |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
|  |  |  | Actual (t) |  | -100%
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.986 |  | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 0 | 0 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986
|  |  |  | Actual (g/t) | 0 | -100%
|  |  | Gold | Budget (kg) | 0.41706 |  | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0 | 0 | 0.069509 | 0.069509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804 | 0.27804
|  |  |  | Actual (kg) | 0 | -100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 5L_W11 STOPE | Tonnes | Budget (t) | 420 |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
|  |  |  | Actual (t) | 337 | -19.76% | 50 | 76 | 34 | 36 | 55 | 86
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.4564 |  | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 0 | 0 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477
|  |  |  | Actual (g/t) | 0.83398 | -42.74% | 2.29 | 0.84 | 0.94 | 0.3 | 1.09
|  |  | Gold | Budget (kg) | 0.61168 |  | 0 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0 | 0 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | . | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234
|  |  |  | Actual (kg) | 0.28105 | -54.05% | 0.1145 | 0.06384 | 0.03196 | 0.0108 | 0.05995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 5L_W8 STOPE |  | Budget (t) | 630 |  | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 0 | 0 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
|  |  |  | Actual (t) | 873 | 38.57% | 144 | 114 | 164 | 164 | 155 | 132
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.5226 |  | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 0 | 0 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271
|  |  |  | Actual (g/t) | 2.8526 | 87.35% | 2.29 | 2.28 | 5.7 | 3.98 | 2.02
|  |  | Gold | Budget (kg) | 0.95923 |  | 0 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0 | 0 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185 | . | 0.19185 | 0.19185 | 0.19185 | 0.19185 | 0.19185
|  |  |  | Actual (kg) | 2.4903 | 159.6% | 0.32976 | 0.25992 | 0.9348 | 0.65272 | 0.3131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_E1 STOPE | Tonnes | Budget (t) | 210 |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 70
|  |  |  | Actual (t) | 171 |  |  | 45 | 22.5 | 49.5 | 54
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 3.1379 |  | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 0 | 0 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379
|  |  |  | Actual (g/t) | 4.2834 | 36.51% |  | 3.41 | 3.54 | 4.35 | 5.26
|  |  | Gold | Budget (kg) | 0.65895 |  | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0 | 0 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.10982 | 0.21965
|  |  |  | Actual (kg) | 0.73246 | 11.16% | 0 | 0.15345 | 0.07965 | 0.21532 | 0.28404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W1 STOPE | Tonnes | Budget (t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (t) | 0 | 0%
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (g/t) | 0 | 0%
|  |  | Gold | Budget (kg) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W2 STOPE | Tonnes | Budget (t) | 840 |  | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 0 | 0 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
|  |  |  | Actual (t) | 1184.5 | 41.01% | 166.5 | 279 | 267 | 196.5 | 275.5
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 2.5421 |  | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 0 | 0 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421
|  |  |  | Actual (g/t) | 3.6779 | 44.68% | 2.53 | 7 | 1.85 | 2.19 | 3.84
|  |  | Gold | Budget (kg) | 2.1353 |  | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0 | 0 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589 | 0.35589
|  |  |  | Actual (kg) | 4.3564 | 104% | 0.42124 | 1.953 | 0.49395 | 0.43033 | 1.0579 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W3 STOPE | Tonnes | Budget (t) | 630 |  | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 0 | 0 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
|  |  |  | Actual (t) | 591 | -6.19% | 114 | 177 | 145.5 | 45 | 109.5
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 2.3832 |  | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 0 | 0 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832
|  |  |  | Actual (g/t) | 3.4994 | 46.84% | 2.64 | 2.29 | 5.76 | 2.49 | 3.76
|  |  | Gold | Budget (kg) | 1.5014 |  | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0 | 0 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023 | 0.25023
|  |  |  | Actual (kg) | 2.0681 | 37.75% | 0.30096 | 0.40533 | 0.83808 | 0.11205 | 0.41172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W4 STOPE | Tonnes | Budget (t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (t) | 0 | 0%
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (g/t) | 0 | 0%
|  |  | Gold | Budget (kg) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W8 STOPE | Tonnes | Budget (t) | 630 |  | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 0 | 0 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
|  |  |  | Actual (t) | 64.5 | -89.76% |  |  |  | 9 | 55.5
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 2.7804 |  | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 0 | 0 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804
|  |  |  | Actual (g/t) | 0.80233 | -71.14% |  |  |  | 1.31 | 0.72
|  |  | Gold | Budget (kg) | 1.7516 |  | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0 | 0 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194 | 0.29194
|  |  |  | Actual (kg) | 0.05175 | -97.05% | 0 | 0 | 0 | 0.01179 | 0.03996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W13 STOPE | Tonnes | Budget (t) | 210 |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 0 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
|  |  |  | Actual (t) | 0 | -100%
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.986 |  | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 0 | 0 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986
|  |  |  | Actual (g/t) | 0 | -100%
|  |  | Gold | Budget (kg) | 0.41706 |  | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0 | 0 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509 | 0.069509
|  |  |  | Actual (kg) | 0 | -100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W15_STOPE | Tonnes | Budget (t) | 420 |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 35
|  |  |  | Actual (t) | 174 | -58.57% | 37.5 | 37.5 | 46.5 | 37.5 | 15
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 1.7477 |  | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 0 | 0 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477
|  |  |  | Actual (g/t) | 1.2989 | -25.68% | 2.61 | 1.59 | 0.62 | 0.79 | 0.67
|  |  | Gold | Budget (kg) | 0.73402 |  | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0 | 0 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.12234 | 0.061168
|  |  |  | Actual (kg) | 0.22601 | -69.21% | 0.097875 | 0.059625 | 0.02883 | 0.029625 | 0.01005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 6L_W18_STOPE | Tonnes | Budget (t) | 420 |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
|  |  |  | Actual (t) | 186 | -55.71% | 30 | 49.5 | 46.5 | 30 | 30
Reason if Actual is RED
|  |  | Grade | Budget (g/t) | 2.7804 |  | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 0 | 0 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804
|  |  |  | Actual (g/t) | 3.625 | 30.38% | 1.84 | 2.86 | 2.72 | 5.35 | 6.35
|  |  | Gold | Budget (kg) | 1.1678 |  | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0 | 0 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463 | 0.19463
|  |  |  | Actual (kg) | 0.67425 | -42.26% | 0.0552 | 0.14157 | 0.12648 | 0.1605 | 0.1905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8

## Hoisting
BRECKRIDGE INVESTMENTS | [5 empty] | KEY |  |  | GRADE LEGEND |  |  |  |  | Reason if Actual is RED |  |  |  |  | SG | 1.68
Pickstone Underground Mine | [5 empty] | Above Budget |  |  | < 0.60 Waste |  |  |  |  | No Sample - NS
Hoisting | [5 empty] | Below Budget |  |  | 0.60 - 1.60 Low Grade |  |  |  |  | Awaiting Assay Results - AAR
1.60 - 2.00 Medium Grade
Month: | 2025-08-01 | [7 empty] | > 2.00 High Grade |  |  |  |  | Reduced Draw - RD
Day: | 6
MTD | Budget | Actual | Variance |  | Shifts | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Hoisted (t) | 4990 | 5350 | 7.214% |  | Daily Budget (t) | 740 | 850 | 850 | 850 | 850 | 850
Grade (g/t) | 2.2344 | 1.7739 | -20.61% |  | Daily Actual (t) | 782 | 952 | 907 | 812 | 931 | 966
Gold (kg) | 11.1496 | 9.4905 | -14.88% |  | Daily Budget (g/t) | 2.2027 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2399
[5 empty] | Daily Actual (g/t) | 1.99 | 2.13 | 1.67 | 1.82 | 3.13 | 0
[5 empty] | Daily Budget (kg) | 1.63 | 1.9039 | 1.9039 | 1.9039 | 1.9039 | 1.9039
[5 empty] | Daily Actual (kg) | 1.5562 | 2.0278 | 1.5147 | 1.4778 | 2.914 | 0
| Source |  |  | MTD | MTD Var | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | COMMENTS
| Trucking (HOWO) | # of Loads | Southwell | 186 |  | 29 | 34 | 32 | 28 | 31 | 32
|  |  | Concession | 0 | [14 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 186 |  | 29 | 34 | 32 | 28 | 31 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Volume (LCM) | 2715.6 |  | 423.4 | 496.4 | 467.2 | 408.8 | 452.6 | 467.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Delivered Tonnes | Budget (t) | 4990 |  | 740 | 850 | 850 | 850 | 850 | 850 | 850 | 740 | 850 | 850 | 0 | 0 | 850 | 850 | 705 | 815 | 815 | 815 | 705 | 815 | 815 | 955 | 955 | 955 | 955 | 955 | 955 | 955 | 845 | 955 | 955
|  |  | Actual (t) | 5350 | 7.214% | 782 | 952 | 907 | 812 | 931 | 966
Reason if Actual is RED
|  | Delivered Grade | Budget (g/t) | 2.2344 |  | 2.2027 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2027 | 2.2399 | 2.2399 | 0 | 0 | 2.2399 | 2.2399 | 2.2135 | 2.2508 | 2.2508 | 2.2508 | 2.2135 | 2.2508 | 2.2508 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.1758 | 2.212 | 2.212
|  |  | Actual (g/t) | 1.7739 | -20.61% | 1.99 | 2.13 | 1.67 | 1.82 | 3.13
Reason if Actual is RED
|  | Delivered Gold | Budget (kg) | 11.1496 |  | 1.63 | 1.9039 | 1.9039 | 1.9039 | 1.9039 | 1.9039 | 1.9039 | 1.63 | 1.9039 | 1.9039 | 0 | 0 | 1.9039 | 1.9039 | 1.5605 | 1.8344 | 1.8344 | 1.8344 | 1.5605 | 1.8344 | 1.8344 | 2.1124 | 2.1124 | 2.1124 | 2.1124 | 2.1124 | 2.1124 | 2.1124 | 1.8385 | 2.1124 | 2.1124
|  |  | Actual (kg) | 9.4905 | -14.88% | 1.5562 | 2.0278 | 1.5147 | 1.4778 | 2.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concession Adit | Tonnage Delivered | Budget (t) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual (t) | 0 | 0%
Reason if Actual is RED
| Lobe Shaft | Skips Hoisted | Budget Skips | 825.7143 |  | 111.4286 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 111.4286 | 142.8571 | 142.8571 | 0 | 0 | 142.8571 | 142.8571 | 111.4286 | 142.8571 | 142.8571 | 142.8571 | 111.4286 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 111 | 142.8571 | 111.4286 | 142.8571 | 142.8571
|  |  | Actual Skips | 817 | -1.055% | 96 | 166 | 150 | 104 | 153 | 148
|  | Tonnage Hoisted | Budget (t) | 2890 |  | 390 | 500 | 500 | 500 | 500 | 500 | 500 | 390 | 500 | 500 | 0 | 0 | 500 | 500 | 390 | 500 | 500 | 500 | 390 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 390 | 500 | 500
|  |  | Actual (t) | 2859.5 | -1.055% | 336 | 581 | 525 | 364 | 535.5 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reason if Actual is RED
| Southwell Shaft | Skips Hoisted | Budget Skips | 1108.8889 |  | 164.4444 | 188.8889 | 188.8889 | 188.8889 | 188.8889 | 188.8889 | 188.8889 | 164.4444 | 188.8889 | 188.8889 | 0 | 186 | 188.8889 | 188.8889 | 156.6667 | 181.1111 | 181.1111 | 181.1111 | 156.6667 | 181.1111 | 181.1111 | 212.2222 | 212.2222 | 212.2222 | 212.2222 | 212.2222 | 212.2222 | 212.2222 | 187.7778 | 212.2222 | 212.2222
|  |  | Actual Skips | 1013 | -8.647% | 174 | 217 | 206 |  | 199 | 217
|  | Tonnage Hoisted | Budget (t) | 4990 |  | 740 | 850 | 850 | 850 | 850 | 850 | 850 | 740 | 850 | 850 | 0 | 835 | 850 | 850 | 705 | 815 | 815 | 815 | 705 | 815 | 815 | 955 | 955 | 955 | 955 | 955 | 955 | 955 | 845 | 955 | 955
|  |  | Actual (t) | 4558.5 | -8.647% | 783 | 976.5 | 927 | 0 | 895.5 | 976.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reason if Actual is RED
|  | Effective Skip Factor |  | 5.2813 | 17.36% | 4.4943 | 4.3871 | 4.4029 | 0 | 4.6784 | 4.4516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tonnage Reconciliation |  | Delivered vs Hoisted |  | 17.36% | -0.1277% | -2.509% | -2.157% | 0% | 3.964% | -1.075%
[6 empty] | 0 | 0
Note on K40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lobe shaft top radial door cylinder failure 2326-0305 (3.5hrs)

## Projects
BRECKRIDGE INVESTMENTS
Pickstone Underground Mine |  |  |  | METERS BELOW 10L | @Start of Month
PROJECTS DAILY CONTROL SHEET |  |  |  | Water Level (m) | 36.3
Year | 2025 |  |  | Subvert Lashing (m) | 45.2
Month: | July
Day: | 6 |  |  | Hoist Chamber % Completion | @Start of Month
PUG 3 COMMISSIONING DATE |  |  |  | Subvert | 100%
Plan | Forecast | Variance (days) |  | Venning | 100%
2025-11-09 | 2025-11-17 | -8 |  | Burnett | 100% |  | KEY
Above Budget
DEWATERING TO 10.5L | [6 empty] | Below Budget |  |  | Post a COMMENT with REASON if Actual is RED
Plan | Forecast | Variance (days) | Target (m) | Required Rate (m/day)
2025-04-05 | 2025-07-24 | -110 | 45 | -0.063043 | Shifts | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
LOCATION | ACTIVITY |  |  | MTD | MTD Var | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | Comments
SOUTHWELL | Slype and Support from 10L to 10.5L | Budget % Progress |  | 30% |  | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5%
|  | Actual % Progress |  | 30% | 0% | 5% | 5% | 5% | 5% | 5% | 5%
| Installation of 10.5L Loading station. | Budget % Progress |  | 0% | [16 empty] | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2%
|  | Actual % Progress |  | 0%
DEWATERING | Meters below 10L | Budget (m) |  | 70.4 |  | 62.9 | 64.4 | 65.9 | 67.4 | 68.9 | 70.4 | 71.9 | 73.4 | 74.9 | 74.9 | 74.9 | 76.4 | 77.9 | 79.4 | 80.9 | 82.4 | 83.9 | 85.4 | 86.9 | 88.4 | 89.9 | 91.4 | 92.9 | 94.4 | 95.9 | 97.4 | 98.9 | 100.4 | 101.9 | 103.4 | 104.9
|  | Actual (m) |  | 58 | -17.61% | 55.5 | 55.9 | 56.4 | 56.9 | 57.3 | 58
| Dewatering Advance | Budget (m) |  | 9 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
|  | Actual (m) |  | 2.9 | -67.78% | 0.4 | 0.4 | 0.5 | 0.5 | 0.4 | 0.7
| Volumes | Venning Pump to 6L (m3) |  | 13200 |  | 2330 | 2150 | 2220 | 2330 | 1970 | 2200
|  | 1st 147kW to Surface (m3) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 185kW to Surface (m3) |  | 15320 |  | 2540 | 2510 | 2570 | 2800 | 2430 | 2470
|  | 2L Cascade to Surface (m3) |  | 3530 |  | 580 | 630 | 530 | 650 | 600 | 540
|  | Total Discharge To Surface (m3) |  | 18850 |  | 3120 | 3140 | 3100 | 3450 | 3030 | 3010
|  | Drilling Water into the Mine (m3) |  | 7803 |  | 1183 | 1569 | 1193 | 1302 | 1200 | 1356
|  | Net Volume Pumped (m3) |  | 11047 |  | 1937 | 1571 | 1907 | 2148 | 1830 | 1654
| Running Hours | Venning Pump Hours |  | 142.5 |  | 24 | 23 | 24 | 23.5 | 24 | 24
|  | 1st 147kw Pump Hours |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2nd 147kw Pump Hours |  | 142 |  | 24 | 24 | 24 | 24 | 24 | 22
|  | 2L Cascade Pump Hours |  | 144 |  | 24 | 24 | 24 | 24 | 24 | 24
VENNING | Hoist Installation & Commissioning | Budget % Complete |  | 9% |  | 1.8% | 1.8% | 0% | 1.8% | 1.8% | 1.8% | 1.8% | 1.8% | 1.8% |  | 1.8% | 1.8% | 1.8% | 1.8% | 1.8% | 1.8%
|  | Actual % Progress |  | 9% | 0% | 1.8% | 1.8% | 0% | 1.8% | 1.8% | 1.8%
VENNING EXTENSION | Installation of ladders | Budget % Complete |  | 5 | [5 empty] | 5 |  |  | 5
|  | Actual % Progress |  | 5 | 0 |  |  |  |  | 5
10L Haulage | Installation of rails | Budget (m) |  | 60 |  | 12 | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12
|  | Actual (m) |  | 66 | 10% | 12 | 12 | 0 | 12 | 12 | 18
| Installation of pipes | Budget (m) |  | 0
|  | Actual (m) |  | 0 | 0%
Formulas:
Forecast = DATE(C5,MONTH(1&C6),C7)+ ([Target (m)]-G4)/AVERAGEIF(H15:AL15,"<="&C7,H25:AL25)
Note on H19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Blasted constriction above 10L, made safe and supported
Note on I19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Installed support and lashed material on 10L deck 100% complete.
Note on J19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Completed support above 10L and removed the deck
Note on K19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shaft plumbing and installation of the deck at 10.5L 100% complete.
Note on L19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shaft plumbing was done from 10L to 10.5L 100% complete Drilled and blasted constriction at 10L collar 50% complete
Note on M19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilled & blasted constriction at the shaft collar and slyped 1m below 10L
Note on H38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Floor screeding 40% complete
Note on I38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Transported all double door panels, driver's desk and cables to site.
Note on J38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Electrical installations 60% & winder primary alignment 50% complete.
Note on K38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Primary alignment and installation of depth indicator 100% complete
Note on L38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hoist electrical installations and lighting 100% complete
Note on M38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fixed the deadman switch and completed earthing.
Note on H40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed the second 45kw pump and installed support
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lowered the second 45kw pump and switched to 525V supply. Pump running.
Note on K40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Installed a platform for ladders.
Note on L40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Installed the third ladder
Note on J42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No activity, off day.

## PLANT
BRECKRIDGE INVESTMENTS
Pickstone Peerless Mine
Processing Plant |  |  |  |  | Shifts | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
[5 empty] | Budget Tonnes (t) | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 586.9356 | 1173.8712
Month: | 2025-08-01 |  |  |  | Daily Crushed (t) | 1078.5736 | 1066.0176 | 648.2984 | 753.7309 | 738.6 | 0
Day: | 6 |  |  |  | Daily Milled (t) | 1244.3207 | 1143.296 | 665.4402 | 1124.527 | 1067.219 | 0
[5 empty] | Budget Grade (g/t) | 2.3 | 2.3 | 1.832 | 2.2315 | 2.2339 | 2.2355
MTD | Tonnes (t) | Grade (g/t) | Gold (kg) |  | Daily Crushed (g/t) | 1.4864 | 1.8517 | 2.7927 | 1.7003 | 2.6778 | 0
Budget | 6456.2916 | 2.1847 | 14.1052 |  | Daily Milled (g/t) | 1.3227 | 1.9326 | 2.1524 | 1.7907 | 2.0169 | 0
Crushed | 4285.2205 | 2.0179 | 8.647 |  | Daily CIL (g/t) | 1.8464 | 2.0515 | 2.722 | 2.296 | 2.1612 | 0
Variance | -33.63% | -7.637% | -38.7% |  | Budget Tails (g/t) | 0.276 | 0.276 | 0.2554 | 0.26346 | 0.26374 | 0.26392
Mill Feed | 5244.8029 | 1.8025 | 9.4539 |  | Daily Tails (g/t) | 0.26984 | 0.29961 | 0.39 | 0.34393 | 0.30121 | 0
Variance | -18.76% | -17.49% | -32.98% |  | Budget Gold (kg) | 2.6999 | 2.6999 | 2.1505 | 2.6195 | 1.3112 | 2.6242
CIL Feed |  | 2.1626 | 11.3426 |  | Daily Crushed (kg) | 1.6032 | 1.9739 | 1.8105 | 1.2816 | 1.9778 | 0
Variance |  | -1.011% | -19.59% |  | Daily Milled (kg) | 1.6459 | 2.2095 | 1.4323 | 2.0137 | 2.1525 | 0
Budget Tails |  | 0.26666 | 1.7217 |  | Daily CIL (kg) | 2.2975 | 2.3455 | 1.8113 | 2.5819 | 2.3064 | 0
Actual Tails |  | 0.31384 | 1.6461 |  | Budget Tails (kg) | 0.32399 | 0.32399 | 0.2998 | 0.30926 | 0.1548 | 0.30981
Variance |  | 17.69% | -4.391% |  | Daily Tails (kg) | 0.33577 | 0.34255 | 0.25952 | 0.38676 | 0.32145 | 0
|  |  |  | MTD | MTD Var | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | COMMENTS
| Crushing | Tonnage | Budget (t) | 6456.2916 |  | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 586.9356 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1072.8027 | 1072.8027 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 586.9356 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1.75 - Ore depletion
|  |  | Crushed (t) | 4285.2205 | -33.63% | 1078.5736 | 1066.0176 | 648.2984 | 753.7309 | 738.6
Reason if Actual is RED
|  | Grade | Budget (g/t) | 2.1847 |  | 2.3 | 2.3 | 1.832 | 2.2315 | 2.2339 | 2.2355 | 2.2368 | 2.3 | 2.3 | 2.3 | 2.232 | 2.232 | 2.2344 | 2.2362 | 2.2285 | 2.2391 | 2.2461 | 2.0346 | 2.3 | 2.3 | 2.2395 | 2.2271 | 2.2195 | 2.2152 | 2.2131 | 2.2122 | 2.2121 | 2.212 | 2.0444 | 1.9375 | 1.9375
|  |  | Crushed (g/t) | 2.0179 | -7.637% | 1.4864 | 1.8517 | 2.7927 | 1.7003 | 2.6778
Reason if Actual is RED
|  | Gold | Budget (kg) | 14.1052 |  | 2.6999 | 2.6999 | 2.1505 | 2.6195 | 1.3112 | 2.6242 | 2.6257 | 2.6999 | 2.6999 | 2.6999 | 2.6201 | 2.3945 | 2.3971 | 2.6251 | 2.616 | 2.6284 | 2.6366 | 2.3884 | 2.6999 | 2.6999 | 2.6289 | 2.6143 | 2.6054 | 2.6004 | 2.5979 | 1.2984 | 2.5967 | 2.5966 | 2.3998 | 2.2744 | 2.2744
|  |  | Crushed (kg) | 8.647 | -38.7% | 1.6032 | 1.9739 | 1.8105 | 1.2816 | 1.9778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Milling | Tonnage | Budget (t) | 6456.2916 |  | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 586.9356 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1072.8027 | 1072.8027 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 586.9356 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 3.03 - Ore depletion
|  |  | Milled (t) | 5244.8029 | -18.76% | 1244.3207 | 1143.296 | 665.4402 | 1124.527 | 1067.219 | [26 empty] | 1.93 - Tunnel vibro-feeder blockage
|  |  | Reason if Actual is RED | [33 empty] | 1.32 - Surge bin clearing
|  | Grade | Budget (g/t) | 2.1847 |  | 2.3 | 2.3 | 1.832 | 2.2315 | 2.2339 | 2.2355 | 2.2368 | 2.3 | 2.3 | 2.3 | 2.232 | 2.232 | 2.2344 | 2.2362 | 2.2285 | 2.2391 | 2.2461 | 2.0346 | 2.3 | 2.3 | 2.2395 | 2.2271 | 2.2195 | 2.2152 | 2.2131 | 2.2122 | 2.2121 | 2.212 | 2.0444 | 1.9375 | 1.9375
|  |  | Milled (g/t) | 1.8025 | -17.49% | 1.3227 | 1.9326 | 2.1524 | 1.7907 | 2.0169
Reason if Actual is RED
|  | Gold | Budget (kg) | 14.1052 |  | 2.6999 | 2.6999 | 2.1505 | 2.6195 | 1.3112 | 2.6242 | 2.6257 | 2.6999 | 2.6999 | 2.6999 | 2.6201 | 2.3945 | 2.3971 | 2.6251 | 2.616 | 2.6284 | 2.6366 | 2.3884 | 2.6999 | 2.6999 | 2.6289 | 2.6143 | 2.6054 | 2.6004 | 2.5979 | 1.2984 | 2.5967 | 2.5966 | 2.3998 | 2.2744 | 2.2744
|  |  | Milled (kg) | 9.4539 | -32.98% | 1.6459 | 2.2095 | 1.4323 | 2.0137 | 2.1525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CIL | Grade | Budget (g/t) | 2.1847 |  | 2.3 | 2.3 | 1.832 | 2.2315 | 2.2339 | 2.2355 | 2.2368 | 2.3 | 2.3 | 2.3 | 2.232 | 2.232 | 2.2344 | 2.2362 | 2.2285 | 2.2391 | 2.2461 | 2.0346 | 2.3 | 2.3 | 2.2395 | 2.2271 | 2.2195 | 2.2152 | 2.2131 | 2.2122 | 2.2121 | 2.212 | 2.0444 | 1.9375 | 1.9375
|  |  | CIL (g/t) | 2.1626 | -1.011% | 1.8464 | 2.0515 | 2.722 | 2.296 | 2.1612
|  | Gold | Budget (kg) | 14.1052 |  | 2.6999 | 2.6999 | 2.1505 | 2.6195 | 1.3112 | 2.6242 | 2.6257 | 2.6999 | 2.6999 | 2.6999 | 2.6201 | 2.3945 | 2.3971 | 2.6251 | 2.616 | 2.6284 | 2.6366 | 2.3884 | 2.6999 | 2.6999 | 2.6289 | 2.6143 | 2.6054 | 2.6004 | 2.5979 | 1.2984 | 2.5967 | 2.5966 | 2.3998 | 2.2744 | 2.2744
|  |  | CIL (kg) | 11.3426 | -19.59% | 2.2975 | 2.3455 | 1.8113 | 2.5819 | 2.3064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tails | Grade | Budget (g/t) | 0.26666 |  | 0.276 | 0.276 | 0.2554 | 0.26346 | 0.26374 | 0.26392 | 0.26407 | 0.276 | 0.276 | 0.276 | 0.26351 | 0.26351 | 0.2638 | 0.26401 | 0.2631 | 0.26434 | 0.26517 | 0.25731 | 0.276 | 0.276 | 0.2644 | 0.26293 | 0.26203 | 0.26153 | 0.26128 | 0.26118 | 0.26116 | 0.26115 | 0.25289 | 0.25111 | 0.25111
|  |  | Tails (g/t) | 0.31384 | 17.69% | 0.26984 | 0.29961 | 0.39 | 0.34393 | 0.30121
|  | Gold | Budget (kg) | 1.7217 |  | 0.32399 | 0.32399 | 0.2998 | 0.30926 | 0.1548 | 0.30981 | 0.30999 | 0.32399 | 0.32399 | 0.32399 | 0.30933 | 0.2827 | 0.283 | 0.30992 | 0.30885 | 0.31031 | 0.31128 | 0.30205 | 0.32399 | 0.32399 | 0.31037 | 0.30865 | 0.30759 | 0.307 | 0.30671 | 0.15329 | 0.30657 | 0.30656 | 0.29687 | 0.29477 | 0.29477
|  |  | Tails (kg) | 1.6461 | -4.391% | 0.33577 | 0.34255 | 0.25952 | 0.38676 | 0.32145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Tonnage Recon
BRECKRIDGE INVESTMENTS
Pickstone Underground Mine
Wekly Tonnage Reconciliation
Month: | 2025-08-01
Week: | 1
|  |  |  | 1 | 2 | 3 | 4 | 5
PERIOD ENDING |  | UoM | 2025-07-31 | [5 empty] | MTD
INVENTORY AT CLOSE OF PERIOD
Fine Ore Stockpiles
Mill Spillages |  | t | [6 empty] | 0
Mill Scats |  | t | [6 empty] | 0
Fine Ore (Live) |  | t | [6 empty] | 0
Crusher Spillage |  | t | [6 empty] | 0
Fine Ore Purchases |  | t | 0 | 0 | 0 | 0 |  |  | 0
Total Fine Ore Inventory |  | t | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uncrushed Ore Stockpiles
ROM Pad (Ex PUG) |  | t | [6 empty] | 0
ROM Pad (Ex Pit&SP) |  | t | [6 empty] | 0
ROM Pad (Ex Ore Purchases) |  | t | 0 | 0 | 0 |  |  |  | 0
Total Uncrushed Ore Inventory |  | t | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHANGE IN INVENTORY
Fine Ore Stockpiles
Mill Spillages |  | t |  | 0 | 0 | 0 | 0 | 0 | 0
Mill Scats |  | t |  | 0 | 0 | 0 | 0 | 0 | 0
Fine Ore (Live) |  | t |  | 0 | 0 | 0 | 0 | 0 | 0
Crusher Spillage |  | t |  | 0 | 0 | 0 | 0 | 0 | 0
Fine Ore (Ex Sands Purchases) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Total Change in Fine Ore Inventory |  | t |  | 0 | 0 | 0 | 0 | 0 | 0
Uncrushed Stockpiles
ROM Pad (Ex PUG) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ROM Pad (Ex Pit&SP) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ROM Pad (Ex Ore Purchases) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Total Change in Uncrushed Ore Stockpiles |  | t |  | 0 | 0 | 0 | 0 | 0 | 0
REPORTED ORE VALUES
Reported Fine Ore Crushed (Weightometer) |  | t | [6 empty] | 0
Milled Ore (Weightometer) |  | t | [6 empty] | 0
Ore Deliveries (Mining) |  | t |  | 5350 | 0 | 0 |  |  | 5350
RECONCILED ORE VALUES
Calculated Fine Ore Available for Milling |  | t |  | 0 | 0 | 0 | 0 | 0 | 0
Calculated Fine Ore Crushed |  | t |  | 5350 | 0 | 0 | 0 | 0 | 5350
Calculated Fine Ore Variance |  | t |  | 5350 | 0 | 0 | 0 | 0 | 5350
Crusher Weightometer Variance |  | % |  | -100% |  |  |  |  | -100%

## Hoisting Charts (hidden)
Hoisting
| Lobe | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01
13950 | Budget (t) | 390 | 500 | 500 | 500 | 500 | 500 | 500 | 390 | 500 | 500 | 0 | 0 | 500 | 500 | 390 | 500 | 500 | 500 | 390 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 390 | 500 | 500
2859.5 | Actual (t) | 336 | 581 | 525 | 364 | 535.5 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11090.5 | Cum Budget (t) | 390 | 890 | 1390 | 1890 | 2390 | 2890 | 3390 | 3780 | 4280 | 4780 | 4780 | 4780 | 5280 | 5780 | 6170 | 6670 | 7170 | 7670 | 8060 | 8560 | 9060 | 9560 | 10060 | 10560 | 11060 | 11560 | 12060 | 12560 | 12950 | 13450 | 13950
| Cum Actual (t) | 336 | 917 | 1442 | 1806 | 2341.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5 | 2859.5
1584.3571
2034.3571

## DEV.
DATE | LEVEL | W23 | HLGE | RCH | DISTANCE FROM PEG(m) | DIRECTION | PEG ID | FROM (m) | TO (m) | SAMPLE WIDTH (m) | SAMPLEID | AU | FACE Average Grade (g/t) | SAMPLER | GEOTECH | RCH NUMBER | LITHOLOGY
2025-08-01 | 6L | W2 | SBL1 | FCH | 3.4 | East | P01123 | 0 | 0.6 | 0.6 | MM964265 | 0.34 | 1.105
2025-08-01 | [7 empty] | 0.6 | 0.8 | 0.2 | MM964266 | 1.87
2025-08-01 | 6L | W2 | SBL1 | FCH | 4.8 | West | P01120 | 0 | 0.6 | 0.6 | MM964267 | 0.24 | 0.39667
2025-08-01 | [7 empty] | 0.6 | 1.2 | 0.6 | MM964268 | 0.32
2025-08-01 | [7 empty] | 1.2 | 1.4 | 0.2 | MM964269 | 0.63
2025-08-01 | 5L | W12 | CON-DRV | SLG | 0 | West | W12_RSE | 0 | 0.6 | 0.6 | MM964275 | 2.11 | 2.035
2025-08-01 | 5L | W12 | CON-DRV | SLG | 0 | West | W12_RSE | 0.6 | 1.2 | 0.6 | MM964276 | 1.96
2025-08-01 | 5L | W12 | CON-DRV | SLG | 0 | West | W12_RSE | 0 | 0.6 | 0.6 | MM964277 | 0.07 | 0.07
2025-08-01 | 5L | W12 | CON-DRV | SLG | 0 | West | W12_RSE | 0.6 | 1.2 | 0.6 | MM964278 | 0.07
2025-08-01 | 5L | W12 | CON-DRV | SLG | 2 | West | W12_RSE | 0 | 0.6 | 0.6 | MM964279 | 0.496 | 0.313
2025-08-01 | 5L | W12 | CON-DRV | SLG | 2 | West | W12_RSE | 0.6 | 1.2 | 0.6 | MM964280 | 0.13
2025-08-01 | 5L | W12 | CON-DRV | SLG | 0 | West | P0927 | 0 | 0.6 | 0.6 | MM964281 | 0.05 | 0.06
2025-08-01 | 5L | W12 | CON-DRV | SLG | 0 | West | P0927 | 0.6 | 1.2 | 0.6 | MM964282 | 0.07
2025-08-01 | 5L | W12 | CON-DRV | SLG | 2 | West | P0927 | 0 | 0.6 | 0.6 | MM964283 | 7.69 | 4.225
2025-08-01 | 5L | W12 | CON-DRV | SLG | 2 | West | P0927 | 0.6 | 1.2 | 0.6 | MM964284 | 0.76
2025-08-01 | 5L | W12 | CON-DRV | SLG | 4 | West | P0927 | 0 | 0.6 | 0.6 | MM964285 | 0.22 | 0.175
2025-08-01 | 5L | W12 | CON-DRV | SLG | 4 | West | P0927 | 0.6 | 1.2 | 0.6 | MM964286 | 0.13
2025-08-01 | 5L | W12 | CON-DRV | SLG | 6 | West | P0927 | 0 | 0.6 | 0.6 | MM964287 | 0.73 | 0.735
2025-08-01 | 5L | W12 | CON-DRV | SLG | 6 | West | P0927 | 0.6 | 1.2 | 0.6 | MM964288 | 0.74
2025-08-01 | 7L | W14 | CON-DRV | FCH | 21.6 | West | P1087 | 0 | 0.6 | 0.6 | MM966279 | 1.53 | 1.32
2025-08-01 | [7 empty] | 0.6 | 1.2 | 0.6 | MM966280 | 1.11
2025-08-01 | 7L | W14 | SBL1 | FCH | 1.3 | West | W14A_RSE | 0 | 0.6 | 0.6 | MM966281 | 0.24 | 0.33
2025-08-01 | [7 empty] | 0.6 | 1.2 | 0.6 | MM966282 | 0.42
2025-08-01 | 7L | W14 | SBL1 | FCH | 0 | East | W14A_RSE | 0 | 0.6 | 0.6 | MM966283 | 0.34 | 0.345
2025-08-01 | [7 empty] | 0.6 | 1.2 | 0.6 | MM966284 | 0.35
2025-08-01 | 8L | W16 | SBL2 | FCH | 19.8 | West | P1088 | 0 | 0.6 | 0.6 | MM966285 | 0.01 | 0.086667
2025-08-01 | [7 empty] | 0.6 | 1 | 0.4 | MM966286 | 0.19
2025-08-01 | [7 empty] | 1 | 1.4 | 0.4 | MM966287 | 0.06
2025-08-01 | 8L | W15 | RSE | FCH | 20.1 | Up | W15A_RSE | 0 | 0.6 | 0.6 | MM966288 | 0.48 | 0.4
2025-08-01 | [7 empty] | 0.6 | 1.2 | 0.6 | MM966289 | 0.32
2025-08-01 | 8L | W16 | RSE | FCH | 16.2 | Up | W16A_RSE | 0 | 0.6 | 0.6 | MM966290 | 0.45 | 0.42
2025-08-01 | [7 empty] | 0.6 | 1.2 | 0.6 | MM966291 | 0.39
2025-08-02 | 7L | W14 | CON-DRV | RCH | 2 | West | P1086 | 0 | 0.6 | 0.6 | MM966267 | 0.3 | 0.21 |  |  | 1
2025-08-02 | 7L | W14 | CON-DRV | RCH | 2 | West | P1086 | 0.6 | 1.2 | 0.6 | MM966268 | 0.12
2025-08-02 | 7L | W14 | CON-DRV | RCH | 4 | West | P1086 | 0 | 0.6 | 0.6 | MM966269 | 0.89 | 0.605 |  |  | 2
2025-08-02 | [7 empty] | BLANK |  |  | MM966270 | 3.2
2025-08-02 | 7L | W14 | CON-DRV | RCH | 4 | West | P1086 | 0.6 | 1.1 | 0.5 | MM966271 | 0.32
2025-08-02 | 7L | W14 | CON-DRV | RCH | 6 | West | P1086 | 0 | 0.6 | 0.6 | MM966272 | 0.2 | 0.205 |  |  | 3
2025-08-02 | 7L | W14 | CON-DRV | RCH | 6 | West | P1086 | 0.6 | 1 | 0.4 | MM966273 | 0.21
2025-08-02 | 7L | W14 | CON-DRV | RCH | 8 | West | P1086 | 0 | 0.6 | 0.6 | MM966274 | 4.13 | 2.09 |  |  | 4
2025-08-02 | [7 empty] | STD 0660 3.160g/t |  |  | MM966275 | 3.07
2025-08-02 | 7L | W14 | CON-DRV | RCH | 8 | West | P1086 | 0.6 | 1.2 | 0.6 | MM966276 | 0.05
2025-08-02 | 7L | W14 | CON-DRV | RCH | 10 | West | P1086 | 0 | 0.6 | 0.6 | MM966277 | 0.04 | 0.07 |  |  | 5
2025-08-02 | 7L | W14 | CON-DRV | RCH | 10 | West | P1086 | 0.6 | 1.2 | 0.6 | MM966278 | 0.1
2025-08-02 | 5L | W13 | RSE | FCH | 2 | x/cS | W13_OP | 0 | 0.6 | 0.6 | MM907011 | 4.078 | 2.2335
2025-08-02 | [7 empty] | 0.6 | 1.2 | 0.6 | MM907012 | 0.389
2025-08-02 | 5L | W13 | RSE | FCH | 1.8 | x/cN | W13_OP | 0 | 0.6 | 0.6 | MM907013 | 0.158 | 0.7215
2025-08-02 | [7 empty] | 0.6 | 1.2 | 0.6 | MM907014 | 1.285
2025-08-02 | 5L | W13 | HLGE | FCH | 2 | West | W13B_OP | 0 | 1 | 1 | MM907015 | 0.141 | 0.565
2025-08-02 | [7 empty] | 1 | 2 | 1 | MM907016 | 0.298
2025-08-02 | [7 empty] | 2 | 3 | 1 | MM907017 | 1.256
2025-08-02 | 6L | W14 | SBL3 | FCH | 5.4 | West | P1105 | 0 | 0.6 | 0.6 | MM907018 | 0.439 | 0.4775
2025-08-02 | [7 empty] | 0.6 | 1.2 | 0.6 | MM907019 | 0.516
2025-08-02 | 6L | W2 | SBL2 | FCH | 5.6 | West | P1120 | 0 | 0.6 | 0.6 | MM907020 | 0.121 | 0.898
2025-08-02 | [7 empty] | 0.6 | 1.2 | 0.6 | MM907021 | 1.675
2025-08-04 | 5L | W13 | RSE | SDC | 1 | x/cS | W13_RSE | 0 | 1 | 1 | MM907034 | 0.12 | 0.165
2025-08-04 | [7 empty] | 1 | 2 | 1 | MM907035 | 0.21
2025-08-04 | 5L | W13 | RSE | SDC | 1 | x/cN | W13_RSE | 0 | 1 | 1 | MM907036 | 1.5 | 1.41
2025-08-04 | [7 empty] | 1 | 2 | 1 | MM907037 | 1.32
2025-08-04 | 5L | W13 | HLGE | FCH | 7.5 | West | P1124 | 0 | 1 | 1 | MM907038 | 0.22 | 0.17333
2025-08-04 | [7 empty] | 1 | 2 | 1 | MM907039 | 0.24
2025-08-04 | [7 empty] | 2 | 3 | 1 | MM907040 | 0.06
2025-08-04 | 5L | W13 | RSE | FCH | 5.6 | Up | W13B_RSE | 0 | 0.6 | 0.6 | MM907041 | 0.1 | 0.28
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM907042 | 0.46
2025-08-04 | 6L | W14 | SBL3 | FCH | 1 | x/cS | W14_DRW | 0 | 1 | 1 | MM907043 | 0.18 | 0.18 | EAST
2025-08-04 | 6L | W14 | SBL3 | FCH | 1 | x/cS | W14_DRW | 0 | 1 | 1 | MM907044 | 0.74 | 0.74 | WEST
2025-08-04 | 3L | W23 | SBL3 | RCH | 7 | East | P0533 | 0 | 0.6 | 0.6 | MM905386 | 2.53 | 1.559 |  |  | 1
2025-08-04 | 3L | W23 | SBL3 | RCH | 7 | East | P0533 | 0.6 | 1.2 | 0.6 | MM905387 | 0.588
2025-08-04 | 3L | W23 | SBL3 | RCH | 5 | East | P0533 | 0 | 0.3 | 0.3 | MM905388 | 1.284 | 0.6715 |  |  | 2
2025-08-04 | 3L | W23 | SBL3 | RCH | 5 | East | P0533 | 0.3 | 1.2 | 0.9 | MM905389 | 0.059
2025-08-04 | [7 empty] | STD 0660 3.160g/t |  |  | MM905390 | 3.25
2025-08-04 | 3L | W23 | SBL3 | RCH | 3 | East | P0533 | 0 | 0.6 | 0.6 | MM905391 | 0.05 | 0.04 |  |  | 3
2025-08-04 | 3L | W23 | SBL3 | RCH | 3 | East | P0533 | 0.6 | 1.2 | 0.6 | MM905392 | 0.03
2025-08-04 | 3L | W23 | SBL3 | RCH | 1 | East | P0533 | 0 | 0.6 | 0.6 | MM905393 | 0.221 | 0.1925 |  |  | 4
2025-08-04 | 3L | W23 | SBL3 | RCH | 1 | East | P0533 | 0.6 | 1.2 | 0.6 | MM905394 | 0.164
2025-08-04 | [7 empty] | BLANK |  |  | MM905395 | 0
2025-08-04 | 3L | W23 | SBL3 | RCH | 1 | West | P0533 | 0 | 0.6 | 0.6 | MM905396 | 0.254 | 0.385 |  |  | 5
2025-08-04 | 3L | W23 | SBL3 | RCH | 1 | West | P0533 | 0.6 | 1.2 | 0.6 | MM905397 | 0.516
2025-08-04 | 3L | W23 | SBL3 | RCH | 3 | West | P0533 | 0 | 0.6 | 0.6 | MM905398 | 0.41 | 1.578 |  |  | 6
2025-08-04 | 3L | W23 | SBL3 | RCH | 3 | West | P0533 | 0.6 | 1.2 | 0.6 | MM905399 | 2.746
2025-08-04 | 3L | W23 | SBL3 | RCH | 5 | West | P0533 | 0 | 0.6 | 0.6 | MM905400 | 0.352 | 0.291 |  |  | 7
2025-08-04 | 3L | W23 | SBL3 | RCH | 5 | West | P0533 | 0.6 | 1.2 | 0.6 | MM905601 | 0.23
2025-08-04 | 3L | W23 | SBL3 | RCH | 7 | West | P0533 | 0 | 0.6 | 0.6 | MM905602 | 0.25 | 0.3 |  |  | 8
2025-08-04 | 3L | W23 | SBL3 | RCH | 7 | West | P0533 | 0.6 | 1.2 | 0.6 | MM905603 | 0.35
2025-08-04 | 3L | W23 | SBL3 | RCH | 9 | West | P0533 | 0 | 0.6 | 0.6 | MM905604 | 0.18 | 0.16 |  |  | 9
2025-08-04 | [7 empty] | STD 0660 3.160g/t |  |  | MM905605 | 3.27
2025-08-04 | 3L | W23 | SBL3 | RCH | 9 | West | P0533 | 0.6 | 1.2 | 0.6 | MM905606 | 0.14
2025-08-04 | [7 empty] | STD UGGS012493 |  |  | MM907515 | 0
2025-08-04 | 6L | W15 | SBL2 | SLG | 3.8 | x/cN | W15_OP | 0 | 0.9 | 0.9 | MM907516 | 0.46 | 1.12
2025-08-04 | [7 empty] | 0.9 | 1.8 | 0.9 | MM907517 | 1.78
2025-08-04 | 6L | W15 | SBL2 | SLG | 2.8 | x/cN | W15_OP | 0 | 0.9 | 0.9 | MM907518 | 0.39 | 0.37
2025-08-04 | [7 empty] | 0.9 | 1.8 | 0.9 | MM907519 | 0.35
2025-08-04 | 7L | W2 | SBL2 | FCH | 12.1 | West | P1111 | 0 | 0.6 | 0.6 | MM907520 | 1.34 | 1.2235
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM907521 | 1.107
2025-08-04 | 7L | W2 | SBL2 | RCH | 0 |  | P1111 | 0 | 0.6 | 0.6 | MM907522 | 0.658 | 0.364
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM907523 | 0.07
2025-08-04 | 7L | W2 | SBL2 | RCH | 2 | West | P1111 | 0 | 0.6 | 0.6 | MM907524 | 0.04 | 0.8035
2025-08-04 | [7 empty] | BLANK |  |  | MM907525 | 0.909
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM907526 | 1.567
2025-08-04 | 7L | W2 | SBL2 | RCH | 4 | West | P1111 | 0 | 0.6 | 0.6 | MM907527 | 3.893 | 3.583
2025-08-04 | [7 empty] | 0.6 | 1 | 0.4 | MM907528 | 3.632
2025-08-04 | [7 empty] | 1 | 1.2 | 0.2 | MM907529 | 3.224
2025-08-04 | [7 empty] | FDUP |  |  | MM907530 | 3.185
2025-08-04 | 7L | W14 | CON-DRV | FCH | 24.3 | West | P1087 | 0 | 0.6 | 0.6 | MM946317 | 0.98 | 0.79
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM946318 | 0.6
2025-08-04 | 7L | W14 | SBL1 | FCH | 3.2 | East | W14A_RSE | 0 | 0.6 | 0.6 | MM946319 | 0.05 | 0.25
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM946320 | 0.45
2025-08-04 | 8L | W16 | SBL2 | FCH | 23.9 | West | P1088 | 0 | 0.6 | 0.6 | MM946321 | 0.05 | 0.235
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM946322 | 0.42
2025-08-04 | 8L | W15 | RSE | FCH | 22.3 | Up | W15A_RSE | 0 | 0.3 | 0.3 | MM946323 | 0.21 | 0.29667
2025-08-04 | [7 empty] | 0.3 | 0.9 | 0.6 | MM946324 | 0.36
2025-08-04 | [7 empty] | STD 0660 3.160g/t |  |  | MM946325 | 3.22
2025-08-04 | [7 empty] | 0.9 | 1.3 | 0.4 | MM946326 | 0.32
2025-08-04 | 8L | W16 | RSE | FCH | 18.5 | Up | W16A_RSE | 0 | 0.6 | 0.6 | MM946327 | 0.24 | 0.14
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM946328 | 0.04
2025-08-04 | 8L | W16 | RSE | FCH | 17.6 | Up | W16B_RSE | 0 | 0.6 | 0.6 | MM946329 | 0.12 | 0.11
2025-08-04 | [7 empty] | BLANK |  |  | MM946330 | 0
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM946331 | 0.1
2025-08-04 | 8L | W16 | HLGE | FCH |  |  |  | 0 | 0.6 | 0.6 | MM946332 | 0.1 | 1.62
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM946333 | 3.9
2025-08-04 | [7 empty] | 1.2 | 1.8 | 0.6 | MM946334 | 0.86
2025-08-04 | [7 empty] | FDUP |  |  | MM946335 | 0.08
2025-08-04 | 8L | W16 | SBL2 | SLG | 19.5 | West | P1088 | 0 | 0.6 | 0.6 | MM946336 | 0.04 | 0.045
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM946337 | 0.05
2025-08-04 | 8L | W16 | SBL2 | SLG | 19.5 | West | P1088 | 0 | 0.6 | 0.6 | MM946338 | 0.03 | 0.025
2025-08-04 | [7 empty] | 0.6 | 1.2 | 0.6 | MM946339 | 0.02
2025-08-05 | 6L | W14 | SBL3 | FCH | 11.3 | x/cN | P1102 | 0 | 1 | 1 | MM907046 | 0.22 | [5 empty] | WEST
2025-08-05 | 6L | W14 | SBL3 | FCH | 11.3 | x/cN | P1102 | 0 | 1 | 1 | MM907047 | 0.13 | [5 empty] | EAST
2025-08-05 | 5L | W13 | HLGE | FCH | 5.3 | West | W13B_RSE | 0 | 1 | 1 | MM907048 | 0.21
2025-08-05 | [7 empty] | 1 | 2 | 1 | MM907049 | 0.13
2025-08-05 | [7 empty] | 2 | 3 | 1 | MM907050 | 0.03
2025-08-05 | 5L | W13 | BOX RSE | FCH | 5.2 | Up | W13B_RSE | 0 | 0.6 | 0.6 | MM907051 | 0.27
2025-08-05 | [7 empty] | 0.6 | 1.2 | 0.6 | MM907052 | 0.09
2025-08-05 | 5L | W13 | RSE | FCH | 3 | x/cS | W13_OP | 0 | 1 | 1 | MM907053 | 0.9
2025-08-05 | [7 empty] | 0 | 1 | 1 | MM907054 | 0.86
2025-08-05 | 3L | W23 | HLGE | RCH | 10 | East | P0409 | 0 | 0.6 | 0.6 | MM905638 | 0.18 |  |  |  | 9
2025-08-05 | 3L | W23 | HLGE | RCH | 10 | East | P0409 | 0.6 | 1.3 | 0.7 | MM905639 | 0.15
2025-08-05 | 3L | W23 | HLGE | RCH | 12 | East | P0409 | 0 | 0.6 | 0.6 | MM905640 | 0.55 |  |  |  | 10
2025-08-05 | 3L | W23 | HLGE | RCH | 12 | East | P0409 | 0.6 | 1.2 | 0.6 | MM905641 | 0.17
2025-08-05 | 3L | W23 | HLGE | RCH | 14 | East | P0409 | 0 | 0.6 | 0.6 | MM905642 | 0.19 |  |  |  | 11
2025-08-05 | 3L | W23 | HLGE | RCH | 14 | East | P0409 | 0.6 | 1.2 | 0.6 | MM905643 | 0.11
2025-08-05 | 3L | W23 | HLGE | RCH | 16 | East | P0409 | 0 | 0.6 | 0.6 | MM905644 | 0.13 |  |  |  | 12
2025-08-05 | [7 empty] | FDUP |  | #VALUE! | MM905645 | 0.12
2025-08-05 | 3L | W23 | HLGE | RCH | 16 | East | P0409 | 0.6 | 1.2 | 0.6 | MM905646 | 0.13
2025-08-05 | 7L | W14 | CON-DRV | RCH | 2 | West | P1087 | 0 | 0.6 | 0.6 | MM964340 | 0.083 | 0.1145 |  |  | 6
2025-08-05 | 7L | W14 | CON-DRV | RCH | 2 | West | P1087 | 0.6 | 0.9 | 0.3 | MM964341 | 0.146
2025-08-05 | 7L | W14 | CON-DRV | RCH | 4 | West | P1087 | 0 | 0.6 | 0.6 | MM964342 | 0.107 | 0.2445 |  |  | 7
2025-08-05 | 7L | W14 | CON-DRV | RCH | 4 | West | P1087 | 0.6 | 0.9 | 0.3 | MM964343 | 0.382
2025-08-05 | 7L | W14 | CON-DRV | RCH | 6 | West | P1087 | 0 | 0.6 | 0.6 | MM964344 | 1.866 | 1.0165 |  |  | 8
2025-08-05 | [7 empty] | BLANK |  | #VALUE! | MM964345 | 0
2025-08-05 | 7L | W14 | CON-DRV | RCH | 6 | West | P1087 | 0.6 | 1.1 | 0.5 | MM964346 | 0.167
2025-08-05 | 7L | W14 | CON-DRV | RCH | 8 | West | P1087 | 0 | 0.6 | 0.6 | MM964347 | 0.991 | 1.0595 |  |  | 9
2025-08-05 | 7L | W14 | CON-DRV | RCH | 8 | West | P1087 | 0.6 | 1.1 | 0.5 | MM964348 | 1.128
2025-08-05 | 7L | W14 | CON-DRV | RCH | 10 | West | P1087 | 0 | 0.6 | 0.6 | MM964349 | 1.293 | 0.6955 |  |  | 10
2025-08-05 | [7 empty] | STD 0660 3.160g/t |  | #VALUE! | MM964350 | 3.25
2025-08-05 | 7L | W14 | CON-DRV | RCH | 10 | West | P1087 | 0.6 | 0.9 | 0.3 | MM964351 | 0.098
2025-08-05 | 7L | W14 | CON-DRV | RCH | 12 | West | P1087 | 0 | 0.6 | 0.6 | MM964352 | 0.164 | 0.1565 |  |  | 11
2025-08-05 | 7L | W14 | CON-DRV | RCH | 12 | West | P1087 | 0.6 | 0.9 | 0.3 | MM964353 | 0.149
2025-08-05 | 7L | W14 | CON-DRV | RCH | 14 | West | P1087 | 0 | 0.6 | 0.6 | MM964354 | 1.403 | 0.797 |  |  | 12
2025-08-05 | [7 empty] | FDUP |  | #VALUE! | MM964355 | 1.41
2025-08-05 | 7L | W14 | CON-DRV | RCH | 14 | West | P1087 | 0.6 | 1 | 0.4 | MM964356 | 0.191
2025-08-05 | 7L | W14 | CON-DRV | RCH | 16 | West | P1087 | 0 | 0.6 | 0.6 | MM964357 | 0.4 | 0.2755 |  |  | 13
2025-08-05 | 7L | W14 | CON-DRV | RCH | 16 | West | P1087 | 0.6 | 0.9 | 0.3 | MM964358 | 0.151
2025-08-05 | 7L | W14 | CON-DRV | RCH | 18 | West | P1087 | 0 | 0.6 | 0.6 | MM964359 | 0.183 | 0.261 |  |  | 14
2025-08-05 | 7L | W14 | CON-DRV | RCH | 18 | West | P1087 | 0.6 | 0.9 | 0.3 | MM964360 | 0.339
2025-08-05 | 7L | W14 | CON-DRV | RCH | 20 | West | P1087 | 0 | 0.6 | 0.6 | MM964361 | 1.784 | 2.2515 |  |  | 15
2025-08-05 | 7L | W14 | CON-DRV | RCH | 20 | West | P1087 | 0.6 | 1 | 0.4 | MM964362 | 2.719
2025-08-06 | 2L | W29 | RSE | FCH | 5.8 | Up | W29_RSE | 0 | 0.6 | 0.6 | MM905683
2025-08-06 | [7 empty] | 0.6 | 1.2 | 0.6 | MM905684
2025-08-06 | 10L | W7 | RSE | FCH | 1.2 | West | P0850 | 0 | 0.6 | 0.6 | MM905701
2025-08-06 | [7 empty] | 0.6 | 1.2 | 0.6 | MM905702
2025-08-06 | 10L | W7 | RSE | FCH | 1.2 | Up | W7B_RSE | 0 | 0.35 | 0.35 | MM905703
2025-08-06 | [7 empty] | 0.35 | 0.85 | 0.5 | MM905704
2025-08-06 | [7 empty] | 0.85 | 1.45 | 0.6 | MM905705
2025-08-06 | 10L | W7 | RSE | FCH | 1.2 | Up | W7C_RSE | 0 | 0.6 | 0.6 | MM905706
2025-08-06 | [7 empty] | 0.6 | 1.2 | 0.6 | MM905707
2025-08-06 | 10L | E3 | CON-DRV | FCH | 2 | West | E3C_RSE | 0 | 0.6 | 0.6 | MM905708
2025-08-06 | [7 empty] | 0.6 | 0.9 | 0.3 | MM905709
2025-08-06 | 10L | E3 | CON-DRV | FCH | 2 | East | E3A_RSE | 0 | 0.6 | 0.6 | MM905710
2025-08-06 | [7 empty] | 0.6 | 0.9 | 0.3 | MM905711
2025-08-06 | [7 empty] | 0.9 | 1.4 | 0.5 | MM905712
2025-08-06 | 6L | W14 | SBL3 | FCH | 12.3 | x/cS | P1102 | 0 | 1 | 1 | MM907061
2025-08-06 | [7 empty] | 0 | 1 | 1 | MM907062
2025-08-06 | 5L | W13 | HLGE | FCH | 6.5 | West | W13B_RSE | 0 | 1 | 1 | MM907063
2025-08-06 | [7 empty] | 1 | 2 | 1 | MM907064
2025-08-06 | [7 empty] | 2 | 3 | 1 | MM907065
2025-08-06 | 5L | W13 | RSE | FCH | 4.4 | x/cS | W13C_RSE | 3 | 4 | 1 | MM907066
2025-08-06 | [7 empty] | 3 | 4 | 1 | MM907067
2025-08-06 | 5L | W11 | SBL1 | FCH | 8.6 | West | W11_OP | 0 | 0.6 | 0.6 | MM907068
2025-08-06 | [7 empty] | 0.6 | 1.2 | 0.6 | MM907069
2025-08-06 | 8L | W16 | SBL2 | SDC | 0 | x/cS | P1088 | 0 | 0.6 | 0.6 | MM964363 | 0.07 | [5 empty] | EAST
2025-08-06 | [7 empty] | 0.6 | 1.2 | 0.6 | MM964364 | 0.42
2025-08-06 | [7 empty] | BLANK |  |  | MM964365 | 0
2025-08-06 | [7 empty] | 1.2 | 1.4 | 0.2 | MM964366 | 0.42
2025-08-06 | [7 empty] | 1.4 | 1.6 | 0.2 | MM964367 | 0.11
2025-08-06 | [7 empty] | 1.6 | 1.8 | 0.2 | MM964368 | 0.36
2025-08-06 | [7 empty] | 1.8 | 2 | 0.2 | MM964369 | 0.1
2025-08-06 | [7 empty] | STD 0660 3.160g/t |  |  | MM964370 | 3.25
2025-08-06 | [7 empty] | 2 | 2.6 | 0.6 | MM964371 | 0.06
2025-08-06 | 8L | W16 | SBL2 | FCH | 2.6 | x/cS | P1088 | 0 | 0.6 | 0.6 | MM964372 | 0.05
2025-08-06 | [7 empty] | 0.6 | 1.2 | 0.6 | MM964373 | 0.04
2025-08-06 | [7 empty] | 1.2 | 1.6 | 0.4 | MM964374 | 0.04
2025-08-06 | [7 empty] | BLANK |  |  | MM964375 | 0
2025-08-06 | 8L | W16 | SBL2 | FCH | 0 | x/cS | P1088 | 0 | 1.2 | 1.2 | MM964376 | 0.04 | [5 empty] | WEST
2025-08-06 | [7 empty] | 1.2 | 1.6 | 0.4 | MM964377 | 0.43
2025-08-06 | [7 empty] | 1.6 | 2.4 | 0.8 | MM964378 | 0.06
2025-08-06 | [7 empty] | 2.4 | 2.9 | 0.5 | MM964379 | 0.46
2025-08-06 | [7 empty] | 2.9 | 3.1 | 0.2 | MM964380 | 0.09
2025-08-06 | [7 empty] | 3.1 | 3.5 | 0.4 | MM964381 | 0.07
2025-08-06 | 8L | W15 | RSE | FCH | 11.4 | Up | W15A_RSE | 0 | 0.6 | 0.6 | MM964382
2025-08-06 | [7 empty] | 0.6 | 1.2 | 0.6 | MM964383
2025-08-06 | 8L | W15 | RSE | SDC | 0 |  | W15A_RSE | 0 | 0.6 | 0.6 | MM964384
2025-08-06 | [9 empty] | 0 | MM964385
2025-08-06 | [7 empty] | 0.6 | 1.2 | 0.6 | MM964386
2025-08-06 | 8L | W16 | SBL2 | FCH | 1.5 | West | P1088 | 0 | 0.6 | 0.6 | MM964387
2025-08-06 | [7 empty] | 0.6 | 1.2 | 0.6 | MM964388
2025-08-06 | 8L | W16 | SBL2 | FCH | 16.1 | West | P1088 | 0 | 0.6 | 0.6 | MM964389
2025-08-06 | [9 empty] | 0 | MM964390
2025-08-06 | [7 empty] | 0.6 | 1.2 | 0.6 | MM964391
2025-08-06 | [7 empty] | 1.2 | 1.4 | 0.2 | MM964392
2025-08-06 | 8L | W16 | SBL1 | FCH | 22 | West | P1088 | 0 | 0.6 | 0.6 | MM964393
2025-08-06 | [7 empty] | 0.6 | 1.2 | 0.6 | MM964394
2025-08-06 | [9 empty] | 0 | MM964395
2025-08-06 | 7L | W14 | CON-DRV | FCH | 24 | West | P1087 | 0 | 0.6 | 0.6 | MM964396
2025-08-06 | [7 empty] | 0.6 | 1 | 0.4 | MM964397
2025-08-06 | 7L | W14 | SBL1 | FCH | 4.7 | East | W14A_RSE | 0 | 0.6 | 0.6 | MM964398
2025-08-06 |  |  |  | FCH |  |  |  | 0.6 | 1.2 | 0.6 | MM964399
2025-08-06 | 7L | W2 | SBL1 | FCH | 11 | West | P1111 | 0 | 1.2 | 1.2 | MM904142
WEST
EAST
SW
NW

## BENCHES.
DATE | LEVEL | SECTION |  | LOCATION | SAMPLE TYPE | DISTANCE FROM PEG(m) | DIRECTION | PEG ID | DEPTH (m) | FROM | TO | SAMPLE WIDTH | SAMPLE ID | AU | STOPE .AV | SAMPLER | GEOTECH
2025-08-01 | 2L | W23 |  | SBL1 | FLCH | 2 | East | W23_OP |  | 0 | 1 | 1 | MM905313 | 1.45 | 1.9511
[10 empty] | 1 | 2 |  | MM905314 | 2.86
[9 empty] | STD 0925 1.04g/t |  |  |  | MM905315 | 1.06
[10 empty] | 2 | 3 | 1 | MM905316 | 1.79
[10 empty] | 3 | 4 | 1 | MM905317 | 1.94
| 2L | W23 |  | SBL1 | FLCH | 4 | East | W23_OP |  | 0 | 1 | 1 | MM905318 | 1.15
[10 empty] | 1 | 2 | 1 | MM905319 | 0.56
[10 empty] | 2 | 3 | 1 | MM905320 | 2.71
[10 empty] | 3 | 4 | 1 | MM905321 | 2.59
[10 empty] | 4 | 5 | 1 | MM905322 | 2.51
| 3L | W23 |  | SBL2 | SCH | 4.8 | South | W23_OP |  | 0 | 1 | 1 | MM905323 | 1.87 | 1.016
[10 empty] | 1 | 2 | 1 | MM905324 | 0.24
[9 empty] | FDUP |  |  |  | MM905325 | 0.12
[10 empty] | 2 | 3 | 1 | MM905326 | 0.16
[10 empty] | 3 | 4 | 1 | MM905327 | 0.24
[10 empty] | 4 | 5 | 1 | MM905328 | 2.57
| 5L | W8 |  | SBL1 | FLCH | 2 | East | W8_OP |  | 0 | 1.2 | 1.2 | MM905329 | 2.84 | 3.8767
[9 empty] | BLANK |  |  |  | MM905330 | 0
[10 empty] | 1.2 | 2.2 | 1 | MM905331 | 1.11
[10 empty] | 2.2 | 3.2 | 1 | MM905332 | 4.17
[10 empty] | 3.2 | 3.9 | 0.7 | MM905333 | 4.5
| 5L | W8 |  | SBL1 | FLCH | 4 | East | W8_OP |  | 0 | 1 | 1 | MM905334 | 8.96
[9 empty] | STD 0925 1.04g/t |  |  |  | MM905335 | 3.27
[10 empty] | 1 | 2 | 1 | MM905336 | 0.1
[10 empty] | 2 | 2.6 | 0.6 | MM905337 | 0.49
[10 empty] | 2.6 | 3.6 | 1 | MM905338 | 5.23
[10 empty] | 3.6 | 4.3 | 0.7 | MM905339 | 7.49
| 4L | W25 |  | SBL1 | FLCH | 0.4 | North | W25_OP |  | 0 | 1 | 1 | MM905340 | 3.3 | 4.1217
[10 empty] | 1 | 2 | 1 | MM905341 | 3.12
[10 empty] | 2 | 2.7 | 0.7 | MM905342 | 1.8
| 4L | W25 |  | SBL1 | FLCH | 0.4 |  | W25_OP |  | 0 | 1 | 1 | MM905343 | 7.06
[10 empty] | 1 | 2 | 1 | MM905344 | 4.14
[9 empty] | FDUP |  |  |  | MM905345 | 3.79
[10 empty] | 2 | 2.9 | 0.9 | MM905346 | 5.31
| 5L | W12 | A | CON-DRV | SCH | 3.8 | South | W12A_OP |  | 0 | 1 | 1 | MM964270 | 0.18 | 1.458
[10 empty] | 1 | 2 | 1 | MM964271 | 2.95
[10 empty] | 2 | 3 | 1 | MM964272 | 2.65
[10 empty] | 3 | 4 | 1 | MM964273 | 0.73
[10 empty] | 4 | 5 | 1 | MM964274 | 0.78
| 6L | W18 | B | CON-DRV | SCH | 5.2 | West | W18B_OP |  | 0 | 1 | 1 | MM905226 | 1.12 | 1.16
[10 empty] | 1 | 2 | 1 | MM905227 | 1.14
[10 empty] | 2 | 3 | 1 | MM905228 | 1.22
| 6L | W15 | A | SBL2 | SCH | 3 | West | W15A_OP |  | 0 | 1 | 1 | MM905229 | 1.14 | 1.4783
[9 empty] | FDUP |  |  |  | MM905230 | 0.75
[10 empty] | 1 | 2 | 1 | MM905231 | 0.72
[10 empty] | 2 | 3 | 1 | MM905232 | 0.58
| 6L | W15 | A | SBL1 | SCH | 5 | West | W15A_OP |  | 0 | 1 | 1 | MM905233 | 1.23
[10 empty] | 1 | 2 | 1 | MM905234 | 0.99
[9 empty] | BLANK |  |  |  | MM905235 | 1.06
[10 empty] | 2 | 3 | 1 | MM905236 | 0.61
[10 empty] | 3 | 4 | 1 | MM905237 | 5.078
| 6L | W8 | C | SBL2 | FLCH | 2 | East | W8C_OP | 1 | 0 | 1 | 1 | MM905238 | 4.29 | 2.3925
[10 empty] | 1 | 2 | 1 | MM905239 | 0.08
[10 empty] | 2 | 3 | 1 | MM905240 | 0.08
[10 empty] | 3 | 4 | 1 | MM905241 | 5.12
| 6L | W4 |  | SBL2 | FLCH | 2 | East | W4_OP | 19 | 0 | 1 | 1 | MM905242 | 2.72 | 4.5782
[10 empty] | 1 | 2 | 1 | MM905243 | 3.29
[10 empty] | 2 | 3 | 1 | MM905244 | 2.996
[9 empty] | STD 0660 3.16g/t |  |  |  | MM905245 | 0
[10 empty] | 3 | 4 | 1 | MM905246 | 4.24
| 6L | W4 |  | SBL2 | FLCH | 2 | East | W4_OP | 19 | 0 | 1 | 1 | MM905247 | 4.16
[10 empty] | 1 | 2 | 1 | MM905248 | 5.13
[10 empty] | 2 | 3 | 1 | MM905249 | 7.19
[9 empty] | FDUP |  |  |  | MM905250 | 7.13
[10 empty] | 3 | 4 | 1 | MM905251 | 6.9
| 6L | W2 |  | SBL2 | FLCH | 2 | West | W2_OP | 18.2 | 0 | 1 | 1 | MM905252 | 13.39 | 9.714
[10 empty] | 1 | 2 | 1 | MM905253 | 17.52
| 6L | W2 |  | SBL2 | FLCH | 2 | West | W2_OP |  | 0 | 1 | 1 | MM905254 | 6.894
[9 empty] | BLANK |  |  |  | MM905255 | 3.21
[10 empty] | 1 | 2 | 1 | MM905256 | 6.69
| 6L | W2 |  | SBL2 | FLCH | 2 | West | W2_OP |  | 0 | 1 | 1 | MM905257 | 6.83
[10 empty] | 1 | 2 | 1 | MM905258 | 6.96
| 6L | E1 | B | SBL1 | FLCH | 1 | East | E1_OP |  | 0 | 1 | 1 | MM905259 | 1.32 | 1.7095
[10 empty] | 1 | 2 | 1 | MM905260 | 2.099
2025-08-02 | 5L | W12 |  | CON-DRV | SCH | 11 | South | W12_OP |  | 0 | 1 | 1 | MM907001 | 17.13 | 5.5579
[10 empty] | 1 | 2 | 1 | MM907002 | 5.203
[10 empty] | 2 | 3 | 1 | MM907003 | 6.27
[10 empty] | 3 | 4 | 1 | MM907004 | 8.23
[10 empty] | 4 | 5 | 1 | MM907005 | 4.38
[10 empty] | 5 | 6 | 1 | MM907006 | 2.097
[10 empty] | 6 | 7 | 1 | MM907007 | 4.384
[10 empty] | 7 | 8 | 1 | MM907008 | 0.583
[10 empty] | 8 | 9 | 1 | MM907009 | 4.122
[10 empty] | 9 | 10 | 1 | MM907010 | 3.18
| 5L | W8 |  | SBL1 | FLCH | 2 | East | W8-OP |  | 0 | 1 | 1 | MM905347 | 2.11 | 7.4867
[10 empty] | 1 | 2 | 1 | MM905348 | 2.16
[10 empty] | 2 | 3 | 1 | MM905349 | 13.63
[9 empty] | FDUP |  |  | 0 | MM905350 | 2.26
[10 empty] | 3 | 4 | 1 | MM905351 | 18.99
| 5L | W8 |  | SBL1 | FLCH | 4 | East | W8_OP |  | 0 | 1 | 1 | MM905352 | 15.06
[10 empty] | 1 | 2 | 1 | MM905353 | 0.48
[10 empty] | 2 | 3 | 1 | MM905354 | 1.15
[9 empty] | BLANK |  |  | 0 | MM905355 | 0
[10 empty] | 3 | 4 | 1 | MM905356 | 5.27
[10 empty] | 4 | 5 | 1 | MM905357 | 8.53
| 4L | W25 |  | SBL1 | FLCH | 0.4 | North | W25_OP |  | 0 | 1 | 1 | MM905358 | 1.08 | 2.5183
[10 empty] | 1 | 2 | 1 | MM905359 | 0.85
[10 empty] | 2 | 3 | 1 | MM905360 | 3.2
| 4L | W25 |  | SBL1 | FLCH | 0.4 | North | W25_OP |  | 0 | 1 | 1 | MM905361 | 1.05
[10 empty] | 1 | 2 | 1 | MM905362 | 5.27
[10 empty] | 2 | 3 | 1 | MM905363 | 3.66
| 2L | W23 |  | SBL1 | FLCH | 2 | East | W23_OP |  | 0 | 1 | 1 | MM905364 | 0.53 | 1.4132
[9 empty] | STD UGHLG 004851 |  |  | 0 | MM905365 | 1.11
[10 empty] | 1 | 2 | 1 | MM905366 | 0.47
[10 empty] | 2 | 3 | 1 | MM905367 | 0.51
[10 empty] | 3 | 4 | 1 | MM905368 | 1.036
[10 empty] | 4 | 5 | 1 | MM905369 | 4.52
[9 empty] | FDUP |  |  | 0 | MM905370 | 0.32
| 3L | W23 |  | SBL2 | SCH | 5 | South | W23_OP |  | 0 | 1 | 1 | MM905371 | 0.515 | 1.6132
[10 empty] | 1 | 2 | 1 | MM905372 | 1.148
[10 empty] | 2 | 3 | 1 | MM905373 | 5.492
[10 empty] | 3 | 4 | 1 | MM905374 | 0.52
[9 empty] | BLANK |  |  | 0 | MM905375 | 3.2
[10 empty] | 4 | 5 | 1 | MM905376 | 0.391
| 6L | W8 | C | SBL2 | FLCH | 2 | East | W8C_OP | 2.2 | 0 | 1 | 1 | MM905261 | 1.57 | 1.2723
[10 empty] | 1 | 2 | 1 | MM905262 | 1.78
[10 empty] | 2 | 3 | 1 | MM905263 | 1.65
[10 empty] | 3 | 4 | 1 | MM905264 | 0.089
[9 empty] | STD 0925 1.04g/t |  |  | 0 | MM905265 | 1.03
| 6L | W4 |  | SBL2 | FLCH | 2 | East | W4_OP | 18 | 0 | 1 | 1 | MM905266 | 3.97 | 3.3288
[10 empty] | 1 | 2 | 1 | MM905267 | 2.44
[10 empty] | 2 | 3 | 1 | MM905268 | 2.87
[10 empty] | 3 | 4 | 1 | MM905269 | 5.27
[9 empty] | FDUP |  |  | 0 | MM905270 | 7.68
| 6L | W4 |  | SBL2 | FLCH | 4 | East | W4_OP |  | 0 | 1 | 1 | MM905271 | 4.62
[10 empty] | 1 | 2 | 1 | MM905272 | 4.63
[10 empty] | 2 | 3 | 1 | MM905273 | 1.25
[10 empty] | 3 | 4 | 1 | MM905274 | 1.58
[9 empty] | BLANK |  |  | 0 | MM905275 | 0
| 6L | E1 | B | SBL1 | FLCH | 1.2 | East | E1_OP | 17 | 0 | 1 | 1 | MM905276 | 0.94 | 3.565
[10 empty] | 1 | 2 | 1 | MM905277 | 4.67
[10 empty] | 2 | 3 | 1 | MM905278 | 3.98
| 6L | E1 | B | SBL1 | FLCH | 3.2 | East | E1_OP | 17 | 0 | 1 | 1 | MM905279 | 7.58
[10 empty] | 1 | 2 | 1 | MM905280 | 4.09
[10 empty] | 2 | 3 | 1 | MM905281 | 0.13
| 6L | W2 |  | SBL2 | FLCH | 2 | West | W2_OP |  | 0 | 1 | 1 | MM905282 | 6.74 | 5.9556
[10 empty] | 1 | 2 | 1 | MM905283 | 7.85
[10 empty] | 2 | 3 | 1 | MM905284 | 3.88
[9 empty] | STD 0925 |  |  | 0 | MM905285 | 1.05
| 6L | W2 |  | SBL2 | FLCH | 4 | West | W2_OP |  | 0 | 1 | 1 | MM905286 | 6.55
[10 empty] | 1 | 2 | 1 | MM905287 | 8.45
[10 empty] | 2 | 3 | 1 | MM905288 | 3.17
| 6L | W2 |  | SBL2 | FLCH | 4 | West | W2_OP |  | 0 | 1 | 1 | MM905289 | 5.29
[9 empty] | FDUP |  |  | 0 | MM905290 | 3.77
[10 empty] | 1 | 2 | 1 | MM905291 | 6.74
[10 empty] | 2 | 3 | 1 | MM905292 | 4.93
| 6L | W15 | A | SBL2 | SCH | 4.2 | West | W15A_OP |  | 0 | 1 | 1 | MM967188 | 1.47 | 0.9325
[10 empty] | 1 | 2 | 1 | MM967189 | 0.74
[9 empty] | FDUP |  |  | 0 | MM967190 | 0.44
[10 empty] | 2 | 3 | 1 | MM967191 | 0.34
| 6L | W15 | A | SBL1 | FLCH | 2.6 | West | W15A_OP |  | 0 | 1 | 1 | MM967192 | 0.58
[10 empty] | 1 | 2 | 1 | MM967193 | 0.6
[10 empty] | 2 | 3 | 1 | MM967194 | 1.02
[9 empty] | STD 0925 1.04g/t |  |  | 0 | MM967195 | 0.68
[10 empty] | 3 | 4 | 1 | MM967196 | 0.45
[10 empty] | 4 | 4.6 | 0.6 | MM967197 | 2.26
2025-08-03 | 6L | W18 | B | CON-DRV | GRABS | 1.2 | East | W18B_OP |  | 0 | 1 | 1 | MM905293 | 0.85 | 1.5315
[10 empty] | 1 | 2 | 1 | MM905294 | 0.52
[9 empty] | BLANK UGHLG004857 |  |  | 0 | MM905295 | 1.71
[10 empty] | 2 | 3 | 1 | MM905296 | 2.99
[10 empty] | 3 | 4 | 1 | MM905297 | 2.01
[10 empty] | 4 | 5 | 1 | MM905298 | 6.88
| 6L | W18 | B | CON-DRV | SLGE | 3 | North | W18B_OP |  | 0 | 0.8 | 0.8 | MM905299 | 0.13
[10 empty] | 0.8 | 1.6 | 0.8 | MM905300 | 0.26
[10 empty] | 1.6 | 2.4 | 0.8 | MM967701 | 3.79
| 6L | W18 | B | CON-DRV | SLGE | 4 | North | W18B_OP |  | 0 | 0.8 | 0.8 | MM967702 | 0.41
[10 empty] | 0.8 | 1.6 | 0.8 | MM967703 | 2.85
[10 empty] | 1.6 | 2.4 | 0.8 | MM967704 | 1.4
[9 empty] | STD 0660 3.16g/t |  |  | 0 | MM967705 | 3.11
| 6L | W18 | B | CON-DRV | FLCH | 0.4 | North | W18B_OP |  | 0 | 0.6 | 0.6 | MM967706 | 0.79
[10 empty] | 0.6 | 1.2 | 0.6 | MM967707 | 0.42
[10 empty] | 1.2 | 1.8 | 0.6 | MM967708 | 0.27
| 6L | W18 | B | CON-DRV | FLCH | 0.4 | North | W18B_OP |  | 0 | 0.6 | 0.6 | MM967709 | 0.38
[9 empty] | FDUP |  |  | 0 | MM967710 | 0.46
[10 empty] | 0.6 | 1.2 | 0.6 | MM967711 | 0.43
[10 empty] | 1.2 | 1.8 | 0.6 | MM967712 | 2.94
[10 empty] | 1.8 | 2.4 | 0.6 | MM967713 | 0.7
[10 empty] | 2.4 | 3 | 0.6 | MM967714 | 0.5
[9 empty] | BLANK UGHLG004759 |  |  | 0 | MM967715 | 1.25
[10 empty] | 3 | 3.6 | 0.6 | MM967716 | 0.92
| 6L | W15 |  | SBL1 | SCH | 6 | West | W15_OP |  | 0 | 1 | 1 | MM967717 | 1.07 | 1.5825
[10 empty] | 1 | 2 | 1 | MM967718 | 0.88
[10 empty] | 2 | 3 | 1 | MM967719 | 1.72
[10 empty] | 3 | 4 | 1 | MM967720 | 2.66
| 6L | W15 |  | SBL1 | SLGE | 3 | West | W15_OP |  | 0 | 0.9 | 0.9 | MM967722 | 0.06 | 0.06
[10 empty] | 0.9 | 1.8 | 0.9 | MM967723 | 0.06
2025-08-04 | 5L | W12 | C | CON-DRV | FLCH | 4 | South | W12_OP |  | 0 | 0.6 | 0.6 | MM907022 | 1.22 | 2.9756
[10 empty] | 0.6 | 1.2 | 0.6 | MM907023 | 3.2
[10 empty] | 1.2 | 1.8 | 0.6 | MM907024 | 0.62
[10 empty] | 1.8 | 2.4 | 0.6 | MM907025 | 3.07
[10 empty] | 2.4 | 3 | 0.6 | MM907026 | 4.86
[10 empty] | 3 | 3.6 | 0.6 | MM907027 | 6.73
| 5L | W12 | C | CON-DRV | SLGE | 6 | South | W12_OP |  | 0 | 0.8 | 0.8 | MM907028 | 5.52
[10 empty] | 0.8 | 2 | 1.2 | MM907029 | 0.26
| 5L | W12 | C | CON-DRV | SLGE | 8 | South | W12_OP |  | 0 | 0.8 | 0.8 | MM907030 | 1.3
[10 empty] | 0.8 | 2 | 1.2 | MM907031 | NS
| 5L | W12 | C | CON-DRV | SLGE | 10 | South | W12_OP |  | 0 | 0.8 | 0.8 | MM907032 | NS
[10 empty] | 0.8 | 2 | 1.2 | MM907033 | NS
| 2L | W23 |  | SBL1 | FLCH | 2 | East | W23_OP |  | 0 | 1 | 1 | MM905377 | 1.854 | 3.6116
[10 empty] | 1 | 2 | 1 | MM905378 | 7.629
[10 empty] | 2 | 3 | 1 | MM905379 | 8.151
[10 empty] | 3 | 4 | 1 | MM905380 | 7.176
| 2L | W23 |  | SBL1 | FLCH | 4 | East | W23_OP |  | 0 | 1 | 1 | MM905381 | 0.582
[10 empty] | 1 | 2 | 1 | MM905382 | 0.624
[10 empty] | 2 | 3 | 1 | MM905383 | 1.329
[10 empty] | 3 | 4 | 1 | MM905384 | 1.548
| 3L | W23 |  | SBL2 | FLCH | 0.5 | South | W23_OP |  | 0 | 1 | 1 | MM905607 | 0.14 | 1.3625
[10 empty] | 1 | 2 | 1 | MM905608 | 0.32
[10 empty] | 2 | 3 | 1 | MM905609 | 0.67
[9 empty] | BLANK |  |  | 0 | MM905610 | 0
[10 empty] | 3 | 4 | 1 | MM905611 | 4.32
| 4L | W25 |  | SBL1 | FLCH | 0.4 | North | W25_OP |  | 0 | 1 | 1 | MM905612 | 3.37 | 3.3833
[10 empty] | 1 | 2 | 1 | MM905613 | 3.72
[10 empty] | 2 | 3 | 1 | MM905614 | NS
[9 empty] | FDUP |  |  | 0 | MM905615 | 1.54
[10 empty] | 3 | 4 | 1 | MM905616 | 3.06
| 5L | W8 |  | SBL1 | FLCH | 2 | East | W8_OP |  | 0 | 1 | 1 | MM905617 | 3.1 | 1.3856
[10 empty] | 1 | 2 | 1 | MM905618 | 4.93
[10 empty] | 2 | 3 | 1 | MM905619 | 0.3
[10 empty] | 3 | 4 | 1 | MM905620 | 0.08
| 5L | W8 |  | SBL1 | FLCH | 4 | East | W8_OP |  | 0 | 1 | 1 | MM905621 | 0.67
[10 empty] | 1 | 2 | 1 | MM905622 | 0.95
[10 empty] | 2 | 3 | 1 | MM905623 | 0.89
[10 empty] | 3 | 4 | 1 | MM905624 | 0.73
[9 empty] | STD 0660 3.16g/t |  |  | 0 | MM905625 | 3.22
[10 empty] | 4 | 5 | 1 | MM905626 | 0.82
| 6L | W8 | C | SBL2 | FLCH | 5 | East | W8C_OP | 0 | 0 | 1 | 1 | MM967724 | 0.614 | 1.6692
[9 empty] | STD 0660 3.16g/t |  |  | 0 | MM967725 | 3.15
[10 empty] | 1 | 2 | 1 | MM967726 | 1.941
| 6L | W8 | C | SBL2 | FLCH | 7 | East | W8C_OP | 0 | 0 | 1 | 1 | MM967727 | 2.038
[10 empty] | 1 | 2 | 1 | MM967728 | 2.084
| 6L | W2 |  | SBL2 | FLCH | 3 | West | W2_OP | 16 | 0 | 1 | 1 | MM967729 | 0.273 | 8.7966
[9 empty] | FDUP |  |  | 0 | MM967730 | 0.705
[10 empty] | 1 | 2 | 1 | MM967731 | 1.547
[10 empty] | 2 | 3 | 1 | MM967732 | 28.89
[10 empty] | 3 | 3.4 | 0.4 | MM967733 | 25.92
[10 empty] | 3.4 | 4.4 | 1 | MM967734 | 25.41
[9 empty] | BLANK |  |  | 0 | MM967735 | 0.241
[10 empty] | 4.4 | 5.4 | 1 | MM967736 | 4.539
| 6L | W2 |  | SBL2 | FLCH | 5 | West | W2_OP | 16 | 0 | 1 | 1 | MM967737 | 3.478
[10 empty] | 1 | 2 | 1 | MM967738 | 2.266
[10 empty] | 2 | 3 | 1 | MM967739 | 0.12
[10 empty] | 3 | 4 | 1 | MM967740 | 4.581
| 6L | W2 |  | SBL2 | FLCH | 5 | West | W2_OP | 16 | 0 | 1 | 1 | MM967741 | 4.131
[10 empty] | 1 | 2 | 1 | MM967742 | 4.404
| 6L | W4 |  | SBL2 | FLCH | 1 | East | W4_OP | 18 | 0 | 1 | 1 | MM967743 | 3.561 | 2.0195
[10 empty] | 1 | 2 | 1 | MM967744 | 1.531
[9 empty] | STD 0925 |  |  | 0 | MM967745 | 1.03
[10 empty] | 2 | 3 | 1 | MM967746 | 1.447
[10 empty] | 3 | 4 | 1 | MM967747 | 1.539
| 6L | E1 | B | SBL1 | FLCH | 2 | East | E1B_OP | 11 | 0 | 1 | 1 | MM967748 | 13.027 | 8.8162
[10 empty] | 1 | 2 | 1 | MM967749 | 11.347
[9 empty] | FDUP |  |  | 0 | MM967750 | 9.554
| 6L | E1 | B | SBL1 | FLCH | 2 | East | E1B_OP | 11 | 0 | 1 | 1 | MM967751 | 8.738
[10 empty] | 1 | 2 | 1 | MM967752 | 10.44
[10 empty] | 2 | 3 | 1 | MM967753 | 0.529
| 6L | W18 | B | CON-DRV | FLCH | 0.4 | North | W18B_OP |  | 0 | 0.6 | 0.6 | MM907501 | 6.82 | 5.0467
[10 empty] | 0.6 | 1.2 | 0.6 | MM907502 | 5.27
[10 empty] | 1.2 | 1.8 | 0.6 | MM907503 | 6.25
| 6L | W18 | B | CON-DRV | FLCH | 0.4 | West | W18B_OP |  | 0 | 0.6 | 0.6 | MM907504 | 2.82
[9 empty] | BLANK |  |  | 0 | MM907505 | 1.95
[10 empty] | 0.6 | 1.2 | 0.6 | MM907506 | 5.03
[10 empty] | 1.2 | 1.8 | 0.6 | MM907507 | 4.09
| 6L | W15 | A | SBL1 | FLCH | 1.5 | West | W15A_OP |  | 0 | 1 | 1 | MM907508 | 5.14 | 3.12
[10 empty] | 1 | 2 | 1 | MM907509 | 2.73
[9 empty] | FDUP |  |  | 0 | MM907510 | 1.47
[10 empty] | 2 | 3 | 1 | MM907511 | 0.84
| 6L | W15 | A | SBL1 | FLCH | 3.5 | West | W15A_OP |  | 0 | 1 | 1 | MM907512 | 2.81
[10 empty] | 1 | 2 | 1 | MM907513 | 3.08
[10 empty] | 2 | 3 | 1 | MM907514 | 4.12
2025-08-05 | 5L | W12 | C | CON-DRV | FLCH | 1 | South | W12_OP |  | 0 | 0.6 | 0.6 | MM907055 | 0.14 | 0.14833
[10 empty] | 0.6 | 1.2 | 0.6 | MM907056 | 0.18
[10 empty] | 1.2 | 1.8 | 0.6 | MM907057 | 0.09
[10 empty] | 0 | 0.6 | 0.6 | MM907058 | 0.15
[10 empty] | 0.6 | 1.2 | 0.6 | MM907059 | 0.13
[10 empty] | 1.2 | 1.8 | 0.6 | MM907060 | 0.2
| 5L | W8 |  | SBL1 | FLCH | 2 | East | W8_OP | 7.9 | 0 | 1 | 1 | MM905627 | 0.55 | 3.138
[10 empty] | 1 | 2 | 1 | MM905628 | 1.66
[10 empty] | 2 | 3 | 1 | MM905629 | 1.75
[9 empty] | STD |  |  | 0 | MM905630 | 3.15
[10 empty] | 3 | 4 | 1 | MM905631 | 5.58
[10 empty] | 4 | 5 | 1 | MM905632 | 6.15
| 4L | W25 |  | SBL1 | FLCH | 0.5 | North | W25_OP |  | 0 | 1 | 1 | MM905633 | 0.83 | 1.9425
[10 empty] | 1 | 2 | 1 | MM905634 | 0.39
[9 empty] | BLANK |  |  | 0 | MM905635 | 0
[10 empty] | 2 | 3 | 1 | MM905636 | 3.39
[10 empty] | 3 | 4 | 1 | MM905637 | 3.16
| 3L | W23 |  | SBL2 | FLCH | 2 | South | W23_OP |  | 0 | 1 | 1 | MM905647 | 0.48 | 0.28
[10 empty] | 1 | 2 | 1 | MM905648 | 0.21
[10 empty] | 2 | 3 | 1 | MM905649 | 0.08
[9 empty] | STD |  |  | 0 | MM905650 | 3.23
[10 empty] | 3 | 4 | 1 | MM905651 | 0.35
| 2L | W23 |  | SBL1 | FLCH | 2 | East | W23_OP |  | 0 | 1 | 1 | MM905652 | 0.85 | 3.62
[10 empty] | 1 | 2 | 1 | MM905653 | 2.16
[10 empty] | 2 | 3 | 1 | MM905654 | 5.53
[9 empty] | BLANK |  |  | 0 | MM905655 | 0
[10 empty] | 3 | 4 | 1 | MM905656 | 3.75
[10 empty] | 4 | 5 | 1 | MM905657 | 5.81
| 4L | W27 |  | HLGE | SCH | 14.2 | West | P1140 |  | 0 | 0.6 | 0.6 | MM905658 | 0.9 | 0.60667
[10 empty] | 0.6 | 1.2 | 0.6 | MM905659 | 0.34
[10 empty] | 1.2 | 1.8 | 0.6 | MM905660 | 0.58
| 6L | W14 | A | SBL1 | SCH | 1.5 | East | W14_OP |  | 0 | 1 | 1 | MM967754 | 0.54 | 0.5475
[9 empty] | BLANK |  |  | 0 | MM967755 | 0
[10 empty] | 1 | 2 | 1 | MM967756 | 1.27
| 6L | W14 | A | SBL1 | SCH | 3.5 | East | W14A_OP | 1 | 0 | 1 | 1 | MM967757 | 0.31
[10 empty] | 1 | 2 | 1 | MM967758 | 0.07
| 6L | W15 | A | SBL1 | SCH | 2 | West | W15A_OP | 1 | 0 | 1 | 1 | MM967759 | 0.13 | 0.23
[10 empty] | 1 | 2 | 1 | MM967760 | 0.33
[10 empty] | 2 | 3 | 1 | MM967761 | 0.24
[10 empty] | 3 | 4 | 1 | MM967762 | 0.22
| 6L | W8 | C | SBL2 | FLCH | 2 | East | W8C_OP | 1 | 0 | 1 | 1 | MM967763 | 0.36 | 0.86
[10 empty] | 1 | 2 | 1 | MM967764 | 0.98
[9 empty] | STD 0660 3.16g/t |  |  | 0 | MM967765 | 3.08
[10 empty] | 2 | 3 | 1 | MM967766 | 1.56
[10 empty] | 3 | 4 | 1 | MM967767 | 0.54
| 6L | W8 | C | SBL2 | FLCH | 3 | East | W8C_OP | 1 | 0 | 1 | 1 | MM967768 | 0.28
[10 empty] | 1 | 2 | 1 | MM967769 | 0.69
[9 empty] | FDUP |  |  | 0 | MM967770 | 0.48
[10 empty] | 2 | 3 | 1 | MM967771 | 0.27
[10 empty] | 3 | 4 | 1 | MM967772 | 0.19
| 6L | W18 |  | CON-DRV | SLGE | 1 | West | W18_OP |  | 0 | 1 | 1 | MM967773 | 0.17 | 0.44
[10 empty] | 1 | 2 | 1 | MM967774 | NS
[9 empty] | BLANK |  |  | 0 | MM967775 | 0.01
| 6L | W18 |  | CON-DRV | SLGE | 3 | West | W18_OP |  | 0 | 1 | 1 | MM967776 | NS
[10 empty] | 1 | 2 | 1 | MM967777 | 0.71
| 6L | W4 | A | SBL2 | FLCH | 1.5 | West | W4A_OP | 22 | 0 | 1 | 1 | MM967778 | 0.8 | 1.2733
[10 empty] | 1 | 2 | 1 | MM967779 | 1.65
[10 empty] | 2 | 3 | 1 | MM967780 | 1.37
| 6L | W3 | A | SBL2 | FLCH | 3.5 | East | W4A_OP | 20 | 0 | 1 | 1 | MM967781 | NS | 2.3233
[10 empty] | 1 | 2 | 1 | MM967782 | 2.74
[10 empty] | 2 | 3 | 1 | MM967783 | 2.63
[10 empty] | 3 | 4 | 1 | MM967784 | 1.6
[9 empty] | STD 0660 3.16g/t |  |  | 0 | MM967785 | 3.12
| 6L | W2 |  | SBL2 | FLCH | 3 | West | W2_OP | 18 | 0 | 1 | 1 | MM967786 | 0.7 | 1.3367
[10 empty] | 1 | 2 | 1 | MM967787 | 0.98
[10 empty] | 2 | 3 | 1 | MM967788 | 2.33
| 6L | W2 |  | SBL2 | FLCH | 5 | West | W2_OP | 18 | 0 | 1 | 1 | MM967789 | 1.67 | 0.90333
[9 empty] | FDUP |  |  | 0 | MM967790 | 3.54
[10 empty] | 1 | 2 | 1 | MM967791 | 0.21
[10 empty] | 2 | 3 | 1 | MM967792 | 0.83
| 6L | W2 |  | SBL2 | FLCH | 7 | West | W2_OP | 18 | 0 | 1 | 1 | MM967793 | 0.36 | 0.935
[10 empty] | 1 | 2 | 1 | MM967794 | 1.51
[9 empty] | BLANK |  |  | 0 | MM967795 | 0
| 6L | E1 | B | SBL2 | FLCH | 2.4 | East | E1B_OP | 13.2 | 0 | 1 | 1 | MM967796 | 1.27 | 0.9525
[10 empty] | 1 | 2 | 1 | MM967797 | 1.02
[10 empty] | 2 | 3 | 1 | MM967798 | 1.21
[10 empty] | 3 | 4 | 1 | MM967799 | 0.31
[10 empty] | 4 | 5 | 1 | MM967800 | -
2025-08-06 | 2L | W23 |  | SBL1 | FLCH | 2 | East | W23_OP | 0 | 0 | 1 | 1 | MM905661 | 2.39 | 3.4686
[10 empty] | 1 | 2 | 1 | MM905662 | 3.68
[10 empty] | 2 | 3 | 1 | MM905663 | 1.45
[10 empty] | 3 | 4 | 1 | MM905664 | 3.53
[9 empty] | STD 0660 3.16g/t |  |  | 0 | MM905665 | 3.23
[10 empty] | 4 | 5 | 1 | MM905666 | 5.24
[10 empty] | 5 | 6 | 1 | MM905667 | 3.95
[10 empty] | 6 | 7 | 1 | MM905668 | 4.04
| 4L | W25 |  | SBL1 | FLCH | 0.5 | North | W25_OP | 3 | 0 | 1 | 1 | MM905669 | 2.2 | 4.1429
[9 empty] | FDUP |  |  | 0 | MM905670 | 3.04
[10 empty] | 1 | 2 | 1 | MM905671 | 0.1
[10 empty] | 2 | 3 | 1 | MM905672 | 1.72
| 4L | W25 |  | SBL1 | FLCH | 0.5 | North | W25-OP | 3 | 0 | 1 | 1 | MM905673 | 4.81
[10 empty] | 1 | 2 | 1 | MM905674 | 3.94
[9 empty] | BLANK |  |  | 0 | MM905675 | 0
[10 empty] | 2 | 3 | 1 | MM905676 | 8.84
[10 empty] | 3 | 4 | 1 | MM905677 | 7.39
| 5L | W8 |  | SBL1 | FLCH | 2 | East | W8_OP | 10.4 | 0 | 1 | 1 | MM905678 | 2.12 | 1.372
[10 empty] | 1 | 2 | 1 | MM905679 | 2.3
[10 empty] | 2 | 3 | 1 | MM905680 | 0.25
[10 empty] | 3 | 4 | 1 | MM905681 | 0.24
[10 empty] | 4 | 5 | 1 | MM905682 | 1.95
| 5L | W12 | B | CON-DRV | SLGE | 4 | South | W12_BENCH |  | 0 | 0.8 | 0.8 | MM907070 | 0.1 | 0.09
[10 empty] | 0.8 | 1.5 | 0.7 | MM907071 | 0.08
| 5L | W12 | B | CON-DRV | SLGE | 4 | South | W12_BENCH |  | 0 | 0.8 | 0.8 | MM907072
[10 empty] | 0.8 | 1.5 | 0.7 | MM907073
| 5L | W12 | B | CON-DRV | SLGE | 4 | South | W12_BENCH |  | 0 | 0.8 | 0.8 | MM907074
[10 empty] | 0.8 | 1.5 | 0.7 | MM907075
| 5L | W12 | B | CON-DRV | SLGE | 4 | South | W12_BENCH |  | 0 | 0.8 | 0.8 | MM907076
[10 empty] | 0.8 | 1.5 | 0.7 | MM907077
| 5L | W12 | B | CON-DRV | SLGE | 4 | South | W12_BENCH |  | 0 | 0.8 | 0.8 | MM907078
[10 empty] | 0.8 | 1.5 | 0.7 | MM907079
| 6L | W18 |  | CON-DRV | SLGE | 1.2 | West | W18_OP |  | 0 | 1 | 1 | MM904101 | 0.54 | 1.746
[10 empty] | 1 | 2 | 1 | MM904102 | 1.44
| 6L | W18 |  | CON-DRV | SLGE | 1.2 | West | W18_OP |  | 0 | 1 | 1 | MM904103 | 0.36
[10 empty] | 1 | 2 | 1 | MM904104 | 0.11
[9 empty] | STD 0660 3.16g/t |  |  | 0 | MM904105 | 2.36
| 6L | W18 |  | CON-DRV | SCH |  |  |  |  | 0 | 1 | 1 | MM904143 | 6.28
| 6L | W15 | A | SBL1 | FLCH | 1 | West | W15A_OP | 3.2 | 0 | 1 | 1 | MM904106 | 0.89 | 2.3725
[10 empty] | 1 | 2 | 1 | MM904107 | 4.6
| 6L | W15 | A | SBL1 | FLCH | 3 | West | W15A_OP | 3.2 | 0 | 1 | 1 | MM904108 | 3.75
[10 empty] | 1 | 2 | 1 | MM904109 | 0.25
[9 empty] | FDUP |  |  | 0 | MM904110 | 1.83
| 6L | W8 | C | SBL2 | FLCH | 1 | East | W8C_OP | 3.6 | 0 | 1 | 1 | MM904111 | 0.74 | 2.1283
[10 empty] | 1 | 2 | 1 | MM904112 | 0.45
[10 empty] | 2 | 2.7 | 0.7 | MM904113 | 0.12
| 6L | W8 | C | SBL2 | FLCH | 4 | East | W8C_OP | 2.3 | 0 | 1 | 1 | MM904114 | 0.21
[9 empty] | BLANK |  |  | 0 | MM904115 | 0
[10 empty] | 1 | 2 | 1 | MM904116 | 5.77
[10 empty] | 2 | 3 | 1 | MM904117 | 5.48
| 6L | W4 |  | SBL2 | FLCH | 2 | East | W4_OP | 22 | 0 | 1 | 1 | MM904118 | 4.98 | 4.97
[10 empty] | 1 | 2 | 1 | MM904119 | 6.02
[10 empty] | 2 | 3 | 1 | MM904120 | 5.08
[10 empty] | 3 | 4 | 1 | MM904121 | 6.81
| 6L | W4 |  | SBL2 | FLCH | 4 | East | W4_OP | 22 | 0 | 1 | 1 | MM904122 | 7.62
[10 empty] | 1 | 2 | 1 | MM904123 | 2
[10 empty] | 2 | 3 | 1 | MM904124 | 3.95
[9 empty] | STD 0660 3.16g/t |  |  | 0 | MM904125 | 3.17
[10 empty] | 3 | 4 | 1 | MM904126 | 3.3
| 6L | W2 |  | SBL2 | FLCH | 3 | West | W2_OP | 18 | 0 | 1 | 1 | MM904127 | 1.86 | 3.425
[10 empty] | 1 | 2 | 1 | MM904128 | 4.57
[10 empty] | 2 | 3 | 1 | MM904129 | 3.79
[9 empty] | FDUP |  |  | 0 | MM904130 | 3.18
| 6L | W2 |  | SBL2 | FLCH | 5 | West | W2_OP |  | 0 | 1 | 1 | MM904131 | 2.27
[10 empty] | 1 | 2 | 1 | MM904132 | 2.27
[10 empty] | 2 | 3 | 1 | MM904133 | 4.51
| 6L | W2 |  | SBL2 | FLCH | 7 | West | W2_OP |  | 0 | 1 | 1 | MM904134 | 3.74
[9 empty] | BLANK |  |  | 0 | MM904135 | 0
[10 empty] | 1 | 2 | 1 | MM904136 | 4.39
| 6L | E1 | B | SBL1 | FLCH | 1 | East | E1B_OP | 15 | 0 | 1 | 1 | MM904137 | 4.13 | 4.515
[10 empty] | 1 | 2 | 1 | MM904138 | 2.09
| 6L | E1 | B | SBL1 | FLCH | 3 | East | E1B_OP |  | 0 | 1 | 1 | MM904139 | 5.92
[10 empty] | 1 | 2 | 1 | MM904140 | 5.92
[10 empty] | 0 | 1 | 1 | MM904141 | 5.13
| 6L | W18 |  | CON-DRV | SCH |  |  |  |  | 0 | 1 | 1 | MM904143 | 6.28
PASS
PASS
PASS
PASS
PASS
7

## TRAMMING.
DISPATCH DATE | ORIGINAL SAMPLE ID | NEW SAMPLE ID | AU | AVERAGE PER BOX ( g/t ) | DATE SAMPLED
2025-08-01 | 6L_W2B_BOX_N/S | UGGS012579 | 2.53 |  | 2025-07-31
| 6L_W3_SCRAPPING_N/S | UGGS012580 | 2.69 | 2.665
| 6L_W4A-BOX_N/S | UGGS012581 | 2.64
| 6L_W15B_BOX_N/S | UGGS012582 | 2.61
| 6L_E1C-BOX_N/S | UGGS012583 | 3.97
| UGGS012502 2.12g/t | UGGS012584 | 4.26
| BLANK UGGS012506 0.00g/t | UGGS012585 | 1.23
| STD 0660 3.16g/t | UGGS012586 | 0.9 | fail
| 4L_W23C_BOX_N/S | UGGS012587 | 0 | pass
| 4L_W23B_BOX_N/S | UGGS012588 | 3.23
| 5L_W8A_BOX_N/S | UGGS012589 | 2.29
| 6L_W18B_BOX_DS | UGGS012590 | 1.84
| 6L_W4A_BOX_DS | UGGS012591 | 1.92
| 6L_W15B_BOX_DS | UGGS012592 | 0.15
| 6L_W3_SCRAPPING_DS | UGGS012593 | 2.26
| 6L_W19A_BOX_DS | UGGS012594 | 0.75
| UGGS012439 1.32g/t | UGGS012595 | 1.15
| STD 0660 3.16g/t | UGGS012596 | 1.02 | fail
| BLANK | UGGS012597 | 0 | pass
| 4L_W23B_BOX_D/S | UGGS012598 | 0.64
| 4L_W23C_BOX_D/S | UGGS012599 | 1.84
| 5L_W8A_BOX_D/S | UGGS012600 | 2.95
2025-08-02 | 6L_W15B_BOX_NS | UGGS012601 | 1.59 |  | 2025-08-01
| 6L_W2_BOX_NS | UGGS012602 | 8.15
| 6L_W3_SCRAPPING_NS | UGGS012603 | 4.31
| 6L-W4A_BOX_N/S | UGGS012604 | 2.29
| 6L-W8B_BOX_N/S | UGGS012605 | 2.14
| 5L_W12A_BOX_N/S | UGGS012606 | 0.96
| 4L_W25A_BOX_N/S | UGGS012607 | 0.65
| 4L_W23C_BOX_N/S | UGGS012608 | 2.69
| STD 0925 1.04g/t | UGGS012609 | 1.08 | pass
| BLANK | UGGS012610 | 0 | pass
| UGGS012492 4.59g/t | UGGS012611 | 4.96
| 4L_W23C_BOX_D/S | UGGS012612 | 2.281
| 5L_W8A_BOX_D/S | UGGS012613 | 2.283
| 5L_W12A_BOX_D/S | UGGS012614 | 0.712
| STD 0925 1.04g/t | UGGS012615 | 1.03
| UGHLG004855 3.65g/t | UGGS012616 | 7.832
| 6L_W3_SCRAPPING_DS | UGGS012617 | 2.599
| 6L-W4A_BOX_D/S | UGGS012618 | 3.225
| 6L-E1B_BOX_D/S | UGGS012619 | 3.408
| 6L-E1C_BOX_D/S | UGGS012620 | 5.139
| 6L_W18B_BOX_DS | UGGS012621 | 2.86
| 6L_W15B_BOX_DS | UGGS012622 | 0.303
| 6L_W2B_BOX_DS | UGGS012623 | 1.991
2025-08-03 | 6L_W2B_BOX_DS | UGGS012624 | 1.33 | 1.85 | 2025-08-02
| 6L_W2B_BOX_DS | UGGS012642 | 2.37
| 4L_W23B_BOX_N/S | UGGS012631 | 1.39
| 4L_W23C_BOX_D/S | UGGS012635 | 0.95 | 1.97
| 4L_W23C_BOX_N/S | UGGS012632 | 2.99
| 5L_W12A_BOX_D/S | UGGS012636 | 0.89 | 0.94
| 5L_W12A_BOX_N/S | UGGS012634 | 0.99
| 5L_W8A_BOX_D/S | UGGS012637 | 6.64 | 5.7
| 5L_W8A_BOX_N/S | UGGS012633 | 4.75
| 6L_W15B_BOX_DS | UGGS012645 | 0.85 | 0.62
| 6L_W15B_BOX_NS | UGGS012626 | 0.39
| 6L_W18B_BOX_DS | UGGS012643 | 4.57 | 2.72
| 6L_W18B_BOX_NS | UGGS012627 | 0.87
| 6L_W3_SCRAPING_DS | UGGS012647 | 5.76
| 6L-E1B_BOX_D/S | UGGS012641 | 2.4 | 3.54
| 6L-E1C_BOX_D/S | UGGS012644 | 4.68
| 6L-W4A_BOX_D/S | UGGS012646 | 1.25 | 1.67
| 6L-W4A_BOX_N/S | UGGS012625 | 2.09
| BLANK | UGGS012630 | 0 | pass
| BLANK | UGGS012638 | 0 | pass
| STD 0660 3.16g/t | UGGS012639 | 3.19 | pass
| STD 0925 1.04g/t | UGGS012629 | 3.14 | fail
| UGGS012491 1.67g/t | UGGS012640 | 1.55
| UGHLG004761 1.42g/t | UGGS012628 | 1.52
2025-08-04 |  |  |  |  | 2025-08-03
| 4L_W23B_BOX_N/S | UGGS012656 | 4.24 | 2.8217
| 4L_W23C_BOX_D/S | UGGS012660 | 3.105
| 4L_W23C_BOX_N/S | UGGS012657 | 1.12
| 5L_W12B_BOX_NS | UGGS012659 | 0.3 | 0.3
| 5L_W8B_BOX_DS | UGGS012661 | 2.847 | 3.9835
| 5L_W8B_BOX_NS | UGGS012658 | 5.12
| 6L_E1B_BOX_DS | UGGS012664 | 4.398 | 4.347
| 6L_E1C-BOX_D/S | UGGS012667 | 4.296
| 6L_W15B_BOX_DS | UGGS012670 | 0.933 | 0.7915
| 6L_W15B_BOX_NS | UGGS012652 | 0.65
| 6L_W18B_BOX_DS | UGGS012671 | 4.418 | 5.349
| 6L_W18B_BOX_NS | UGGS012650 | 6.28
| 6L_W2B_BOX_DS | UGGS012668 | 3.077 | 2.1935
| 6L_W2B_BOX_NS | UGGS012651 | 1.31
| 6L_W3_SCRAPPING_NS | UGGS012648 | 2.14 | 3.239
| 6L_W3_SCRAPPING_DS | UGGS012666 | 4.338
| 6L_W8C_BOX_DS | UGGS012669 | 1.305 | 1.305
| 6L-W4A_BOX_D/S | UGGS012665 | 1.94 | 1.57
| 6L-W4A_BOX_N/S | UGGS012649 | 1.2
| BLANK | UGGS012653 | 0 | pass
| BLANK | UGGS012662 | 0 | pass
| CHECK | UGGS012654 | 2.77
| STD 0660 3.16g/t | UGGS012655 | 3.12 | pass
| UGGS012440 0.29g/t | UGGS012663 | 0.335 | pass
2025-08-05 | 6L_W3_SCRAPPING_NS | UGGS012672 | 1.85 | 1.85 | 2025-08-04
| 4L_W23C_BOX_D/S | UGGS012682 | 0.975 | 1.3603
| 4L_W23C_BOX_N/S | UGGS012679 | 2.6
| 4L_W25_BOX_D/S | UGGS012683 | 0.506
| 5L_W12B_BOX_DS | UGGS012684 | 0.367 | 1.0885
| 5L_W12B_BOX_NS | UGGS012681 | 1.81
| 5L_W8B_BOX_DS | UGGS012685 | 3.391 | 2.0205
| 5L_W8B_BOX_NS | UGGS012680 | 0.65
| 6L_E1B_BOX_DS | UGGS012689 | 7 | 5.26
| 6L_E1B_BOX_NS | UGGS012674 | 1.78
| 6L_E1C_BOX_DS | UGGS012690 | 7
| 6L_W15B_BOX_DS | UGGS012693 | 0.662 | 0.671
| 6L_W15B_BOX_NS | UGGS012677 | 0.68
| 6L_W18B_BOX_DS | UGGS012687 | 7 | 4.235
| 6L_W18B_BOX_NS | UGGS012676 | 1.47
| 6L_W2B_BOX_DS | UGGS012686 | 3.135 | 3.8383
| 6L_W2B_BOX_NS | UGGS012675 | 1.38
| 6L_W2B_WINZ_DS | UGGS012688 | 7
| 6L_W3_SCRAPPING_DS | UGGS012694 | 4.967 | 3.7557
| 6L_W4A_BOX_DS | UGGS012692 | 4.97
| 6L_W4A_BOX_NS | UGGS012673 | 1.33
| 6L_W8C_BOX_DS | UGGS012691 | 0.72 | 0.72
| BLANK | UGGS012697 | 0 | pass
| STD 0660 3.16g/t | UGGS012696 | 3.2 | pass
| UGGS012304 0.83g/t | UGGS012678 | 1.02 | pass
| UGHLG004920 1.77g/t | UGGS012695 | 1.24 | pass
2025-08-06 | 6L_W2B_BOX_NS | UGGS012698 | 2.067 |  | 2025-08-05
| 6L_W3_SCRAPPING | UGGS012699 | 2.428
| 6L_W13C_BOX_NS | UGGS012700 | 0.723
| 6L_W9A_BOX_NS | UGGS012701 | 3.588
| 6L_W4A_BOX_NS | UGGS012702 | 1.365
| BLANK | UGGS012703 | 0
| UGHLG004856 1.37g/t | UGGS012704 | 1.515
| STD 0660 3.16g/t | UGGS012705 | 3.21
| 5L_W8B_BOX_NS | UGGS012706 | 2.185
| 5L_W12B_BOX_NS | UGGS012707 | 1.344
| 4L_W23B_BOX_N/S | UGGS012708 | 2.38
| 6L_E1B_BOX_DS | UGGS012709
| 6L_W4A_BOX_DS | UGGS012710
| 6L_W13C_BOX_DS | UGGS012711
| 6L_W2B_BOX_DS | UGGS012712
| 6L_E1C_BOX_DS | UGGS012713
| 6L_W2_WINZE_DS | UGGS012714
| 6L_W8C_BOX_DS | UGGS012715
| 5L_W8A_BOX_DS | UGGS012716
| 5L_W12A_BOX_DS | UGGS012717
| 4L_W23C_BOX_D/S | UGGS012718
| 4L_W25A_BOX_D/S | UGGS012719
| STD 0660 3.16g/t | UGGS012720
| UGHLG12652 0.65g/t | UGGS012721
2025-08-01 | 6L_W2B_BOX_N/S | UGGS012579 |  |  | 2025-07-31
| 6L_W3_SCRAPPING_N/S | UGGS012580
| 6L_W4A-BOX_N/S | UGGS012581
| 6L_W15B_BOX_N/S | UGGS012582
| 6L_E1C-BOX_N/S | UGGS012583
| UGGS012502 | UGGS012584
| BLANK UGGS012506 | UGGS012585
| STD 0660 3.16g/t | UGGS012586
| 4L_W23C_BOX_N/S | UGGS012587
| 4L_W23B_BOX_N/S | UGGS012588
| 5L_W8A_BOX_N/S | UGGS012589
| 6L_W15B_BOX_N/S | UGGS012601 | 1.59 |  |  | UGGS012601 | 1.59
| 4L_W23B_BOX_N/S | UGGS012602 | 8.15 |  |  | UGGS012602 | 8.15
| 6L_W3_SCRAPPING_N/S | UGGS012603 | 4.31 |  |  | UGGS012603 | 4.31
| 6L_W4A-BOX_N/S | UGGS012604 | 2.29 |  |  | UGGS012604 | 2.29
| 5L_W8A_BOX_N/S | UGGS012605 | 2.14 |  |  | UGGS012605 | 2.14
| 5L_W12A_BOX_N/S | UGGS012606 | 0.96 |  |  | UGGS012606 | 0.96
| 4L_W25A_BOX_N/S | UGGS012607 | 0.65 |  |  | UGGS012607 | 0.65
| 4L_W23C_BOX_N/S | UGGS012608 | 2.69 |  |  | UGGS012608 | 2.69
| Std 0925 1.04g/t | UGGS012609 | 1.08 |  |  | UGGS012609 | 1.08
| BLANK | UGGS012610 | 0 |  |  | UGGS012610 | 0
| UGGS012492 | UGGS012611 | 4.96 |  |  | UGGS012611 | 4.96
| 4L_W23C_BOX_D/S | UGGS012612
| 5L_W8A_BOX_D/S | UGGS012613
UGGS012614
UGGS012615
UGGS012616
UGGS012617
UGGS012618
UGGS012619
UGGS012620
UGGS012621
UGGS012622
UGGS012623

## HOISTING.
DISPATCH DATE | ORIGINAL SAMPLE ID | NEW SAMPLE ID | AU | AVERAGE ( g/t ) | DATE SAMPLED
2025-08-01 | E1_BOX_N/S | UGHLG004894 | 1.88 | 1.99 | 2025-07-31
| E2_BOX_N/S | UGHLG004895 | 2
| BOX2_NS 1 | UGHLG004896 | 1.69
| BOX2_NS 2 | UGHLG004897 | 2.95
| STD 0660 3.16g/t | UGHLG004898 | 1.44
| BLANK | UGHLG004899 | 1.98
| UGHLG004853 2.49g/t | UGHLG004900 | 3.2 | pass
| E1_BOX_D/S | UGHLG004901 | 3.24 | fail
| E2_BOX_D/S | UGHLG004902 | 2.66 | pass
2025-08-02 | E1_BOX_D/S | UGHLG004903 | 3.15 | 2.132 | 2025-08-01
| E2_BOX_D/S | UGHLG004904 | 5.17
| E1_BOX_N/S | UGHLG004905 | 3.27
| E2_BOX_N/S | UGHLG004906 | 1.12
| BOX1_DS 1 | UGHLG004907 | 3.2
| BOX1_DS 2 | UGHLG004908 | 0.7
| BOX1_NS 1 | UGHLG004909 | 0.66
| BOX1_NS 2 | UGHLG004910 | 0.96
| BOX2_DS 1 | UGHLG004911 | 1.12
| BOX2_DS 2 | UGHLG004912 | 1.12
| BOX2_NS 1 | UGHLG004913 | 1.36
| BOX2_NS 2 | UGHLG004914 | 0.85
| STD 0660 3.16g/t | UGHLG004915 | 1.01 | fail
| BLANK | UGHLG004916 | 0 | pass
| UGHLG004852 1.59g/t | UGHLG004917 | 0.51
2025-08-03 | E1_BOX_D/S | UGHLG004918 | 1.57 | 1.67 | 2025-08-02
| E2_BOX_D/S | UGHLG004919 | 1.17
| E1_BOX_N/S | UGHLG004920 | 1.77
| E2_BOX_N/S | UGHLG004921 | 1.21
| BLANK | UGHLG004922 | 0 | pass
| UGHLG004760 1.17g/t | UGHLG004923 | 1.23
| STD 0660 3.16g/t | UGHLG004924 | 3.1 | pass
2025-08-04 | E1_BOX_N/S | UGHLG004925 | 2.19 | 1.816 | 2025-08-03
| E2_BOX_N/S | UGHLG004926 | 1.18
| BOX1_NS 1 | UGHLG004927 | 0.96
| BOX1_NS 2 | UGHLG004928
| BOX2_NS 1 | UGHLG004929 | 3.23
| BOX2_NS 2 | UGHLG004930 | 1.52
| STD 0925 1.04g/t | UGHLG004931 | 1.08
| BLANK | UGHLG004932 | 0
| UGGS012443 1.53g/t | UGHLG004933 | 2.03
2025-08-05 | E1_BOX_N/S | UGHLG004934 | 1.34 | 3.13 | 2025-08-04
| E2_BOX_N/S | UGHLG004935 | 2.34
| E1_BOX_D/S | UGHLG004936 | 3.73
| E2_BOX_D/S | UGHLG004937 | 2.32
| BOX1_NS 1 | UGHLG004938 | 2.24
| BOX1_NS 2 | UGHLG004939 | 6.81
| BLANK | UGHLG004940 | 0 | pass
| UGGS012437 (1.22g/t) | UGHLG004941 | 1.63
| STD 0660 3.16g/t | UGHLG004942 | 3.09 | pass
2025-08-06 | E1_BOX_N/S | UGHLG004943 | 11.51 | 4.6865 | 2025-08-05
| E2_BOX_N/S | UGHLG004944 | 3.11
| BOX2_DS 1 | UGHLG004945 | 2.367
| BOX2_DS 2 | UGHLG004946 | 1.759
| BLANK | UGHLG004947 | 0
| STD 0660 3.16g/t | UGHLG004948 | 3.23
| UGHLG4919 1.17g/t | UGHLG004949 | 1.301

## DEV.TRKR
2025-08-01 | [13 empty] | 3LRCH | 6LRC | 6LRC
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | AVE | CHOCKED | CH
1L_W26_HLGE_XCN
1L_W28_CON-DRV_WEST
1L_W28_SBL1_DRV_WEST
2L_W28_CON-DRV_WEST
2L_W28_HLGE_WEST
3L_W29_RSE
3L_W29_X/C
4L_W29_HLGE_WEST
4L_W26_WINZ
3L_E9_HLGE_EAST
4L_E13_HLGE_EAST
5L_W11_SBL1_DRV_WEST
5L_W13_ConDRV_WEST
5L_W13_HLGE
5L_W13_RSE
5L_W13_BOX_RSE
6A_W2_SBL1_DRV_EAST
6A_W2_SBL1_WEST
6A_HLGE_W1_DRV_WEST
6A_HLGE_W13_DRV_WEST
6A_W13_RSE
6L_W18_SBL3_EAST
6L_W18_SBL3_WEST
6L_W19_RSE
6L_W19_SBL3_EAST
6L_W19_SBL3_WEST
6L_W19_SBL3_XCN
6L_W2_SBL3_WEST
6L_W2_RSE
6L_W5_RSE
6L_W5_SBL3
6L_W5_SBL3_EAST
6L_W5_SBL3_WEST
6L_W5_SBL4_EAST
6L_W6_SBL3_EAST
6L_W7_RSE
7L_W2_SBL2_EAST
7L_W1_SBL2_EAST
7L_W2_SBL2_WEST | 0.36 | 1.17 |  | 3.58
7L_W14B_RSE
7L_W14B_SBL1_WEST
7L_W14B_SBL1_EAST
8L_W14_SBL1_WEST
8L_W14_SBL2_EAST
8L_W14_SBL2_WEST
8L_W15_RSE
8L_W15_SBL1_WEST
8L_W15_SBL2_EAST
8L_W15_SBL2_WEST
8L_W16A_RSE
8L_W16B_RSE

## Development.
| 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | Grand Total
3L_E9_HAULAGE_EAST | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 38.4
3L_W28_SL_2_EAST | 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-17: 0; 2025-08-20: 1.6; 2025-08-21: 1.6; 2025-08-22: 1.6; 2025-08-23: 1.6; 2025-08-25: 1.6; 2025-08-26: 1.6; 2025-08-27: 1.6; 2025-08-28: 1.6; 2025-08-29: 1.6; 2025-08-30: 1.6; 2025-08-31: 0 | 16
3L_W29_RAISE | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 |  |  |  |  | 0 | [6 empty] | 0 | 12.6
4L_E13_HAULAGE | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 38.4
4L_W29_HAULAGE | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 0 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 1.3 | 1.13 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 31.03
0
5L_W11_SL_1_WEST' | 2025-08-01: 1.6; 2025-08-02: 1.6; 2025-08-04: 1.6; 2025-08-05: 1.6; 2025-08-06: 1.6; 2025-08-07: 1.6; 2025-08-08: 1.6; 2025-08-09: 1.6; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 1.6; 2025-08-14: 1.6; 2025-08-15: 1.6; 2025-08-16: 1.6 | 19.2
5L_W13_CROSS_CUT | 2025-08-01: 1.3; 2025-08-02: 1.3; 2025-08-03: 0; 2025-08-04: 1.3; 2025-08-05: 1.3; 2025-08-06: 1.3; 2025-08-07: 1.3; 2025-08-08: 1.3; 2025-08-09: 1.3; 2025-08-13: 1.3; 2025-08-14: 1.3; 2025-08-15: 1.3; 2025-08-16: 1.3; 2025-08-18: 1.3; 2025-08-19: 1.3 | 18.2
5L_W14_CDRIVE_WEST | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |  | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |  | 38.4
5L_W14_HAULAGE | 1.6 | 1.6 |  | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |  | 38.4
5L_W2_CROSS_CUT | 2025-08-01: 1.6; 2025-08-02: 1.6; 2025-08-03: 0; 2025-08-04: 1.6; 2025-08-05: 1.6; 2025-08-06: 1.6; 2025-08-07: 1.6; 2025-08-08: 1.6; 2025-08-09: 1.6; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 1.6; 2025-08-14: 1.6 | 16
5L_W26_HOISTROOM | 2025-08-15: 1.6; 2025-08-16: 1.6; 2025-08-18: 1.6; 2025-08-19: 1.6; 2025-08-20: 1.6; 2025-08-21: 1.6; 2025-08-22: 1.6; 2025-08-23: 1.6; 2025-08-25: 1.6; 2025-08-26: 1.6; 2025-08-27: 1.6; 2025-08-28: 1.6; 2025-08-29: 1.6; 2025-08-30: 1.6 | 22.4
6LA_W5_DRIVE_EAST | 2025-08-18: 1.3; 2025-08-19: 1.3; 2025-08-20: 1.3; 2025-08-21: 1.3; 2025-08-22: 1.3; 2025-08-23: 1.3; 2025-08-24: 0; 2025-08-25: 1.3; 2025-08-26: 1.3; 2025-08-27: 1.3; 2025-08-28: 1.3; 2025-08-29: 1.3; 2025-08-30: 1.3 | 15.6
6LA_W2_SL1_DRIVE | 1.3 | 1.3 | 0 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 0 | 0 | 1.3 | 1.3 | 1.3 | 1.3 |  | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 |  | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 |  | 31.2
6LA_W4_DRIVE_EAST | 2025-08-01: 1.6; 2025-08-02: 1.6; 2025-08-03: 0; 2025-08-04: 1.6; 2025-08-05: 1.6; 2025-08-06: 1.6; 2025-08-07: 1.6; 2025-08-08: 1.6; 2025-08-09: 1.6; 2025-08-13: 1.6 | 14.4
6LA_W3_RAISE | [9 empty] | 0 | 0 | 0 |  | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  | 13.5
6L__W14_RAISE | 2025-08-01: 0.9; 2025-08-02: 0.9; 2025-08-03: 0; 2025-08-04: 0.9; 2025-08-05: 0.9; 2025-08-06: 0.9; 2025-08-07: 0.9; 2025-08-08: 0.9; 2025-08-09: 0.9; 2025-08-10: 9; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0.9; 2025-08-24: 0 | 17.1
6LA_W14_DRIVE_WEST | 2025-08-14: 1.3; 2025-08-15: 1.3; 2025-08-16: 1.3; 2025-08-18: 1.3; 2025-08-19: 1.3; 2025-08-20: 1.3; 2025-08-21: 1.3; 2025-08-22: 1.3; 2025-08-23: 1.3; 2025-08-25: 1.3; 2025-08-26: 1.3; 2025-08-27: 1.3; 2025-08-28: 1.3; 2025-08-29: 1.3; 2025-08-30: 1.3; 2025-08-31: 0 | 19.5
0
6LA_W19_DRIVE_WEST | 2025-08-01: 1.6; 2025-08-02: 1.6; 2025-08-04: 1.6; 2025-08-05: 1.6; 2025-08-06: 1.6; 2025-08-07: 1.6; 2025-08-08: 1.6; 2025-08-09: 1.6; 2025-08-13: 1.6; 2025-08-14: 1.6; 2025-08-15: 1.6; 2025-08-16: 1.6; 2025-08-18: 1.6; 2025-08-19: 1.6; 2025-08-20: 1.6 | 24
6LW24_BYPASS | 2025-08-21: 1.6; 2025-08-22: 1.6; 2025-08-23: 1.6; 2025-08-25: 1.6; 2025-08-26: 1.6; 2025-08-27: 1.6; 2025-08-28: 1.6; 2025-08-29: 1.6; 2025-08-30: 1.6 | 14.4
7L_E1_OREPASS | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 21.6
7L_E1_TWAY | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  | 21.6
7L_W2_SL_2_WEST | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |  | 38.4
8L_W17_SL_2_WEST | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |  | 38.4
8L_W14_TWAY | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | [8 empty] | 16.2
8L_W15_SL_3_WEST | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 38.4
8L_W15_SLOT | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 21.6
8L_W16_HUALAGE_WEST | 2025-08-17: 0; 2025-08-19: 1.6; 2025-08-20: 1.6; 2025-08-21: 1.6; 2025-08-22: 1.6; 2025-08-23: 1.6; 2025-08-24: 0; 2025-08-25: 1.6; 2025-08-26: 1.6; 2025-08-27: 1.6; 2025-08-28: 1.6; 2025-08-29: 1.6; 2025-08-30: 1.6; 2025-08-31: 0 | 17.6
8L_W16_TWAY | 2025-08-01: 0.9; 2025-08-02: 0.9; 2025-08-04: 0.9; 2025-08-05: 0.9; 2025-08-06: 0.9; 2025-08-07: 0.9 | 5.4
8L_W16_SL_3_WEST | [7 empty] | 1.6 | 1.6 |  |  |  | 1.6 | 1.6 | 1.6 | 1.6 |  | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 28.8
8L_W16_OREPASS | 2025-08-01: 0.9; 2025-08-02: 0.9; 2025-08-04: 0.9; 2025-08-05: 0.9; 2025-08-06: 0.9; 2025-08-07: 0.9; 2025-08-08: 0.9; 2025-08-09: 0.9; 2025-08-13: 0.9; 2025-08-14: 0.9; 2025-08-15: 0.9; 2025-08-16: 0.9; 2025-08-18: 0.9; 2025-08-19: 0.9; 2025-08-20: 0.9; 2025-08-21: 0.9; 2025-08-22: 0.9 | 15.3
8L_W14_OREPASS | 2025-08-24: 0; 2025-08-27: 0.9; 2025-08-28: 0.9; 2025-08-29: 0.9; 2025-08-30: 0.9; 2025-08-31: 0 | 3.6
10L_E2_RAISE | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  |  |  | 0.9 | 0.9 | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  | 21.6
10L_E2_C_DRIVE | 1.6 | 1.6 |  | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 |  | 38.4
10L_E1_RAISE | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  |  |  | 0.9 | 0.9 | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  | 21.6
10L_W8_RAISE |  |  | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 19.8
10LW7_BOX_RSE | 2025-08-05: 0.9; 2025-08-06: 0.9; 2025-08-07: 0.9; 2025-08-08: 0.9; 2025-08-09: 0.9; 2025-08-13: 0.9; 2025-08-14: 0.9; 2025-08-15: 0.9; 2025-08-16: 0.9 | 8.1
10LW7_CDRIVE_EAST | 2025-08-18: 1.6; 2025-08-19: 1.6; 2025-08-20: 1.6; 2025-08-21: 1.6; 2025-08-22: 1.6; 2025-08-23: 1.6; 2025-08-25: 1.6; 2025-08-26: 1.6; 2025-08-27: 1.6; 2025-08-28: 1.6; 2025-08-29: 1.6; 2025-08-30: 1.6 | 19.2
0
9L_E3_OREPASS | 2025-08-07: 0.9; 2025-08-08: 0.9; 2025-08-09: 0.9; 2025-08-13: 0.9; 2025-08-15: 0.9; 2025-08-16: 0.9; 2025-08-18: 0.9; 2025-08-19: 0.9; 2025-08-20: 0.9; 2025-08-21: 0.9; 2025-08-22: 0.9; 2025-08-23: 0.9; 2025-08-25: 0.9; 2025-08-26: 0.9; 2025-08-27: 0.9; 2025-08-28: 0.9; 2025-08-29: 0.9; 2025-08-30: 0.9 | 16.2
9L_E3_WASTEPASS | 2025-08-07: 0.9; 2025-08-08: 0.9; 2025-08-09: 0.9; 2025-08-13: 0.9; 2025-08-15: 0.9; 2025-08-16: 0.9; 2025-08-18: 0.9; 2025-08-19: 0.9; 2025-08-20: 0.9; 2025-08-21: 0.9; 2025-08-22: 0.9; 2025-08-23: 0.9; 2025-08-25: 0.9; 2025-08-26: 0.9; 2025-08-27: 0.9; 2025-08-28: 0.9; 2025-08-29: 0.9; 2025-08-30: 0.9 | 16.2
10L_E3_OREPASS | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  |  |  | 0.9 |  | 0.9 | 0.9 |  | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  | 19.8
10L_E3_WASTEPAS | 0.9 | 0.9 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  |  |  | 0.9 | 0.9 | 0.9 | 0.9 |  | 0.9 |  | 0.9 | 0.9 | 0.9 | 0.9 |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 |  | 20.7
10L_W15_OREPASS | 2025-08-01: 0.9; 2025-08-02: 0.9; 2025-08-03: 0; 2025-08-04: 0.9; 2025-08-05: 0.9; 2025-08-07: 0.9; 2025-08-08: 0.9; 2025-08-09: 0.9; 2025-08-14: 0.9; 2025-08-15: 0.9; 2025-08-16: 0.9; 2025-08-18: 0.9; 2025-08-19: 0.9; 2025-08-21: 0.9; 2025-08-22: 0.9; 2025-08-23: 0.9 | 13.5
10L_W15_WASTEPASS | 2025-08-06: 0.9; 2025-08-07: 0.9; 2025-08-08: 0.9; 2025-08-09: 0.9; 2025-08-15: 0.9; 2025-08-16: 0.9; 2025-08-18: 0.9; 2025-08-19: 0.9; 2025-08-20: 0.9; 2025-08-21: 0.9; 2025-08-22: 0.9; 2025-08-23: 0.9 | 10.8
10L_E7_DAM | 2025-08-06: 1.3; 2025-08-08: 1.3; 2025-08-13: 1.3; 2025-08-14: 1.3; 2025-08-15: 1.3; 2025-08-18: 1.3; 2025-08-19: 1.3; 2025-08-20: 1.3; 2025-08-21: 1.3; 2025-08-22: 1.3; 2025-08-23: 1.3; 2025-08-25: 1.3; 2025-08-26: 1.3; 2025-08-27: 1.3; 2025-08-28: 1.3 | 19.5
Venning Shaft Overrun | 2025-08-01: 0.9; 2025-08-02: 0.9; 2025-08-03: 0.9; 2025-08-04: 0.9; 2025-08-06: 0.9; 2025-08-07: 0.9; 2025-08-08: 0.9; 2025-08-09: 0.9; 2025-08-10: 0.9; 2025-08-13: 0.9 | 9
Grand Total | 35.7 | 35.7 | 0.9 | 36.6 | 36.6 | 38.8 | 40.2 | 42.2 | 40.9 | 9.9 | 0 | 0 | 40.4 | 37.4 | 41 | 39.7 | 0 | 41.4 | 42.1 | 40.6 | 42.4 | 42.4 | 41.5 | 0 | 38.8 | 38.63 | 39.7 | 39.7 | 38.4 | 38.4 | 0 | 960.03 | 960.03

## Breaking.
TOTAL UNDERGROUND |  | Total | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
Broken Tonnes | Ore Tonnes | 27195 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 0 | 0 | 910 | 910 | 875 | 875 | 875 | 875 | 875 | 875 | 875 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015
| Au_Dil | 2.2484 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 0 | 0 | 2.2564 | 2.2564 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284
Broken Tonnes (5L and Above) | Ore Tonnes | 10955 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 0 | 0 | 350 | 350 | 315 | 315 | 315 | 315 | 315 | 315 | 315 | 455 | 455 | 455 | 455 | 455 | 455 | 455 | 455 | 455 | 455
| Au_Dil | 1.8903 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 0 | 0 | 1.8827 | 1.8827 | 1.8712 | 1.8712 | 1.8712 | 1.8712 | 1.8712 | 1.8712 | 1.8712 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065
0
1L W28 STOPE | Stoping Tons | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1L_TOTAL | Total Stoping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2L_W4_STOPE | Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L_W23A STOPE | Stoping Tons | 1820 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 |  |  | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
| Au_Dil | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 |  |  | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986
3L_W23B STOPE | Stoping Tons | 2030 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 |  |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
| Au_Dil | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 |  |  | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986
3L_W24B STOPE | Stoping Tons | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stoping Tons | 0
| Au_Dil | 0
| Stoping Tons | 0
| Au_Dil | 0
3L_TOTAL | Total Stoping | 3850 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 0 | 0 | 105 | 105 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 210 | 210 | 210 | 210 | 210 | 210 | 210 | 210 | 210 | 210
2L_W4_STOPE | Au_Dil | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 0 | 0 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986
4L_W10A STOPE | Stoping Tons | 0
4L_W10A_STOPE | Au_Dil | 0
4L_W11B STOPE | Stoping Tons | 0
4L_W10A_STOPE | Au_Dil | 0
4L_W13A STOPE | Stoping Tons | 0
4L_W13A_STOPE | Au_Dil | 0
4L_W14C STOPE | Stoping Tons | 0
| Au_Dil | 0
4L_W14B STOPE | Stoping Tons | 0
4L_W14A_STOPE | Au_Dil | 0
4L_W15A STOPE | Stoping Tons | 0
4L_W16A_STOPE | Au_Dil | 0
4L_W16C STOPE | Stoping Tons | 0
| Au_Dil | 0
4L_W16B STOPE | Stoping Tons | 0
| Au_Dil | 0
4L_W17A STOPE | Stoping Tons | 0
| Au_Dil | 0
4L_W23A STOPE | Stoping Tons | 0
| Au_Dil | 0
4L_W23B_STOPE | Stoping Tons | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L_W5_STOPE | Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L_W26 STOPE | Stoping Tons | 2030 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 |  |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
| Au_Dil | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 |  |  | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463
4L_TOTAL | Total Stoping | 2030 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
4L_W5_STOPE | Au_Dil | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 0 | 0 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463 | 1.9463
5L_W4 STOPE | Stoping Tons | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L_W8 STOPE | Stoping Tons | 3045 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 |  |  | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
| Au_Dil | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 |  |  | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271 | 1.8271
5L_W11 STOPE | Stoping Tons | 2030 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 |  |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
| Au_Dil | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 |  |  | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477
0
5L_TOTAL | Total Stoping | 5075 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 0 | 0 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175 | 175
| Au_Dil | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 0 | 0 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953 | 1.7953
6L_E5 STOPE | Stoping Tons | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_E1 STOPE | Stoping Tons | 1015 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 |  |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
| Au_Dil | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 |  |  | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379 | 3.1379
6L_W1 STOPE | Stoping Tons | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_W2 STOPE | Stoping Tons | 4060 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 |  |  | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
| Au_Dil | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 |  |  | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421 | 2.5421
6L_W3 STOPE | Stoping Tons | 3045 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 |  |  | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
| Au_Dil | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 |  |  | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832 | 2.3832
6L_W4 STOPE | Stoping Tons | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_W8 STOPE | Stoping Tons | 3045 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 |  |  | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
| Au_Dil | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 |  |  | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804
6L_W13 STOPE | Stoping Tons | 1015 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 |  |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
| Au_Dil | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 |  |  | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986 | 1.986
6L_W14 STOPE | Stoping Tons | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_W15_STOPE | Stoping Tons | 2030 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 |  |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
| Au_Dil | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 |  |  | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477 | 1.7477
6L_W19_STOPE | Stoping Tons | 2030 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 |  |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70
| Au_Dil | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 |  |  | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804 | 2.7804
6L_TOTAL | Total Stoping Tons | 16240 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 0 | 0 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560
| Au_Dil | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 0 | 0 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899
Grand Total | Stoping Tons | 27195 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 0 | 0 | 910 | 910 | 875 | 875 | 875 | 875 | 875 | 875 | 875 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015
Grand Total | Au_Dil | 2.2484 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 0 | 0 | 2.2564 | 2.2564 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284
0
0
0
0
0
0
2L Total | Total Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2L Total | Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
3L Total | Total Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L Total | Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
6L Total | Total Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L Total | Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
5L Total | Total Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L Total | Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | Dev_Ore_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | Au_Dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11

## Schedule
Pickstone Peerless Consolidated Mine to Mill Schedule | 67.8
2025-08-01
|  | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
| 2025-08-01 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
MINING
Underground
Waste Volume (bcm) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Waste SG | 0 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9
Waste Tonnes (t) | 2025-08-01: 0
Ore Volume (bcm) | 8587.931 | 255.1724 | 293.1034 | 293.1034 | 293.1034 | 293.1034 | 293.1034 | 293.1034 | 255.1724 | 293.1034 | 293.1034 | 0 | 0 | 293.1034 | 293.1034 | 243.1034 | 281.0345 | 281.0345 | 281.0345 | 243.1034 | 281.0345 | 281.0345 | 329.3103 | 329.3103 | 329.3103 | 329.3103 | 329.3103 | 329.3103 | 329.3103 | 291.3793 | 329.3103 | 329.3103
Ore SG | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9
Ore Tonnes (t) | 24905 | 740 | 850 | 850 | 850 | 850 | 850 | 850 | 740 | 850 | 850 | 0 | 0 | 850 | 850 | 705 | 815 | 815 | 815 | 705 | 815 | 815 | 955 | 955 | 955 | 955 | 955 | 955 | 955 | 845 | 955 | 955
Grade (g/t) | 2.2262 | 2.2027 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2027 | 2.2399 | 2.2399 | 0 | 0 | 2.2399 | 2.2399 | 2.2135 | 2.2508 | 2.2508 | 2.2508 | 2.2135 | 2.2508 | 2.2508 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.1758 | 2.212 | 2.212
Content (g/t) | 55442.665 | 1630.019 | 1903.9106 | 1903.9106 | 1903.9106 | 1903.9106 | 1903.9106 | 1903.9106 | 1630.019 | 1903.9106 | 1903.9106 | 0 | 0 | 1903.9106 | 1903.9106 | 1560.5096 | 1834.4013 | 1834.4013 | 1834.4013 | 1560.5096 | 1834.4013 | 1834.4013 | 2112.4387 | 2112.4387 | 2112.4387 | 2112.4387 | 2112.4387 | 2112.4387 | 2112.4387 | 1838.547 | 2112.4387 | 2112.4387
Strip Ratio
PK02
Waste Volume (bcm) | 2025-08-01: 0
Waste SG | 2025-08-01: 0
Waste Tonnes (t) | 2025-08-01: 0
Ore Volume (bcm) | 2025-08-01: 0
Ore SG | 2025-08-01: 0
Ore Tonnes (t) | 2025-08-01: 0
Grade (g/t) | 2025-08-01: 0
Content (g/t) | 2025-08-01: 0
Strip Ratio | 2025-08-01: 0
PE03
Waste Volume (bcm) | 2025-08-01: 0
Waste SG | 2025-08-01: 0
Waste Tonnes (t) | 2025-08-01: 0
Ore Volume (bcm) | 2025-08-01: 0
Ore SG | 2025-08-01: 0
Ore Tonnes (t) | 2025-08-01: 0
Grade (g/t) | 2025-08-01: 0
Content (g/t) | 2025-08-01: 0
Strip Ratio | 2025-08-01: 0
Total Mined
OP Waste Volume (bcm) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Waste SG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OP Waste Tonnes (t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OP Ore Volume (bcm) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Ore Tonnes (t) | 24905 | 740 | 850 | 850 | 850 | 850 | 850 | 850 | 740 | 850 | 850 | 0 | 0 | 850 | 850 | 705 | 815 | 815 | 815 | 705 | 815 | 815 | 955 | 955 | 955 | 955 | 955 | 955 | 955 | 845 | 955 | 955
Grade (g/t) | 2.2262 | 2.2027 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2027 | 2.2399 | 2.2399 | 0 | 0 | 2.2399 | 2.2399 | 2.2135 | 2.2508 | 2.2508 | 2.2508 | 2.2135 | 2.2508 | 2.2508 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.1758 | 2.212 | 2.212
Content (g/t) | 55442.665 | 1630.019 | 1903.9106 | 1903.9106 | 1903.9106 | 1903.9106 | 1903.9106 | 1903.9106 | 1630.019 | 1903.9106 | 1903.9106 | 0 | 0 | 1903.9106 | 1903.9106 | 1560.5096 | 1834.4013 | 1834.4013 | 1834.4013 | 1560.5096 | 1834.4013 | 1834.4013 | 2112.4387 | 2112.4387 | 2112.4387 | 2112.4387 | 2112.4387 | 2112.4387 | 2112.4387 | 1838.547 | 2112.4387 | 2112.4387
Total Mined-OP (bcm) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Mined-OP (t) | 23950 | 740 | 850 | 850 | 850 | 850 | 850 | 850 | 740 | 850 | 850 | 0 | 0 | 850 | 850 | 705 | 815 | 815 | 815 | 705 | 815 | 815 | 955 | 955 | 955 | 955 | 955 | 955 | 955 | 845 | 955
Strip Ratio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fine Ore Bin | 2025-08-01: Opening
Stockpiled Ore Tonnes - Bal. (t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stockpiled Grade - mcf (g/t) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stockpiled Content - mcf (g) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ROMPAD | 2025-08-01: Opening
Underground Stockpile
Stockpiled Ore Tonnes - Bal. (t) |  | 740 | 1590 | 2440 | 2116.1288 | 2379.1932 | 2055.322 | 1731.4508 | 2471.4508 | 3321.4508 | 4171.4508 | 2997.5796 | 1924.7769 | 1701.9742 | 1378.103 | 909.2318 | 550.3606 | 191.4894 | 0 | 705 | 1520 | 1161.1288 | 942.2576 | 723.3864 | 504.5152 | 285.644 | 653.7084 | 434.8372 | 215.966 | 0 | 0 | 0
Stockpiled Grade - mcf (g/t) |  | 2.2027 | 2.2226 | 2.2286 | 2.2315 | 2.2339 | 2.2355 | 2.2368 | 2.2266 | 2.23 | 2.232 | 2.232 | 2.232 | 2.2344 | 2.2362 | 2.2285 | 2.2391 | 2.2461 | 0 | 2.2135 | 2.2335 | 2.2395 | 2.2271 | 2.2195 | 2.2152 | 2.2131 | 2.2122 | 2.2121 | 2.212 | 0 | 0 | 0
Stockpiled Content - mcf (g) | 0 | 1630.019 | 3533.9296 | 5437.8402 | 4722.2159 | 5314.953 | 4594.6738 | 3872.8854 | 5502.9044 | 7406.815 | 9310.7257 | 6690.6318 | 4296.1239 | 3802.9359 | 3081.7797 | 2026.2642 | 1232.2926 | 430.0983 | 0 | 1560.5096 | 3394.9109 | 2600.3876 | 2098.5 | 1605.5468 | 1117.6092 | 632.1577 | 1446.1568 | 961.8957 | 477.719 | 0 | 0 | 0
Chandelier (Joint Venture)
Stockpiled Ore Tonnes - Bal. (t) | 9400 | 8226.1288 | 7052.2576 | 6230.5478 | 6230.5478 | 6230.5478 | 6230.5478 | 6230.5478 | 5056.6766 | 3882.8054 | 2708.9342 | 2708.9342 | 2708.9342 | 2708.9342 | 2708.9342 | 2708.9342 | 2708.9342 | 2708.9342 | 2708.9342 | 1535.063 | 361.1918 | 361.1918 | 361.1918 | 361.1918 | 361.1918 | 361.1918 | 361.1918 | 361.1918 | 361.1918 | 361.1918 | 361.1918 | 361.1918
Stockpiled Grade - mcf (g/t) | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
Stockpiled Content - mcf (g) | 21620 | 18920.0962 | 16220.1925 | 14330.2598 | 14330.2598 | 14330.2598 | 14330.2598 | 14330.2598 | 11630.3561 | 8930.4523 | 6230.5486 | 6230.5486 | 6230.5486 | 6230.5486 | 6230.5486 | 6230.5486 | 6230.5486 | 6230.5486 | 6230.5486 | 3530.6448 | 830.741 | 830.741 | 830.741 | 830.741 | 830.741 | 830.741 | 830.741 | 830.741 | 830.741 | 830.741 | 830.741 | 830.741
HG Scats
Stockpiled Ore Tonnes - Bal. (t) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stockpiled Grade - mcf (g/t) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stockpiled Content - mcf (g) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sort Pads
Stockpiled Ore Tonnes - Bal. (t) | 10000 | 10000 | 10000 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9647.8386 | 9480.4568 | 9480.4568 | 9480.4568 | 9480.4568 | 9480.4568 | 9480.4568 | 9480.4568 | 9480.4568 | 9480.4568 | 9480.4568 | 9480.4568 | 9367.5516 | 9148.6804 | 8929.8092
Stockpiled Grade - mcf (g/t) | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74
Stockpiled Content - mcf (g) | 7400 | 7400 | 7400 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7139.4006 | 7015.538 | 7015.538 | 7015.538 | 7015.538 | 7015.538 | 7015.538 | 7015.538 | 7015.538 | 7015.538 | 7015.538 | 7015.538 | 6931.9882 | 6770.0235 | 6608.0588
Oxides Stockpile
Stockpiled Ore Tonnes - Bal. (t) | bar: 2025-08-01
Stockpiled Grade - mcf (g/t) | bar: 2025-08-01
Stockpiled Content - mcf (g) | bar: 2025-08-01
Rompad Stockpile
Stockpiled Ore Tonnes - Bal. (t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stockpiled Grade - mcf (g/t) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stockpiled Content - mcf (g) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROCESSING
Fine Ore Bin |  | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Milled Ore Tonnes (t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milled Ore Grade - (g/t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milled Ore Content (g) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recovered Grade (g/t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recovery (%) | 0% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88%
Recovered Gold (kg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Underground Ore Feed |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Milled Ore Tonnes (t) | 24905 | 0 | 0 | 0 | 1173.8712 | 586.9356 | 1173.8712 | 1173.8712 | 0 | 0 | 0 | 1173.8712 | 1072.8027 | 1072.8027 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1006.4894 | 0 | 0 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 586.9356 | 1173.8712 | 1173.8712 | 1060.966 | 955 | 955
Milled Ore Grade - (g/t) | 2.2262 | 0 | 0 | 0 | 2.2315 | 2.2339 | 2.2355 | 2.2368 | 0 | 0 | 0 | 2.232 | 2.232 | 2.2344 | 2.2362 | 2.2285 | 2.2391 | 2.2461 | 2.2499 | 0 | 0 | 2.2395 | 2.2271 | 2.2195 | 2.2152 | 2.2131 | 2.2122 | 2.2121 | 2.212 | 2.1832 | 2.212 | 2.212
Milled Ore Content (g) | 55442.665 | 0 | 0 | 0 | 2619.5349 | 1311.1735 | 2624.1899 | 2625.699 | 0 | 0 | 0 | 2620.0939 | 2394.5079 | 2397.0986 | 2625.0668 | 2616.0251 | 2628.3729 | 2636.5956 | 2264.4996 | 0 | 0 | 2628.9246 | 2614.3262 | 2605.3919 | 2600.3762 | 2597.8902 | 1298.4396 | 2596.6997 | 2596.6153 | 2316.2661 | 2112.4387 | 2112.4387
Recovered Grade (g/t) | 1.9633 | 0 | 0 | 0 | 1.9681 | 1.9702 | 1.9716 | 1.9727 | 0 | 0 | 0 | 1.9685 | 1.9685 | 1.9706 | 1.9722 | 1.9654 | 1.9747 | 1.9809 | 1.9843 | 0 | 0 | 1.9751 | 1.9642 | 1.9575 | 1.9537 | 1.9518 | 1.9511 | 1.9509 | 1.9509 | 1.9254 | 1.9508 | 1.9508
Recovery (%) | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19%
Recovered Gold (kg) | 48.8971 | 0 | 0 | 0 | 2.3103 | 1.1564 | 2.3144 | 2.3157 | 0 | 0 | 0 | 2.3108 | 2.1118 | 2.1141 | 2.3152 | 2.3072 | 2.3181 | 2.3253 | 1.9972 | 0 | 0 | 2.3186 | 2.3057 | 2.2978 | 2.2934 | 2.2912 | 1.1451 | 2.2901 | 2.2901 | 2.0428 | 1.863 | 1.863
Chandelier (Joint Venture) |  | 100% | 100% | 70% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Milled Ore Tonnes (t) | 9038.8082 | 1173.8712 | 1173.8712 | 821.7098 | 0 | 0 | 0 | 0 | 1173.8712 | 1173.8712 | 1173.8712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1173.8712 | 1173.8712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milled Ore Grade - (g/t) | 2.3 | 2.3 | 2.3 | 2.3 | 0 | 0 | 0 | 0 | 2.3 | 2.3 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milled Ore Content (g) | 20789.259 | 2699.9038 | 2699.9038 | 1889.9326 | 0 | 0 | 0 | 0 | 2699.9038 | 2699.9038 | 2699.9038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2699.9038 | 2699.9038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recovered Grade (g/t) | 2.024 | 2.024 | 2.024 | 2.024 | 0 | 0 | 0 | 0 | 2.024 | 2.024 | 2.024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.024 | 2.024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recovery (%) | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88%
Recovered Gold (kg) | 18.2945 | 2.3759 | 2.3759 | 1.6631 | 0 | 0 | 0 | 0 | 2.3759 | 2.3759 | 2.3759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3759 | 2.3759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HG Scats | bar: 2025-08-01 to 2025-08-31
Milled Ore Tonnes (t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milled Ore Grade - (g/t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milled Ore Content (g) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recovered Grade (g/t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recovery (%) | 0% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88%
Recovered Gold (kg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sort Pads |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Milled Ore Tonnes (t) | 1070.1908 | 0 | 0 | 352.1614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167.3818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112.9052 | 218.8712 | 218.8712
Milled Ore Grade - (g/t) | 0.74 | 0 | 0 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.74 | 0.74 | 0.74
Milled Ore Content (g) | 791.9412 | 0 | 0 | 260.5994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123.8626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.5498 | 161.9647 | 161.9647
Recovered Grade (g/t) | 0.53268 | 0 | 0 | 0.53268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53268 | 0.53268 | 0.53268
Recovery (%) | 0.71984 | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98% | 71.98%
Recovered Gold (kg) | 0.57007 | 0 | 0 | 0.18759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.060142 | 0.11659 | 0.11659
Rompad Stockpile |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Milled Ore Tonnes (t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milled Ore Grade - (g/t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milled Ore Content (g) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recovered Grade (g/t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recovery (%) | 0 | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88% | 88%
Recovered Gold (kg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL MILLED
Milled Ore Tonnes (t) | 35013.999 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 586.9356 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1072.8027 | 1072.8027 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 586.9356 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712
Milled Ore Grade - (g/t) | 2.1998 | 2.3 | 2.3 | 1.832 | 2.2315 | 2.2339 | 2.2355 | 2.2368 | 2.3 | 2.3 | 2.3 | 2.232 | 2.232 | 2.2344 | 2.2362 | 2.2285 | 2.2391 | 2.2461 | 2.0346 | 2.3 | 2.3 | 2.2395 | 2.2271 | 2.2195 | 2.2152 | 2.2131 | 2.2122 | 2.2121 | 2.212 | 2.0444 | 1.9375 | 1.9375
Milled Ore Content (g) | 77023.8651 | 2699.9038 | 2699.9038 | 2150.532 | 2619.5349 | 1311.1735 | 2624.1899 | 2625.699 | 2699.9038 | 2699.9038 | 2699.9038 | 2620.0939 | 2394.5079 | 2397.0986 | 2625.0668 | 2616.0251 | 2628.3729 | 2636.5956 | 2388.3622 | 2699.9038 | 2699.9038 | 2628.9246 | 2614.3262 | 2605.3919 | 2600.3762 | 2597.8902 | 1298.4396 | 2596.6997 | 2596.6153 | 2399.8159 | 2274.4034 | 2274.4034
Recovered Grade (g/t) | 1.9364 | 2.024 | 2.024 | 1.5766 | 1.9681 | 1.9702 | 1.9716 | 1.9727 | 2.024 | 2.024 | 2.024 | 1.9685 | 1.9685 | 1.9706 | 1.9722 | 1.9654 | 1.9747 | 1.9809 | 1.7773 | 2.024 | 2.024 | 1.9751 | 1.9642 | 1.9575 | 1.9537 | 1.9518 | 1.9511 | 1.9509 | 1.9509 | 1.7915 | 1.6864 | 1.6864
Recovery (%) | 88.02% | 88% | 88% | 86.06% | 88.19% | 88.19% | 88.19% | 88.19% | 88% | 88% | 88% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 87.35% | 88% | 88% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 88.19% | 87.63% | 87.04% | 87.04%
Recovered Gold (kg) | 67.8 | 2.3759 | 2.3759 | 1.8507 | 2.3103 | 1.1564 | 2.3144 | 2.3157 | 2.3759 | 2.3759 | 2.3759 | 2.3108 | 2.1118 | 2.1141 | 2.3152 | 2.3072 | 2.3181 | 2.3253 | 2.0863 | 2.3759 | 2.3759 | 2.3186 | 2.3057 | 2.2978 | 2.2934 | 2.2912 | 1.1451 | 2.2901 | 2.2901 | 2.1029 | 1.9796 | 1.9796
Tails grade (g/t) | 0.26343 | 0.276 | 0.276 | 0.2554 | 0.26346 | 0.26374 | 0.26392 | 0.26407 | 0.276 | 0.276 | 0.276 | 0.26351 | 0.26351 | 0.2638 | 0.26401 | 0.2631 | 0.26434 | 0.26517 | 0.25731 | 0.276 | 0.276 | 0.2644 | 0.26293 | 0.26203 | 0.26153 | 0.26128 | 0.26118 | 0.26116 | 0.26115 | 0.25289 | 0.25111 | 0.25111
| 35013.999 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 586.9356 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1072.8027 | 1072.8027 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 586.9356 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712 | 1173.8712
Plan (kg) | 2025-08-01: 67.8

## UG_Hoisting
|  |  | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
|  | Total | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
Hoisting Capacity |  | 34800 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 0 | 0 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
Hoisted | Ore Tonnes | 24905 | 740 | 850 | 850 | 850 | 850 | 850 | 850 | 740 | 850 | 850 | 0 | 0 | 850 | 850 | 705 | 815 | 815 | 815 | 705 | 815 | 815 | 955 | 955 | 955 | 955 | 955 | 955 | 955 | 845 | 955 | 955
| Au_Dil | 2.2262 | 2.2027 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2399 | 2.2027 | 2.2399 | 2.2399 | 0 | 0 | 2.2399 | 2.2399 | 2.2135 | 2.2508 | 2.2508 | 2.2508 | 2.2135 | 2.2508 | 2.2508 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.212 | 2.1758 | 2.212 | 2.212
Closing Inventory | Ore Tonnes | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Au_Dil | 2.2284 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 0 | 0 | 2.2564 | 2.2564 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284
Broken Inventory | Ore Tonnes | 27195 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 0 | 0 | 910 | 910 | 875 | 875 | 875 | 875 | 875 | 875 | 875 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015
| Au_Dil | 2.2484 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 2.2564 | 0 | 0 | 2.2564 | 2.2564 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2672 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284 | 2.2284
Broken Inventory (5 and above ) | Ore Tonnes | 10955 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 0 | 0 | 350 | 350 | 315 | 315 | 315 | 315 | 315 | 315 | 315 | 455 | 455 | 455 | 455 | 455 | 455 | 455 | 455 | 455 | 455
| Au_Dil | 1.8903 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 1.8827 | 0 | 0 | 1.8827 | 1.8827 | 1.8712 | 1.8712 | 1.8712 | 1.8712 | 1.8712 | 1.8712 | 1.8712 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065 | 1.9065
LOBE SHAFT
|  | Total | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
Target Hoisted Tonnes |  | 13950 | 390 | 500 | 500 | 500 | 500 | 500 | 500 | 390 | 500 | 500 | 0 | 0 | 500 | 500 | 390 | 500 | 500 | 500 | 390 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 390 | 500 | 500
Hoisted (6 Level ) | Ore Tonnes | 13950 | 390 | 500 | 500 | 500 | 500 | 500 | 500 | 390 | 500 | 500 | 0 | 0 | 500 | 500 | 390 | 500 | 500 | 500 | 390 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 390 | 500 | 500
| Au_Dil | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 0 | 0 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899
6 Level Broken Inventory | Ore Tonnes | 16240 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 0 | 0 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560 | 560
| Au_Dil | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 0 | 0 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899 | 2.4899

## DD.
DIAMOND DRILLING PLAN
2025-08-01
| UG |  | FY25 Budget | Aug Plan | Variance
| Capitalised | Exploration | 750 | 750 | 0
| Expensed | Exploration | 462 | 462 | 0
| Expensed | Evaluation | 424 | 424 | 0
| TOTAL |  | 1636 | 1636 | 0
| # of Rigs |  | 7 | 7 | 0
| BRK Drilling |  |  |  |  | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| Rig | Cubby | Hole ID | Days Drilling | Total | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
| BRKU3-9BQ_1 | 6_W21 | 6W21_19 | 8 | 80 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  |  | 6W21_21 | 7 | 70 | [8 empty] | PM | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  | 6W23 | 6W23_03 | 1 | 10 | [16 empty] | PM | Moving | Cubby PreP | Cubby PreP | Cubby PreP | Cubby PreP | Cubby PreP | Cubby PreP | Cubby PreP | 10
|  |  | 6W23_01 | 4 | 40 | [26 empty] | PM | 10 | 10 | 10 | 10
| 250 |  | Total | 20 | 200 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 10 | 10 | 10
| BRK U2AW | 6AW9 | 6AW9_EV_02 | 4 | 32 | 8 | 8 | 8 | 8
|  |  | 6AW9_EV_03 | 4 | 32 |  |  |  |  | Moving | Moving | 8 | 8 | 8 | 8
|  | 6AW10 | 6AW10_EV_04 | 3 | 24 | [10 empty] | PM | 8 | 8 | 8
|  | 8W16 | 8W16_EV_01 | 4 | 32 | [14 empty] | 8 | 8 | 8 | 8
|  |  | 8W16_EV_02 | 4 | 32 | [18 empty] | PM | 8 | 8 | 8 | 8
|  |  | 8W16_EV_03 | 4 | 32 | [23 empty] | 8 | 8 | 8 | 8
|  |  | 8W16_EV_04 | 4 | 32 | [27 empty] | 8 | 8 | 8 | 8
| 200 |  | Total | 27 | 216 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| BRKU3_9BQ_2 | 7_E2 | 7E2_45 | 1 | 10 | Moving | Commisioning | Commisioning | 10
|  |  | 7E2_46 | 3 | 30 |  |  |  |  | 10 | 10 | 10
|  |  | 7E2_47 | 6 | 60 | [7 empty] | PM | 10 | 10 | 10 | 10 | 10 | 10
|  |  | 7E2_48 | 6 | 60 | [14 empty] | PM | 10 | 10 | 10 | 10 | 10 | 10
|  |  | 7E2_49 | 3 | 30 | [21 empty] | 10 | 10 | 10
|  |  | 7E2_50 | 5 | 50 | [24 empty] | 10 | 10 | 10 | 10 | 10 | PM | Moving
| 250 |  | Total | 0 | 240 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0
| BRKU3_9BQ_3 | 10_W4 | 10W4_01 | 2 | 20 | [5 empty] | 10 | 10
|  |  | 10W4_02 | 5 | 50 | [7 empty] | 10 | 10 | 10 | 10 | 10
|  |  | 10W4_03 | 6 | 60 | [12 empty] | PM | 10 | 10 | 10 | 10 | 10 | 10
|  |  | 10W4_04 | 5 | 50 | [19 empty] | 10 | 10 | 10 | 10 | 10
|  |  | 10W4_05 | 4 | 40 | [24 empty] | PM | 10 | 10 | 10 | 10
|  |  | 10W4_06 | 2 | 20 | [29 empty] | 10 | 10
| 250 |  | Total | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10
| Cumulative |  |  |  | 896 | 18 | 18 | 18 | 28 | 20 | 30 | 38 | 28 | 28 | 38 | 30 | 38 | 28 | 38 | 28 | 38 | 28 | 28 | 20 | 28 | 28 | 28 | 28 | 28 | 18 | 38 | 28 | 38 | 38 | 28 | 28
| JBC Drilling |  |  |  |  | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| Rig | Cubby | Hole ID | Days Drilling | Total | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
| JBC01 | 1L_W25 | 1L_W25_EV01 | 3 | 26 | 10 | 8 | 8
|  |  | 1L_W25_EV02 | 4 | 34 |  |  |  | PM | 10 | 8 | 8 | 8
|  |  | 1L_W25_EV03 | 4 | 34 | [8 empty] | 10 | 8 | 8 | 8
|  |  | 1L_W25_EV04 | 4 | 34 | [12 empty] | 10 | 8 | 8 | 8 | PM
|  |  | 1L_W25_EV05 | 4 | 34 | [17 empty] | 10 | 8 | 8 | 8
|  |  | 1L_W25_EV06 | 2 | 20 | [21 empty] | 10 | 10
|  |  | 1L_W25_EV07 | 2 | 20 | [23 empty] | 10 | 10
|  |  | 1L_W25_EV08 | 2 | 20 | [25 empty] | 10 | 10
|  |  | 1L_W25_EV09 | 2 | 20 | [27 empty] | 10 | 10
|  |  | 1L_W25_EV10 | 2 | 20 | [29 empty] | 10 | 10
| 250 |  | Total | 29 | 262 | 10 | 8 | 8 | 0 | 10 | 8 | 8 | 8 | 10 | 8 | 8 | 8 | 10 | 8 | 8 | 8 | 0 | 10 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
7 | JBC02 | 4_E15 | 4E_15_5 | 12 | 120 | 10 | 10 | 10 | 10 | 10 | 10 | PM | 10 | 10 | 10 | 10 | 10 | 10
|  |  | 4E_15_7 | 9 | 90 | [13 empty] | Moving | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  |  | 4E_15_6 | 6 | 60 | [23 empty] | PM | 10 | 10 | 10 | 10 | 10 | 10 | Moving
|  |  |  | 0 | 0
|  |  |  | 0 | 0
| 210 |  | Total | 27 | 270 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0
| JBC03 | 5W11 | 5W11_35 | 2 | 16 | 8 | 8
|  | 5W12 | 5W12_36 | 2 | 16 |  |  | Moving | 8 | 8
|  |  | 5W12_37 | 3 | 24 | [5 empty] | 8 | 8 | 8
|  |  | 5W12_38 | 2 | 16 | [8 empty] | 8 | 8
|  | 5W13 | 5W13_39 | 2 | 16 | [10 empty] | PM | 8 | 8
|  |  | 5W13_40 | 3 | 24 | [13 empty] | 8 | 8 | 8
|  |  | 5W13_41 | 2 | 16 | [16 empty] | 8 | 8
|  | 5W14 | 5W14_42 | 2 | 16 | [18 empty] | PM | Moving | 8 | 8
|  |  | 5W14_43 | 3 | 24 | [22 empty] | 8 | 8 | 8
|  |  | 5W14_44 | 2 | 16 | [25 empty] | 8 | 8
|  | 5W18 | 5W18_46 | 2 | 24 | [27 empty] | PM | 8 | 8 | 8
| 200 |  | Total | 18 | 208 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8
| Cumulative |  |  |  | 740 | 28 | 26 | 18 | 18 | 28 | 26 | 16 | 26 | 28 | 26 | 18 | 26 | 28 | 16 | 26 | 26 | 18 | 28 | 18 | 18 | 26 | 28 | 28 | 18 | 28 | 28 | 28 | 20 | 28 | 28 | 18
0
| Tandamanzi Drilling |  |  |  |  | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
| Rig | Cubby | Hole ID | Days Drilling | Total | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30
| TMD06 | Surface |  |  | 0
0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TMD07 | Surface |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  | Total | 0 | 0 | Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0
| Total |  |  |  | 0 | Thu: 0; Fri: 0; Sat: 0; Sun: 0; Mon: 0; Tue: 0; Wed: 0
| Capitalised | Surface | Exploration |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Capitalised | Underground | Exploration |  | 750 | 10 | 10 | 10 | 20 | 20 | 30 | 20 | 20 | 30 | 30 | 30 | 30 | 20 | 20 | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 20 | 20 | 30 | 30 | 30 | 30 | 20 | 10
| Expensed | Underground | Exploration |  | 462 | 20 | 18 | 18 | 10 | 20 | 18 | 18 | 18 | 10 | 18 | 18 | 18 | 20 | 18 | 18 | 18 | 0 | 10 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 20 | 10 | 20 | 20 | 20 | 20
| Total | Underground | Exploration |  | 1212 | 30 | 28 | 28 | 30 | 40 | 48 | 38 | 38 | 40 | 48 | 48 | 48 | 40 | 38 | 38 | 48 | 30 | 40 | 38 | 38 | 38 | 40 | 40 | 30 | 30 | 50 | 40 | 50 | 50 | 40 | 30
| Expensed | Underground | Evaluation |  | 424 | 16 | 16 | 8 | 16 | 8 | 8 | 16 | 16 | 16 | 16 | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 16 | 16 | 16
| Total | Underground | Drilling |  | 424 | 16 | 16 | 8 | 16 | 8 | 8 | 16 | 16 | 16 | 16 | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 16 | 16 | 16
| GRAND TOTAL |  |  |  | 1636 | 46 | 44 | 36 | 46 | 48 | 56 | 54 | 54 | 56 | 64 | 48 | 64 | 56 | 54 | 54 | 64 | 46 | 56 | 38 | 46 | 54 | 56 | 56 | 46 | 46 | 66 | 56 | 58 | 66 | 56 | 46

## Weekly
| BRECKRIDGE INVESTMENTS | [5 empty] | KEY |  |  | GRADE LEGEND |  |  |  |  | Reason if Actual is RED
| Pickstone Underground Mine | [5 empty] | Above Budget |  |  | < 0.60 Waste |  |  |  |  | Loco Breakdown - LcBD
| Weekly Report | [5 empty] | Below Budget |  |  | 0.60 - 1.60 Low Grade |  |  |  |  | Flooding - FLD
[10 empty] | 1.60 - 2.00 Medium Grade |  |  |  |  | Awaiting Assay Results - AAR
| Month: | 2025-03-01 | [7 empty] | > 2.00 High Grade |  |  |  |  | No Sample - NS
| Day: | 6 | [12 empty] | Reduced Draw - RD; Blockages - BLKG
13 | PRIORITY | BOX ID |  |  | MTD Blasting | MTD Blasting Var | MTD Tramming | MTD Tramming Var | Stope Project to date | Stope Project to date Var | Block Model | Block Model Remaining | COMMENTS
|  | 1L W24 STOPE | Tonnes | Budget (t) | 0 |  | 0 |  | 0 |  | 0 |  | Production drilling suspended to allow for development material handling and evaluation drilling to firm up on grade and tonnage
|  |  |  | Actual (t) | 0 | 0% | 0 | 0% | 0 | 0% | 659 | 0%
|  |  | Grade | Budget (g/t) | 0 |  | 0 |  | 0 |  | 0 |  | Evaluation drilling to firm up on grade
|  |  |  | Actual (g/t) | 0 | 0% | 0 | 0% | 0 | 0% | 0.62186 | 0%
|  |  | Gold | Budget (kg) | 0 |  | 0 |  | 0 |  | 0
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0% | 0 | 0% | 0.40981 | 0%
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 1 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 30 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 15 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 3L_W23A STOPE | Tonnes | Budget (t) | 420 |  | 420 |  | 0 |  | 9411 |  | Trammed tonnage accounted for from stopes below
|  |  |  | Actual (t) | 717 | 70.71% | 0 | -100% | 0 | 0% | 1564 | 7847
|  |  | Grade | Budget (g/t) | 1.986 |  | 1.986 |  | #DIV/0! |  | 1.61 |  | Stope preparation and grade will improve as we open up
|  |  |  | Actual (g/t) | 2.5612 | 28.96% | 0 | -100% | 0 | 0% | 1.9371 | 20.32%
|  |  | Gold | Budget (kg) | 0.83411 |  | 0.83411 |  | 0 |  | 15.1517
|  |  |  | Actual (kg) | 1.8364 | 120.2% | 0 | -100% | 0 | 0% | 3.0296 | 12.1221
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 2.4 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 35 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 7 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 4L_W23A STOPE | Tonnes | Budget (t) | 0 |  | 0 |  | 20825 |  | 5.14
|  |  |  | Actual (t) | 0 | 0% | 0 | 0% | 25876 | 24.25% | 91 | 1670%
|  |  | Grade | Budget (g/t) | 0 |  | 0 |  | 2.6618 |  | 35 |  | Some of the slyping hole intersected the chlorite schist
|  |  |  | Actual (g/t) | 0 | 0% | 0 | 0% | 2.7902 | 4.823% | 3.43 | -90.2%
|  |  | Gold | Budget (kg) | 0 |  | 0 |  | 58.1067 |  | 0.1799
|  |  |  | Actual (kg) | 0 | 0% | 0 | 0% | 72.2002 | 24.25% | 0.31213 | 73.5% |  |  |  | 2.4
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 2.4 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 40 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 7 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 4L_W23B_STOPE | Tonnes | Budget (t) | 420 |  | 420 |  | 0 |  | 0.0855
|  |  |  | Actual (t) | 432 | 2.857% | 0 | -100% | 432 | 0% | 91 | 106333%
|  |  | Grade | Budget (g/t) | 1.9463 |  | 1.9463 |  | 1.9463 |  | 0
|  |  |  | Actual (g/t) | 3.0038 | 54.34% | 0 | -100% | 0 | -100% | 3.43 | 0%
|  |  | Gold | Budget (kg) | 0.81743 |  | 0.81743 |  | 0 |  | 0
|  |  |  | Actual (kg) | 1.2977 | 58.75% | 2.1274 | 160.3% | 0 | 0% | 0.31213 | 0%
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 8 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 40 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 15 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 4L_W26 STOPE | Tonnes | Budget (t) | 0 |  | 210 | 109 | 3045 | 3045 | 100 | 112 | Fairly new stope and stoping in the esatern direction to the orepasss
|  |  |  | Actual (t) | 0 | 0% | 0 | -100% | 2563 | -15.83% | 92 | 5300%
|  |  | Grade | Budget (g/t) | 0 |  | 1.986 | 322% | 1.7356 |  | 0 | 349% |  | 2.6618
|  |  |  | Actual (g/t) | 0 | 0% | 0 | -100% | 1.1345 | -34.63% | 4.43 | 338%
|  |  | Gold | Budget (kg) | 0 |  | 0.41706 | 35.1% | 5.2849 | 0% | 0 | 39.09%
|  |  |  | Actual (kg) | 0 | 0% | 0 | -100% | 2.9078 | -44.98% | 0.40756 | 17.91%
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 2.4 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 15 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 15 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) | 15 | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 5L_W7 STOPE | Tonnes | Budget (t) | 0 |  | 420 | 2.84 | 10080 | 2.84 | 2.84 | 2.84
|  |  |  | Actual (t) | 0 | 0% | 337 | -19.76% | 10182 | 1.012% | 91 | 5200%
|  |  | Grade | Budget (g/t) | 0 |  | 1.4564 | 0% | 1.948 | 2.424% | 0 | 8.151%
|  |  |  | Actual (g/t) | 0 | 0% | 0.83398 | -42.74% | 1.8814 | -3.422% | 3.43 | 238%
|  |  | Gold | Budget (kg) | 0 |  | 0.61168 | 0% | 19.6363 | 0.006884% | 0 | 0.02315%
|  |  |  | Actual (kg) | 0 | 0% | 0.28105 | -54.05% | 19.1562 | -3.463e-05% | 0.31213 | 12.38%
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 2.8 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 15 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 16 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 5L_W8 STOPE | Tonnes | Budget (t) | 420 |  | 210 | 0.07595 | 7175 | 0.07595 | 0.07595 | 0.07595
|  |  |  | Actual (t) | 450 | 7.143% | 171 | -18.57% | 4610.5 | 6900% | 92 | 5300%
|  |  | Grade | Budget (g/t) | 1.7477 |  | 3.1379 | 0% | 2.4764 | 0% | 0 | 0%
|  |  |  | Actual (g/t) | 1.9964 | 14.23% | 4.2834 | 36.51% | 2.4676 | 500% | 4.43 | 338%
|  |  | Gold | Budget (kg) | 0.73402 |  | 0.65895 | 0% | 17.7683 | 0% | 0 | 0%
|  |  |  | Actual (kg) | 0.89837 | 22.39% | 0.73246 | 11.16% | 11.3769 | 34.5% | 0.40756 | 17.91%
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 3 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 20 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 15 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 6L_E1 STOPE | Tonnes | Budget (t) | 210 |  | 0 | 0 | 6440 | 0 | 0 | 0
|  |  |  | Actual (t) | 320 | 52.38% | 0 | 0% | 7103 | 6900% | 92 | 5300%
|  |  | Grade | Budget (g/t) | 3.1379 |  | 0 | 0% | 2.9665 | 0% | 0 | 0% | Grade affected by catwalk mined during stope preparation. Future stopes will have two travel ways.
|  |  |  | Actual (g/t) | 3.5495 | 13.12% | 0 | 0% | 3.3553 | 500% | 4.43 | 338%
|  |  | Gold | Budget (kg) | 0.65895 |  | 0 | 0% | 19.1044 | 0% | 0 | 0%
|  |  |  | Actual (kg) | 1.1358 | 72.37% | 0 | 0% | 23.8329 | 34.5% | 0.40756 | 17.91%
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 4.2 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 30 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 25 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 6L_W1 STOPE | Tonnes | Budget (t) | 0 |  | 840 | 0 | 840 | 0 | 0 | 0
|  |  |  | Actual (t) | 0 | 0% | 1184.5 | 41.01% | 1184.5 | 7000% | 93 | 5400%
|  |  | Grade | Budget (g/t) | 0 |  | 2.5421 | 0% | 2.5421 | 0% | 0 | 0% | Internal waste in the W1 ore shoot
|  |  |  | Actual (g/t) | 0 | 0% | 3.6779 | 44.68% | 3.6779 | 600% | 5.43 | 438%
|  |  | Gold | Budget (kg) | 0 |  | 2.1353 | 0% | 2.1353 | 0% | 0 | 0%
|  |  |  | Actual (kg) | 0 | 0% | 4.3564 | 104% | 4.3564 | 42% | 0.50499 | 23.65%
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 3.6 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 30 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 25 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 6L_W2 STOPE | Tonnes | Budget (t) | 840 |  | 630 | 0 | 630 | 0 | 0 | 0
|  |  |  | Actual (t) | 1049 | 24.88% | 591 | -6.19% | 591 | 7000% | 93 | 5400%
|  |  | Grade | Budget (g/t) | 2.5421 |  | 2.3832 | 0% | 2.3832 | 0% | 0 | 0% | Close to plan
|  |  |  | Actual (g/t) | 4.6257 | 81.97% | 3.4994 | 46.84% | 3.4994 | 600% | 5.43 | 438%
|  |  | Gold | Budget (kg) | 2.1353 |  | 1.5014 | 0% | 1.5014 | 0% | 0 | 0%
|  |  |  | Actual (kg) | 4.8524 | 127.2% | 2.0681 | 37.75% | 2.0681 | 42% | 0.50499 | 23.65%
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 4 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 40 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 25 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 6L_W8 STOPE | Tonnes | Budget (t) | 630 |  | 0 | 0 | 4760 | 0 | 0 | 0
|  |  |  | Actual (t) | 523 | -16.98% | 0 | 0% | 1157 | 7100% | 94 | 5500%
|  |  | Grade | Budget (g/t) | 2.3832 |  | 0 | 0% | 2.2822 | 0% | 0 | 0% | Reef narrows to the east and shaping cone.
|  |  |  | Actual (g/t) | 3.4429 | 44.47% | 0 | 0% | 2.5835 | 700% | 6.43 | 538%
|  |  | Gold | Budget (kg) | 1.5014 |  | 0 | 0% | 10.8633 | 0% | 0 | 0%
|  |  |  | Actual (kg) | 1.8007 | 19.93% | 0 | 0% | 2.9891 | 49.7% | 0.60442 | 29.59%
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 4.8 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 30 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 25 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 6L_W9 STOPE | Tonnes | Budget (t) | 0 |  | 630 | 0 | 7070 | 0 | 0 | 0
|  |  |  | Actual (t) | 0 | 0% | 64.5 | -89.76% | 10041.6 | 7100% | 94 | 5500%
|  |  | Grade | Budget (g/t) | 0 |  | 2.7804 | 0% | 2.5218 | 0% | 0 | 0%
|  |  |  | Actual (g/t) | 0 | 0% | 0.80233 | -71.14% | 2.5984 | 700% | 6.43 | 538%
|  |  | Gold | Budget (kg) | 0 |  | 1.7516 | 0% | 17.8289 | 0% | 0 | 0%
|  |  |  | Actual (kg) | 0 | 0% | 0.05175 | -97.05% | 26.0923 | 49.7% | 0.60442 | 29.59%
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 4.8 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 25 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 18 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0
|  | 6L_W10_STOPE | Tonnes | Budget (t) | 630 |  | 210 | 0 | 1190 | 0 | 0 | 0 | Moving old muck in the stope to open up for stoping. Suspended traming to allow mining of a raise to isolate the old muck.
|  |  |  | Actual (t) | 527 | -16.35% | 0 | -100% | 660 | 7200% | 95 | 5600%
|  |  | Grade | Budget (g/t) | 2.7804 |  | 1.986 | 0% | 2.6152 | 0% | 0 | 0%
|  |  |  | Actual (g/t) | 1.6287 | -41.42% | 0 | 760% | 1.2472 | 800% | 7.43 | 638%
|  |  | Gold | Budget (kg) | 1.7516 |  | 0.41706 | 0% | 3.1121 | 0% | 0 | 0%
|  |  |  | Actual (kg) | 0.85834 | -51% | 0 | -100% | 0.82315 | 57.6% | 0.70585 | 35.73%
|  |  | Reef Width | Budget (m)
|  |  |  | Actual (m) | 4.2 | 0%
|  |  | Length | Budget (m)
|  |  |  | Actual (m) | 15 | 0%
|  |  | Height | Budget (m)
|  |  |  | Actual (m) | 25 | 0%
|  |  | Sampling | Budget (#)
|  |  |  | Actual (#) |  | 0%
|  |  | Commercial | Budget ($/oz)
|  |  |  | Actual ($/oz) |  | 0

## Stope History
|  |  |  | Block Model |  | Evaluation | Plan MTD | Actual | [7 empty] | Plan | Remaining | Grade performance
STOPE ID | Metric | UOM | Block Model | LOM Plan | Evaluation | ST Plan | Stoping | Stoping | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | Mar-25 Plan (MTD) | Mar-25 Actual | 2025-03-01 |  | % | Comments | Width (m)
TOTAL | Actual (t) | (t) | 186387.8505 | 199435 | 0 | 32876 |  | 71959.8 | 4606 | 5875.2 | 12678.4 | 23871.2 | 24929 |  |  | 28910 | 127475.2
TOTAL | Actual (g/t) | (g/t) | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0%
TOTAL | Actual (kg) | (kg) | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1L_W23 STOPE | Budget (t) | [5 empty] | 0
1L_W23 STOPE | Actual (t) | (t) | 0 | 0 |  |  |  | 0 | [5 empty] | 560 | 659 | 1085 | 0 |  |  | 1.3
1L_W23 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 0 | [7 empty] | 1.0723 | 1.8271 | 0
1L_W23 STOPE | Actual (g/t) | (g/t) | 0 | 0 |  | 0 |  | 0 | [5 empty] | 2.1562 | 0.62186 | 1.8271 | 0 | 0% | New stope accessed from the Adit.
1L_W23 STOPE | Budget (kg) | [5 empty] | 0
1L_W23 STOPE | Actual (kg) | (kg) | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.2075 | 0.40981 | 1.9824
3L_W23 STOPE | Budget (t) | [5 empty] | 1960 | [5 empty] | 1960
3L_W23 STOPE | Actual (t) | (t) | 8795.3271 | 9411 |  |  |  | 1564 |  |  |  |  | 1564 | 210 | 0 | 1260 | 7847 |  |  | 5
3L_W23 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 2.85 | [5 empty] | 2.85 |  | 0 | 3.0584
3L_W23 STOPE | Actual (g/t) | (g/t) | 2.0267 | 1.61 |  | 2.85 |  | 1.9371 |  |  |  |  | 1.9371 | 3.85 | 0 | 3.0584 | 1.61 | 157.9% | Directly above 4L_W23. Stoping commenced Feb.
3L_W23 STOPE | Budget (kg) | [5 empty] | 5.586 | [5 empty] | 5.586
3L_W23 STOPE | Actual (kg) | (kg) | 17.8255 | 15.1517 |  |  |  | 3.0296 | 0 | 0 | 0 | 0 | 3.0296 | 0.8085 | 0 | 3.8536 | 12.1221
3L_W24 STOPE | Budget (t) | [5 empty] | 980 | [5 empty] | 980
3L_W24 STOPE | Actual (t) | (t) | 6351.4019 | 6796 |  |  |  | 0 |  |  |  |  | 0
3L_W24 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 1.81 | [5 empty] | 1.81
3L_W24 STOPE | Actual (g/t) | (g/t) | 1.8756 | 1.49 |  | 0 |  | 0 |  |  |  |  | 0 |  |  |  |  | 0%
3L_W24 STOPE | Budget (kg) | [5 empty] | 1.7738 | [5 empty] | 1.7738
3L_W24 STOPE | Actual (kg) | (kg) | 11.913 | 10.126 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
4L_W23A STOPE | Budget (t) | [5 empty] | 20825 |  | 2100 | 4200 | 5075 | 6510 | 2940
4L_W23A STOPE | Actual (t) | (t) | 8264.486 | 8843 |  | 28536 |  | 25876 | 3352 | 4385 | 6166 | 6179 | 5794 | 1610 | 1410 | 2660 | -17033 |  |  | 12
4L_W23A STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 2.6618 |  | 1.64 | 3.17 | 2.44 | 2.44 | 3.54 |  | 2.025 | 2.8121
4L_W23A STOPE | Actual (g/t) | (g/t) | 2.3162 | 1.84 |  |  |  | 2.7902 | 3.2529 | 2.5514 | 2.0825 | 3.2602 | 2.9553 | 3.3091 | 2.025 | 2.8121 | 1.84 | 100.8% | Wider reef (12m vs 4m planned). Grade performing above LOM plan.
4L_W23A STOPE | Budget (kg) | [5 empty] | 55.433 |  | 3.444 | 13.314 | 12.383 | 15.8844 | 10.4076
4L_W23A STOPE | Actual (kg) | (kg) | 19.1425 | 16.2711 |  | 72.2002 |  | 72.2002 | 10.9037 | 11.1878 | 12.8408 | 20.1447 | 17.1231 | 5.3277 | 2.5126 | 7.4803 | -55.9291
4L_W23B STOPE | Budget (t) | [5 empty] | 0
4L_W23B STOPE | Actual (t) | (t) | 8264.486 | 8843 |  | 4340 |  | 0 | [5 empty] | 2240 | 2218 | 4340 | 8843
4L_W23B STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 0 | [7 empty] | 2.3986 | 3.0584
4L_W23B STOPE | Actual (g/t) | (g/t) | 2.3162 | 1.84 |  | 0 |  | 0 | [5 empty] | 3.6094 | 2.3986 | 3.0584 | 1.84 | 0% | New stope above 4L_W23A.
4L_W23B STOPE | Budget (kg) | [5 empty] | 0
4L_W23B STOPE | Actual (kg) | (kg) | 19.1425 | 16.2711 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8.085 | 4.6816 | 13.2735 | 16.2711
4L_W26 STOPE | Budget (t) | [5 empty] | 3045 |  |  |  |  | 1085 | 1960
4L_W26 STOPE | Actual (t) | (t) | 2378.5047 | 2545 |  |  |  | 2563 |  |  |  | 1458 | 1105 | 560 | 518 | 1085 | -18 |  |  | 2.4
4L_W26 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 1.5986 |  |  |  |  | 2.12 | 1.31 | 518 | 1.2823 | 1.6841
4L_W26 STOPE | Actual (g/t) | (g/t) | 0.50353 | 0.4 |  | 1.7708 |  | 1.1345 |  |  |  | 1.2119 | 1.0325 | 1.9875 | 1.2823 | 1.6841 | 0.4 | 148.4% | Block evaluation projecting higher grade compared to block model.
4L_W26 STOPE | Budget (kg) | [5 empty] | 4.8678 |  |  |  |  | 2.3002 | 2.5676
4L_W26 STOPE | Actual (kg) | (kg) | 1.1976 | 1.018 |  |  |  | 2.9078 | 0 | 0 | 0 | 1.767 | 1.1409 | 1.113 | 0.58452 | 1.8273 | -1.8898
5L_W4 STOPE | Budget (t) | [5 empty] | 6300 |  | 2100 | 2100 | 1015 | 1085
5L_W4 STOPE | Actual (t) | (t) | 0 | 0 |  |  |  | 4497.2 | 1254 | 1490.2 | 999 | 754 |  |  | 518 |  | -4497.2 |  |  | 2.5
5L_W4 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 1.8967 |  | 1.66 | 2.17 | 1.86 | 1.86 |  |  | 83.9509
5L_W4 STOPE | Actual (g/t) | (g/t) | 0 | 0 |  | 1.907 |  | 1.9401 | 2.8425 | 1.8793 | 2.0098 | 0.46723 |  |  | 0 |  | 0 | 0% | Stope was not on LOMP. Reef terminated is now out of plan. (8.7kg gained).
5L_W4 STOPE | Budget (kg) | [5 empty] | 11.949 |  | 3.486 | 4.557 | 1.8879 | 2.0181
5L_W4 STOPE | Actual (kg) | (kg) | 0 | 0 |  |  |  | 8.7252 | 3.5645 | 2.8006 | 2.0078 | 0.35229 | 0 |  | 0 |  | -8.7252
5L_W7 STOPE | Budget (t) | [5 empty] | 10080 |  |  |  | 4060 | 4060 | 1960
5L_W7 STOPE | Actual (t) | (t) | 2806.5421 | 3003 |  |  |  | 9845 |  |  | 2601 | 4555 | 2689 | 1120 | 1530 | 2170 | -6842 |  |  | 3
5L_W7 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 1.8874 |  |  |  | 1.86 | 2.01 | 1.69 | 1530 | 1.4162 | 1.69
5L_W7 STOPE | Actual (g/t) | (g/t) | 0.66718 | 0.53 |  | 1.883 |  | 1.9172 |  |  | 1.7308 | 1.8785 | 2.1632 | 1.9944 | 1.4162 | 1.69 | 0.53 | 88.15% | Block evaluation projecting higher grade compared to block model. Shrinkage stoping.
5L_W7 STOPE | Budget (kg) | [5 empty] | 19.0246 |  |  |  | 7.5516 | 8.1606 | 3.3124
5L_W7 STOPE | Actual (kg) | (kg) | 1.8725 | 1.5916 |  |  |  | 18.8752 | 0 | 0 | 4.5018 | 8.5566 | 5.8168 | 2.2338 | 1.9068 | 3.6673 | -17.2836
5L_W8 STOPE | Budget (t) | [5 empty] | 7175 |  |  |  | 0 | 3255 | 3920
5L_W8 STOPE | Actual (t) | (t) | 4451.4019 | 4763 |  |  |  | 4439.5 |  |  | 227 | 2609.5 | 1603 | 70 | 201 | 1120 | 323.5
5L_W8 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 2.3846 |  |  |  | 0 | 1.8 | 2.87 | 201 | 1.1834 | 1.6047
5L_W8 STOPE | Actual (g/t) | (g/t) | 4.1415 | 3.29 |  | 2.0943 |  | 2.3977 |  |  | 3.1389 | 2.4268 | 2.2452 | 2.02 | 1.1834 | 1.6047 | 3.29 | 66.93% | Stope is in poor ground. Grade affected by dilution. | 5.5
5L_W8 STOPE | Budget (kg) | [5 empty] | 17.1094 |  |  |  | 0 | 5.859 | 11.2504
5L_W8 STOPE | Actual (kg) | (kg) | 18.4356 | 15.6703 |  |  |  | 10.6444 | 0 | 0 | 0.71254 | 6.3328 | 3.5991 | 0.1414 | 0.20932 | 1.7972 | 5.0259
6L_E1 STOPE | Budget (t) | [5 empty] | 6440 |  |  |  | 1400 | 2100 | 2940
6L_E1 STOPE | Actual (t) | (t) | 40908.4112 | 43772 |  |  |  | 7103 |  |  | 731.8 | 2028.2 | 4343 | 1120 | 1663.4 | 2170 | 36669 |  |  | 3.6
6L_E1 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 2.9665 |  |  |  | 2.12 | 3.162 | 3.23 |  | 2.8809 | 3.0902
6L_E1 STOPE | Actual (g/t) | (g/t) | 3.5373 | 2.81 |  | 3.0962 |  | 3.3553 |  |  | 1.8545 | 3.1834 | 3.6885 | 3.89 | 2.8809 | 3.0902 | 2.81 | 92.1% | Wide reef (8m versus th eplanned 3.6m). High grade stope.
6L_E1 STOPE | Budget (kg) | [5 empty] | 19.1044 |  |  |  | 2.968 | 6.6402 | 9.4962
6L_E1 STOPE | Actual (kg) | (kg) | 144.7051 | 122.9993 |  |  |  | 23.8329 | 0 | 0 | 1.3571 | 6.4565 | 16.0192 | 4.3568 | 4.2171 | 6.7057 | 99.1665
6L_W1 STOPE | Budget (t) | [5 empty] | 0
6L_W1 STOPE | Actual (t) | (t) | 33295.3271 | 35626 |  |  |  | 0 | [5 empty] | 1680 | 1439.1 | 3255 | 35626 |  |  | 4
6L_W1 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 0 | [7 empty] | 2.0656 | 3.0902
6L_W1 STOPE | Actual (g/t) | (g/t) | 3.5373 | 3.54 |  | 0 |  | 0 | [5 empty] | 3.89 | 2.0656 | 3.0902 | 3.54 | 0% | Stope was not on LOMP. Block evaluation projecting higher grade compared to BM.
6L_W1 STOPE | Budget (kg) | [5 empty] | 0
6L_W1 STOPE | Actual (kg) | (kg) | 117.7754 | 100.1091 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6.5352 | 2.6158 | 10.0586 | 100.1091
6L_W2 STOPE | Budget (t) | [5 empty] | 0
6L_W2 STOPE | Actual (t) | (t) | 27456.0748 | 29378 |  |  |  | 0 | [5 empty] | 1120 | 979.2 | 2170 | 29378
6L_W2 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 0 | [7 empty] | 3.0043 | 2.3117
6L_W2 STOPE | Actual (g/t) | (g/t) | 3.5373 | 2.81 |  | 0 |  | 0 | [5 empty] | 2.91 | 3.0043 | 2.3117 | 2.81 | 0% | Stope was not on LOMP. Block evaluation projecting higher grade compared to BM.
6L_W2 STOPE | Budget (kg) | [5 empty] | 0
6L_W2 STOPE | Actual (kg) | (kg) | 97.1202 | 82.5522 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.2592 | 2.5888 | 5.0164 | 82.5522
6L_W3 STOPE | Budget (t) | [5 empty] | 980 | [5 empty] | 980
6L_W3 STOPE | Actual (t) | (t) | 27456.0748 | 29378 |  |  |  | 2329 |  |  |  |  | 2329 |  | 2330 |  | 27049 |  |  | 4
6L_W3 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 2.91 | [5 empty] | 2.91 |  | 3.91
6L_W3 STOPE | Actual (g/t) | (g/t) | 2.9205 | 2.32 |  | 2.91 |  | 4.1763 |  |  |  |  | 4.1763 |  | 5.1763 |  | 2.32 | 0%
6L_W3 STOPE | Budget (kg) | [5 empty] | 2.8518 | [5 empty] | 2.8518
6L_W3 STOPE | Actual (kg) | (kg) | 80.1847 | 68.157 |  |  |  | 9.7265 | 0 | 0 | 0 | 0 | 9.7265 |  | 12.0607 |  | 58.4305
6L_E5 STOPE | Budget (t) | [5 empty] | 1750 |  |  |  | 700 | 1050
6L_E5 STOPE | Actual (t) | (t) | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 |  |  |  |  | 0
6L_E5 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 1.45 |  |  |  | 2.05 | 1.05
6L_E5 STOPE | Actual (g/t) | (g/t) | 0 | 0 |  | 0 |  | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0%
6L_E5 STOPE | Budget (kg) | [5 empty] | 2.5375 |  |  |  | 1.435 | 1.1025
6L_E5 STOPE | Actual (kg) | (kg) | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
6L_W6 STOPE | Budget (t) | [5 empty] | 1050 |  |  |  |  | 1050
6L_W6 STOPE | Actual (t) | (t) | 3085.0467 | 3301 |  |  |  | 1949 |  |  |  | 1949 |  |  |  |  | 1352
6L_W6 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 2.7285 |  |  |  |  | 2.7285
6L_W6 STOPE | Actual (g/t) | (g/t) | 1.6616 | 1.32 |  | 2.7285 |  | 2.7856 |  |  |  | 2.7856 |  |  |  |  | 1.32 | 0%
6L_W6 STOPE | Budget (kg) | [5 empty] | 2.8649 |  |  |  |  | 2.8649
6L_W6 STOPE | Actual (kg) | (kg) | 5.1263 | 4.3573 |  |  |  | 5.429 | 0 | 0 | 0 | 5.429 | 0 |  | 0 |  | -1.0717
6L_W8 STOPE | Budget (t) | [5 empty] | 4760 |  |  |  | 700 | 2100 | 1960
6L_W8 STOPE | Actual (t) | (t) | 2528.972 | 2706 |  |  |  | 1157 |  |  | 0 | 804 | 353 | 1120 | 90 | 2170 | 1549 |  |  | 3.6
6L_W8 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 2.2822 |  |  |  | 1.66 | 2.193 | 2.6 |  | 0.92489 | 2.2561
6L_W8 STOPE | Actual (g/t) | (g/t) | 1.9764 | 1.57 |  | 2.3172 |  | 2.5835 |  |  | 0 | 2.6024 | 2.5406 | 2.84 | 0.92489 | 2.2561 | 1.57 | 87.33% | Block evaluation projecting higher grade compared to block model.
6L_W8 STOPE | Budget (kg) | [5 empty] | 10.8633 |  |  |  | 1.162 | 4.6053 | 5.096
6L_W8 STOPE | Actual (kg) | (kg) | 4.9981 | 4.2484 |  |  |  | 2.9891 | 0 | 0 | 0 | 2.0923 | 0.89682 | 3.1808 | - | 4.8957 | 1.2593
6L_W9 STOPE | Budget (t) | [5 empty] | 6440 |  |  |  | 1400 | 2100 | 2940
6L_W9 STOPE | Actual (t) | (t) | 4383.1776 | 4690 |  |  |  | 9977.1 |  |  | 1953.6 | 3534.5 | 4489 | 2240 | 2453.8 | 4340 | -5287.1
6L_W9 STOPE | Budget (g/t) | Budget (g/t) | 3.3988 | 2.7 |  | 2.61 | 2.4965 |  |  |  | 2.18 | 2.6605 | 2.53 | 2.53 | 2.1526 | 2.0098 | 2.7 | 0% | Wider reef (average 4m vs plan on 2m). | 3.8
6L_W9 STOPE | Actual (g/t) | Budget (g/t) | [5 empty] | 2.61 |  |  | 2.3305 | 2.2163 | 3.0417 |  | 2.1526 | 2.0098
6L_W9 STOPE | Budget (kg) | [5 empty] | 16.0772 |  |  |  | 3.052 | 5.587 | 7.4382
6L_W9 STOPE | Actual (kg) | (kg) | 14.8976 | 12.663 |  |  |  | 26.0406 | 0 | 0 | 4.5529 | 7.8335 | 13.6542 | 5.6672 | 4.6481 | 8.7226 | -13.3776
6L_W10 STOPE | Budget (t) | [5 empty] | 980 | [5 empty] | 980
6L_W10 STOPE | Actual (t) | (t) | 0 | 0 |  |  |  | 660 |  |  | 0 |  | 660 | 560 | 0 | 1085 | -660 |  |  | 6
6L_W10 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 2.75 |  |  |  | 1.79 |  | 2.75 |  | 0 | 1.7238
6L_W10 STOPE | Actual (g/t) | (g/t) | 0 | 0 |  | 2.75 |  | 1.2472 |  |  | 0 |  | 1.2472 | 2.17 | 0 | 1.7238 | 0 | 138.2% | Stope was not on LOMP (partially mined out).
6L_W10 STOPE | Budget (kg) | [5 empty] | 2.695 | [5 empty] | 2.695
6L_W10 STOPE | Actual (kg) | (kg) | 0 | 0 |  |  |  | 0.82315 | 0 | 0 | 0 | 0 | 0.82315 | 1.2152 | 0 | 1.8704 | -0.82315
6L_W13 STOPE | Budget (t) | [5 empty] | 1400 |  |  |  | 1400
6L_W13 STOPE | Actual (t) | (t) | 2013.0841 | 2154 |  |  |  | 0 |  |  | 0 |  |  |  | 0
6L_W13 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 1.85 |  |  |  | 1.85 |  |  |  | 0
6L_W13 STOPE | Actual (g/t) | (g/t) | 4.5695 | 3.63 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0%
6L_W13 STOPE | Budget (kg) | [5 empty] | 2.59 |  |  |  | 2.59
6L_W13 STOPE | Actual (kg) | (kg) | 9.1988 | 7.819 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
6L_W14 STOPE | Budget (t) | [5 empty] | 700 |  |  |  | 700 | 0 | 0
6L_W14 STOPE | Actual (t) | (t) | 3949.5327 | 4226 |  |  |  | 0 |  |  | 0 | 0 | 0 |  | 0
6L_W14 STOPE | Budget (g/t) | Budget (g/t) |  |  |  |  | 1.79 |  |  |  | 1.79 | 0 | 0 |  | 0
6L_W14 STOPE | Actual (g/t) | (g/t) | 3.6128 | 2.87 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0% |  | 2.7
6L_W14 STOPE | Budget (kg) | [5 empty] | 1.253 |  |  |  | 1.253 | 0 | 0
6L_W14 STOPE | Actual (kg) | (kg) | 14.269 | 12.1286 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0

## KPIs (2) (hidden)
BRECKRIDGE INVESTMENTS
Pickstone Underground Mine
Daily KPIs
Month: | 2025-03-01
Day: | 6
|  |  | Daily |  |  |  | MTD
1 | Development | UoM | Actual | Plan | Var | Var % | Actual | Plan | Var | Var %
1.1 | CAPEX | m | 3.8 | 4.9 | -1.1 | -22.45% | 25.1 | 19.3 | 5.8 | 30.05%
1.2 | ROM | m | 17.3 | 33.9 | -16.6 | -48.97% | 155.2 | 165 | -9.8 | -5.939%
| Total | m | 21.1 | 38.8 | -17.7 | -45.62% | 180.3 | 184.3 | -4 | -2.17%
2 | Equipping
2.1 | CAPEX | m
2.2 | Services | m
3 | Tonnes
3.1 | Generation | t | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
3.2 | Tramming | t | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
3.3 | Hoisting | t | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
4 | Grade
3.1 | Generation | g/t |  |  | #VALUE! | 0% |  |  | #VALUE! | 0%
3.2 | Tramming | g/t |  |  | #VALUE! | 0% |  |  | #VALUE! | 0%
3.3 | Hoisting | g/t |  |  | #VALUE! | 0% |  |  | #VALUE! | 0%
5 | Gold
3.1 | Generation | kg | 2.7777 | 2.0533 | 0.72435 | 35.28% | 16.7046 | 12.3198 | 4.3848 | 35.59%
3.2 | Tramming | kg | 0 | 2.0533 | -2.0533 | -100% | 13.0078 | 12.0057 | 1.0022 | 8.348%
3.3 | Hoisting | kg | 0 | 1.9039 | -1.9039 | -100% | 9.4905 | 11.1496 | -1.6591 | -14.88%
|  | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
CAPEX Development
| Actual | 2025-08-01: 5.7; 2025-08-02: 4.9; 2025-08-03: 2.9; 2025-08-04: 3.8; 2025-08-05: 4; 2025-08-06: 3.8
| Cum. Actual | 2025-08-01: 5.7; 2025-08-02: 10.6; 2025-08-03: 13.5; 2025-08-04: 17.3; 2025-08-05: 21.3; 2025-08-06: 25.1
| Plan | 2025-08-01: 3.6; 2025-08-02: 3.6; 2025-08-03: 0.9; 2025-08-04: 3.6; 2025-08-05: 2.7; 2025-08-06: 4.9
| Cum. Plan | 2025-08-01: 3.6; 2025-08-02: 7.2; 2025-08-03: 8.1; 2025-08-04: 11.7; 2025-08-05: 14.4; 2025-08-06: 19.3
ROM Development
| Actual | 2025-08-01: 33.2; 2025-08-02: 34.7; 2025-08-03: 0; 2025-08-04: 35.1; 2025-08-05: 34.9; 2025-08-06: 17.3
| Cum. Actual | 2025-08-01: 33.2; 2025-08-02: 67.9; 2025-08-03: 67.9; 2025-08-04: 103; 2025-08-05: 137.9; 2025-08-06: 155.2
| Plan | 2025-08-01: 32.1; 2025-08-02: 32.1; 2025-08-03: 0; 2025-08-04: 33; 2025-08-05: 33.9; 2025-08-06: 33.9
| Cum. Plan | 2025-08-01: 32.1; 2025-08-02: 64.2; 2025-08-03: 64.2; 2025-08-04: 97.2; 2025-08-05: 131.1; 2025-08-06: 165
CAPEX Equipping
Actual
| Cum. Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan
| Cum. Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Services Equipping
Actual
| Cum. Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plan
| Cum. Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Generation - Tonnes
| Actual | 2025-08-01: 926; 2025-08-02: 879; 2025-08-03: 965; 2025-08-04: 977; 2025-08-05: 979
| Cum. Actual | 2025-08-01: 926; 2025-08-02: 1805; 2025-08-03: 2770; 2025-08-04: 3747; 2025-08-05: 4726
| Plan | 2025-08-01: 910; 2025-08-02: 910; 2025-08-03: 910; 2025-08-04: 910; 2025-08-05: 910
| Cum. Plan | 2025-08-01: 910; 2025-08-02: 1820; 2025-08-03: 2730; 2025-08-04: 3640; 2025-08-05: 4550
Tramming - Tonnes
| Actual | 2025-08-01: 758; 2025-08-02: 1006; 2025-08-03: 960; 2025-08-04: 795.5; 2025-08-05: 947.5
| Cum. Actual | 2025-08-01: 758; 2025-08-02: 1764; 2025-08-03: 2724; 2025-08-04: 3519.5; 2025-08-05: 4467
| Plan | 2025-08-01: 910; 2025-08-02: 910; 2025-08-03: 910; 2025-08-04: 910; 2025-08-05: 910
| Cum. Plan | 2025-08-01: 910; 2025-08-02: 1820; 2025-08-03: 2730; 2025-08-04: 3640; 2025-08-05: 4550
Hoisting - Tonnes
| Actual | 2025-08-01: 782; 2025-08-02: 952; 2025-08-03: 907; 2025-08-04: 812; 2025-08-05: 931
| Cum. Actual | 2025-08-01: 782; 2025-08-02: 1734; 2025-08-03: 2641; 2025-08-04: 3453; 2025-08-05: 4384
| Plan | 2025-08-01: 740; 2025-08-02: 850; 2025-08-03: 850; 2025-08-04: 850; 2025-08-05: 850
| Cum. Plan | 2025-08-01: 740; 2025-08-02: 1590; 2025-08-03: 2440; 2025-08-04: 3290; 2025-08-05: 4140
Generation - Grade
| Actual | 2025-08-01: 3.5549; 2025-08-02: 3.3304; 2025-08-03: 2.9584; 2025-08-04: 3.4358; 2025-08-05: 1.5282
| Cum. Actual | 2025-08-01: 3.5549; 2025-08-02: 3.4456; 2025-08-03: 3.2759; 2025-08-04: 3.3176; 2025-08-05: 2.9469
| Plan | 2025-08-01: 2.2564; 2025-08-02: 2.2564; 2025-08-03: 2.2564; 2025-08-04: 2.2564; 2025-08-05: 2.2564
| Cum. Plan | 2025-08-01: 2.2564; 2025-08-02: 2.2564; 2025-08-03: 2.2564; 2025-08-04: 2.2564; 2025-08-05: 2.2564
Tramming - Grade
| Actual | 2025-08-01: 2.2936; 2025-08-02: 3.3518; 2025-08-03: 3.1195; 2025-08-04: 2.8487; 2025-08-05: 2.7826
| Cum. Actual | 2025-08-01: 2.2936; 2025-08-02: 2.8971; 2025-08-03: 2.9755; 2025-08-04: 2.9468; 2025-08-05: 2.912
| Plan | 2025-08-01: 1.9111; 2025-08-02: 2.2564; 2025-08-03: 2.2564; 2025-08-04: 2.2564; 2025-08-05: 2.2564
| Cum. Plan | 2025-08-01: 1.9111; 2025-08-02: 2.0838; 2025-08-03: 2.1413; 2025-08-04: 2.1701; 2025-08-05: 2.1873
Hoisting - Grade
| Actual | 2025-08-01: 1.99; 2025-08-02: 2.13; 2025-08-03: 1.67; 2025-08-04: 1.82; 2025-08-05: 3.13
| Cum. Actual | 2025-08-01: 1.99; 2025-08-02: 2.0669; 2025-08-03: 1.9306; 2025-08-04: 1.9046; 2025-08-05: 2.1648
| Plan | 2025-08-01: 2.2027; 2025-08-02: 2.2399; 2025-08-03: 2.2399; 2025-08-04: 2.2399; 2025-08-05: 2.2399
| Cum. Plan | 2025-08-01: 2.2027; 2025-08-02: 2.2226; 2025-08-03: 2.2286; 2025-08-04: 2.2315; 2025-08-05: 2.2333
Generation - Gold
| Actual | 2025-08-01: 3.2919; 2025-08-02: 2.9274; 2025-08-03: 2.8548; 2025-08-04: 3.3567; 2025-08-05: 1.4961; 2025-08-06: 2.7777
| Cum. Actual | 2025-08-01: 3.2919; 2025-08-02: 6.2193; 2025-08-03: 9.0741; 2025-08-04: 12.4309; 2025-08-05: 13.927; 2025-08-06: 16.7046
| Plan | 2025-08-01: 2.0533; 2025-08-02: 2.0533; 2025-08-03: 2.0533; 2025-08-04: 2.0533; 2025-08-05: 2.0533; 2025-08-06: 2.0533
| Cum. Plan | 2025-08-01: 2.0533; 2025-08-02: 4.1066; 2025-08-03: 6.1599; 2025-08-04: 8.2132; 2025-08-05: 10.2665; 2025-08-06: 12.3198
Tramming - Gold
| Actual | 2025-08-01: 1.7386; 2025-08-02: 3.3719; 2025-08-03: 2.9947; 2025-08-04: 2.2661; 2025-08-05: 2.6365; 2025-08-06: 0
| Cum. Actual | 2025-08-01: 1.7386; 2025-08-02: 5.1105; 2025-08-03: 8.1052; 2025-08-04: 10.3713; 2025-08-05: 13.0078; 2025-08-06: 13.0078
| Plan | 2025-08-01: 1.7391; 2025-08-02: 2.0533; 2025-08-03: 2.0533; 2025-08-04: 2.0533; 2025-08-05: 2.0533; 2025-08-06: 2.0533
| Cum. Plan | 2025-08-01: 1.7391; 2025-08-02: 3.7924; 2025-08-03: 5.8457; 2025-08-04: 7.899; 2025-08-05: 9.9523; 2025-08-06: 12.0057
Hoisting - Gold
| Actual | 2025-08-01: 1.5562; 2025-08-02: 2.0278; 2025-08-03: 1.5147; 2025-08-04: 1.4778; 2025-08-05: 2.914; 2025-08-06: 0
| Cum. Actual | 2025-08-01: 1.5562; 2025-08-02: 3.5839; 2025-08-03: 5.0986; 2025-08-04: 6.5765; 2025-08-05: 9.4905; 2025-08-06: 9.4905
| Plan | 2025-08-01: 1.63; 2025-08-02: 1.9039; 2025-08-03: 1.9039; 2025-08-04: 1.9039; 2025-08-05: 1.9039; 2025-08-06: 1.9039
| Cum. Plan | 2025-08-01: 1.63; 2025-08-02: 3.5339; 2025-08-03: 5.4378; 2025-08-04: 7.3418; 2025-08-05: 9.2457; 2025-08-06: 11.1496

## Sheet4 (hidden)
868.5 | 815 | 702 | 805.5 | 603 | 643.5 | 702 | 760.5
2.75 | 1.16 | 1.46 | 1.14 | 1.87 | 1.71 | 2.4 | 2.4
5900
1.8669