## 01August25
Item | Activity | Responsible | Description | Start Date | Completion Date |  |  |  | Comment for 03 June 2025
| PRODUCTION AND GRADE CONTROL |  |  |  |  | Daily | MTD | Budget MTD
1 | Tramming | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 | 758 | 758 | 910
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 | 2.2936 | 2.2936 | 1.9111 | 1W24 mining low grades and needs to be guided by geology
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 | 1.7386 | 1.7386 | 1.7391 | Hoisting budget grade used
2 | Milling | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 | 1244.3207 | 1244.3207 | 1173.8712
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 | 1.3227 | 1.3227 | 2.3 | Stockpiles milled
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 | 1.6459 | 1.6459 | 2.6999
Item | Activity | Responsible | Description | Start Date | Completion Date | Target Date | 2025-05-26 |  | Comment for 26 May 2025
SURVEY
1 | 3D Scanning of stopes and haulages | NR | Update the mine 3D model from scans | 2025-04-14 | 2025-06-30 |  | On schedule
| a. 4L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| b. 5L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| c. 6L | NR |  |  |  | 2025-06-30 | On schedule |  | Daily scanning of 6 active stopes on target
2 | Survey measuring for Weekly production reporting | NR | Volume calculation from scans | 2025-05-11 | 2025-05-31 | 2025-06-01 | On schedule |  | Only one Total station in use. Expediting for payment of machine service and calibration
3 | Print Survey plans per level: | SD | Outsource printing of plans | 2025-04-22 | 2025-05-31
| a. 4L | SD |  |  |  | 2025-05-31 | No progress |  | Surpac software not licenced. Expedite payment through FD
| b. 5L | SD |  |  |  | 2025-06-15 | No progress |  | Lower priority. No progress month end measuring.
| c. 6L | SD |  |  |  | 2025-05-31 | No progress |  | Lower priority. No progress month end measuring.
GEOLOGY
1 | Concession Hill 4L | VT | 4LW29 Haulage and Crosscut |  |  | 2025-06-30 | On schedule |  | Blast 1.1m per day to achieve 23m crosccut to new reef
2 | Concession Hill 6L | VT | Cleaning haulage from 6LW21 to 6LW24 (100m at 5m per day) | 2025-04-24 | 2025-07-01 | 2025-06-30 | No advance. Crews awaited from 10L |  | Open DD cubby on 6LW29. Crews awaited from 10L
3 | Duchess 3L & 4L | VT | Lay tracks and develop 180m to Duchess ore blocks | 2025-05-01 | 2025-11-05 | 2025-11-05 | On schedule |  | Tracks transported to UG. Crews on induction
PROJECTS
1 | Shaft plumbing to 7L | NR | Complete survey transfer to 7L and close it through Southwell |  |  | 2025-06-15 | No progress |  | Projects surveyor setting control pegs on 10L
2 | Commence 10L survey installation | NR |  |  |  | 2025-05-31 | On schedule |  | Projects surveyor setting control pegs on 10L
3 | Hiring of a Projects Surveyor | SD | Recruit a projects surveyor for capital projects | 2025-06-01 | 2025-06-30 | 2025-06-30 | On schedule |  | Contractor Surveyor on site.

## 02August25
Item | Activity | Responsible | Description | Start Date | Completion Date |  |  |  | Comment for 03 June 2025
| PRODUCTION AND GRADE CONTROL |  |  |  |  | Daily | MTD | Budget MTD
1 | Tramming | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 | 1006 | 1764 | 1820
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 | 3.3518 | 2.8971 | 2.0838 | 1W24 mining low grades and needs to be guided by geology
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 | 3.3719 | 5.1105 | 3.7924 | Hoisting budget grade used
2 | Milling | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 | 1143.296 | 2387.6167 | 2347.7424
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 | 1.9326 | 1.6147 | 2.3 | Stockpiles milled
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 | 2.2095 | 3.8554 | 5.3998
Item | Activity | Responsible | Description | Start Date | Completion Date | Target Date | 2025-05-26 |  | Comment for 26 May 2025
SURVEY
1 | 3D Scanning of stopes and haulages | NR | Update the mine 3D model from scans | 2025-04-14 | 2025-06-30 |  | On schedule
| a. 4L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| b. 5L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| c. 6L | NR |  |  |  | 2025-06-30 | On schedule |  | Daily scanning of 6 active stopes on target
2 | Survey measuring for Weekly production reporting | NR | Volume calculation from scans | 2025-05-11 | 2025-05-31 | 2025-06-01 | On schedule |  | Only one Total station in use. Expediting for payment of machine service and calibration
3 | Print Survey plans per level: | SD | Outsource printing of plans | 2025-04-22 | 2025-05-31
| a. 4L | SD |  |  |  | 2025-05-31 | No progress |  | Surpac software not licenced. Expedite payment through FD
| b. 5L | SD |  |  |  | 2025-06-15 | No progress |  | Lower priority. No progress month end measuring.
| c. 6L | SD |  |  |  | 2025-05-31 | No progress |  | Lower priority. No progress month end measuring.
GEOLOGY
1 | Concession Hill 4L | VT | 4LW29 Haulage and Crosscut |  |  | 2025-06-30 | On schedule |  | Blast 1.1m per day to achieve 23m crosccut to new reef
2 | Concession Hill 6L | VT | Cleaning haulage from 6LW21 to 6LW24 (100m at 5m per day) | 2025-04-24 | 2025-07-01 | 2025-06-30 | No advance. Crews awaited from 10L |  | Open DD cubby on 6LW29. Crews awaited from 10L
3 | Duchess 3L & 4L | VT | Lay tracks and develop 180m to Duchess ore blocks | 2025-05-01 | 2025-11-05 | 2025-11-05 | On schedule |  | Tracks transported to UG. Crews on induction
PROJECTS
1 | Shaft plumbing to 7L | NR | Complete survey transfer to 7L and close it through Southwell |  |  | 2025-06-15 | No progress |  | Projects surveyor setting control pegs on 10L
2 | Commence 10L survey installation | NR |  |  |  | 2025-05-31 | On schedule |  | Projects surveyor setting control pegs on 10L
3 | Hiring of a Projects Surveyor | SD | Recruit a projects surveyor for capital projects | 2025-06-01 | 2025-06-30 | 2025-06-30 | On schedule |  | Contractor Surveyor on site.

## 03August25
Item | Activity | Responsible | Description | Start Date | Completion Date |  |  |  | Comment for 03 June 2025
| PRODUCTION AND GRADE CONTROL |  |  |  |  | Daily | MTD | Budget MTD
1 | Tramming | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 | 960 | 2724 | 2730
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 | 3.1195 | 2.9755 | 2.1413 | 1W24 mining low grades and needs to be guided by geology
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 | 2.9947 | 8.1052 | 5.8457 | Hoisting budget grade used
2 | Milling | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 | 665.4402 | 3053.0569 | 3521.6136
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 | 2.1524 | 1.7319 | 2.144 | Stockpiles milled
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 | 1.4323 | 5.2877 | 7.5503
Item | Activity | Responsible | Description | Start Date | Completion Date | Target Date | 2025-05-26 |  | Comment for 26 May 2025
SURVEY
1 | 3D Scanning of stopes and haulages | NR | Update the mine 3D model from scans | 2025-04-14 | 2025-06-30 |  | On schedule
| a. 4L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| b. 5L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| c. 6L | NR |  |  |  | 2025-06-30 | On schedule |  | Daily scanning of 6 active stopes on target
2 | Survey measuring for Weekly production reporting | NR | Volume calculation from scans | 2025-05-11 | 2025-05-31 | 2025-06-01 | On schedule |  | Only one Total station in use. Expediting for payment of machine service and calibration
3 | Print Survey plans per level: | SD | Outsource printing of plans | 2025-04-22 | 2025-05-31
| a. 4L | SD |  |  |  | 2025-05-31 | No progress |  | Surpac software not licenced. Expedite payment through FD
| b. 5L | SD |  |  |  | 2025-06-15 | No progress |  | Lower priority. No progress month end measuring.
| c. 6L | SD |  |  |  | 2025-05-31 | No progress |  | Lower priority. No progress month end measuring.
GEOLOGY
1 | Concession Hill 4L | VT | 4LW29 Haulage and Crosscut |  |  | 2025-06-30 | On schedule |  | Blast 1.1m per day to achieve 23m crosccut to new reef
2 | Concession Hill 6L | VT | Cleaning haulage from 6LW21 to 6LW24 (100m at 5m per day) | 2025-04-24 | 2025-07-01 | 2025-06-30 | No advance. Crews awaited from 10L |  | Open DD cubby on 6LW29. Crews awaited from 10L
3 | Duchess 3L & 4L | VT | Lay tracks and develop 180m to Duchess ore blocks | 2025-05-01 | 2025-11-05 | 2025-11-05 | On schedule |  | Tracks transported to UG. Crews on induction
PROJECTS
1 | Shaft plumbing to 7L | NR | Complete survey transfer to 7L and close it through Southwell |  |  | 2025-06-15 | No progress |  | Projects surveyor setting control pegs on 10L
2 | Commence 10L survey installation | NR |  |  |  | 2025-05-31 | On schedule |  | Projects surveyor setting control pegs on 10L
3 | Hiring of a Projects Surveyor | SD | Recruit a projects surveyor for capital projects | 2025-06-01 | 2025-06-30 | 2025-06-30 | On schedule |  | Contractor Surveyor on site.

## 04August25
Item | Activity | Responsible | Description | Start Date | Completion Date |  |  |  | Comment for 03 June 2025
| PRODUCTION AND GRADE CONTROL |  |  |  |  | Daily | MTD | Budget MTD
1 | Tramming | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 | 795.5 | 3519.5 | 3640
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 | 2.8487 | 2.9468 | 2.1701 | 1W24 mining low grades and needs to be guided by geology
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 | 2.2661 | 10.3713 | 7.899 | Hoisting budget grade used
2 | Milling | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 | 1124.527 | 4177.5839 | 4695.4848
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 | 1.7907 | 1.7478 | 2.1659 | Stockpiles milled
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 | 2.0137 | 7.3014 | 10.1699
Item | Activity | Responsible | Description | Start Date | Completion Date | Target Date | 2025-05-26 |  | Comment for 26 May 2025
SURVEY
1 | 3D Scanning of stopes and haulages | NR | Update the mine 3D model from scans | 2025-04-14 | 2025-06-30 |  | On schedule
| a. 4L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| b. 5L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| c. 6L | NR |  |  |  | 2025-06-30 | On schedule |  | Daily scanning of 6 active stopes on target
2 | Survey measuring for Weekly production reporting | NR | Volume calculation from scans | 2025-05-11 | 2025-05-31 | 2025-06-01 | On schedule |  | Only one Total station in use. Expediting for payment of machine service and calibration
3 | Print Survey plans per level: | SD | Outsource printing of plans | 2025-04-22 | 2025-05-31
| a. 4L | SD |  |  |  | 2025-05-31 | No progress |  | Surpac software not licenced. Expedite payment through FD
| b. 5L | SD |  |  |  | 2025-06-15 | No progress |  | Lower priority. No progress month end measuring.
| c. 6L | SD |  |  |  | 2025-05-31 | No progress |  | Lower priority. No progress month end measuring.
GEOLOGY
1 | Concession Hill 4L | VT | 4LW29 Haulage and Crosscut |  |  | 2025-06-30 | On schedule |  | Blast 1.1m per day to achieve 23m crosccut to new reef
2 | Concession Hill 6L | VT | Cleaning haulage from 6LW21 to 6LW24 (100m at 5m per day) | 2025-04-24 | 2025-07-01 | 2025-06-30 | No advance. Crews awaited from 10L |  | Open DD cubby on 6LW29. Crews awaited from 10L
3 | Duchess 3L & 4L | VT | Lay tracks and develop 180m to Duchess ore blocks | 2025-05-01 | 2025-11-05 | 2025-11-05 | On schedule |  | Tracks transported to UG. Crews on induction
PROJECTS
1 | Shaft plumbing to 7L | NR | Complete survey transfer to 7L and close it through Southwell |  |  | 2025-06-15 | No progress |  | Projects surveyor setting control pegs on 10L
2 | Commence 10L survey installation | NR |  |  |  | 2025-05-31 | On schedule |  | Projects surveyor setting control pegs on 10L
3 | Hiring of a Projects Surveyor | SD | Recruit a projects surveyor for capital projects | 2025-06-01 | 2025-06-30 | 2025-06-30 | On schedule |  | Contractor Surveyor on site.

## 05August25
Item | Activity | Responsible | Description | Start Date | Completion Date |  |  |  | Comment for 03 June 2025
| PRODUCTION AND GRADE CONTROL |  |  |  |  | Daily | MTD | Budget MTD
1 | Tramming | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 | 947.5 | 4467 | 4550
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 | 2.7826 | 2.912 | 2.1873 | 1W24 mining low grades and needs to be guided by geology
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 | 2.6365 | 13.0078 | 9.9523 | Hoisting budget grade used
2 | Milling | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 | 1067.219 | 5244.8029 | 5282.4204
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 | 2.0169 | 1.8025 | 2.1734 | Stockpiles milled
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 | 2.1525 | 9.4539 | 11.481
Item | Activity | Responsible | Description | Start Date | Completion Date | Target Date | 2025-05-26 |  | Comment for 26 May 2025
SURVEY
1 | 3D Scanning of stopes and haulages | NR | Update the mine 3D model from scans | 2025-04-14 | 2025-06-30 |  | On schedule
| a. 4L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| b. 5L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| c. 6L | NR |  |  |  | 2025-06-30 | On schedule |  | Daily scanning of 6 active stopes on target
2 | Survey measuring for Weekly production reporting | NR | Volume calculation from scans | 2025-05-11 | 2025-05-31 | 2025-06-01 | On schedule |  | Only one Total station in use. Expediting for payment of machine service and calibration
3 | Print Survey plans per level: | SD | Outsource printing of plans | 2025-04-22 | 2025-05-31
| a. 4L | SD |  |  |  | 2025-05-31 | No progress |  | Surpac software not licenced. Expedite payment through FD
| b. 5L | SD |  |  |  | 2025-06-15 | No progress |  | Lower priority. No progress month end measuring.
| c. 6L | SD |  |  |  | 2025-05-31 | No progress |  | Lower priority. No progress month end measuring.
GEOLOGY
1 | Concession Hill 4L | VT | 4LW29 Haulage and Crosscut |  |  | 2025-06-30 | On schedule |  | Blast 1.1m per day to achieve 23m crosccut to new reef
2 | Concession Hill 6L | VT | Cleaning haulage from 6LW21 to 6LW24 (100m at 5m per day) | 2025-04-24 | 2025-07-01 | 2025-06-30 | No advance. Crews awaited from 10L |  | Open DD cubby on 6LW29. Crews awaited from 10L
3 | Duchess 3L & 4L | VT | Lay tracks and develop 180m to Duchess ore blocks | 2025-05-01 | 2025-11-05 | 2025-11-05 | On schedule |  | Tracks transported to UG. Crews on induction
PROJECTS
1 | Shaft plumbing to 7L | NR | Complete survey transfer to 7L and close it through Southwell |  |  | 2025-06-15 | No progress |  | Projects surveyor setting control pegs on 10L
2 | Commence 10L survey installation | NR |  |  |  | 2025-05-31 | On schedule |  | Projects surveyor setting control pegs on 10L
3 | Hiring of a Projects Surveyor | SD | Recruit a projects surveyor for capital projects | 2025-06-01 | 2025-06-30 | 2025-06-30 | On schedule |  | Contractor Surveyor on site.

## 06August25
Item | Activity | Responsible | Description | Start Date | Completion Date |  |  |  | Comment for 03 June 2025
| PRODUCTION AND GRADE CONTROL |  |  |  |  | Daily | MTD | Budget MTD
1 | Tramming | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 | 458 | 4925 | 5460
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 | 0 | 2.6412 | 2.1988 | 1W24 mining low grades and needs to be guided by geology
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 | 0 | 13.0078 | 12.0057 | Hoisting budget grade used
2 | Milling | Tonnes (t) | Target 28,505 tonnes | 2025-05-01 | 2025-05-31 |  | 5244.8029 | 5282.4204
|  | Grade (g/t) | Target 2.36 g/t | 2025-05-01 | 2025-05-31 |  | 1.8025 | 2.1734 | Stockpiles milled
|  | Gold (kg) | Target 56.4 kg | 2025-05-01 | 2025-05-31 |  | 9.4539 | 11.481
Item | Activity | Responsible | Description | Start Date | Completion Date | Target Date | 2025-05-26 |  | Comment for 26 May 2025
SURVEY
1 | 3D Scanning of stopes and haulages | NR | Update the mine 3D model from scans | 2025-04-14 | 2025-06-30 |  | On schedule
| a. 4L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| b. 5L | NR |  |  |  | 2025-06-30 | No progress |  | One total station on site used at production
| c. 6L | NR |  |  |  | 2025-06-30 | On schedule |  | Daily scanning of 6 active stopes on target
2 | Survey measuring for Weekly production reporting | NR | Volume calculation from scans | 2025-05-11 | 2025-05-31 | 2025-06-01 | On schedule |  | Only one Total station in use. Expediting for payment of machine service and calibration
3 | Print Survey plans per level: | SD | Outsource printing of plans | 2025-04-22 | 2025-05-31
| a. 4L | SD |  |  |  | 2025-05-31 | No progress |  | Surpac software not licenced. Expedite payment through FD
| b. 5L | SD |  |  |  | 2025-06-15 | No progress |  | Lower priority. No progress month end measuring.
| c. 6L | SD |  |  |  | 2025-05-31 | No progress |  | Lower priority. No progress month end measuring.
GEOLOGY
1 | Concession Hill 4L | VT | 4LW29 Haulage and Crosscut |  |  | 2025-06-30 | On schedule |  | Blast 1.1m per day to achieve 23m crosccut to new reef
2 | Concession Hill 6L | VT | Cleaning haulage from 6LW21 to 6LW24 (100m at 5m per day) | 2025-04-24 | 2025-07-01 | 2025-06-30 | No advance. Crews awaited from 10L |  | Open DD cubby on 6LW29. Crews awaited from 10L
3 | Duchess 3L & 4L | VT | Lay tracks and develop 180m to Duchess ore blocks | 2025-05-01 | 2025-11-05 | 2025-11-05 | On schedule |  | Tracks transported to UG. Crews on induction
PROJECTS
1 | Shaft plumbing to 7L | NR | Complete survey transfer to 7L and close it through Southwell |  |  | 2025-06-15 | No progress |  | Projects surveyor setting control pegs on 10L
2 | Commence 10L survey installation | NR |  |  |  | 2025-05-31 | On schedule |  | Projects surveyor setting control pegs on 10L
3 | Hiring of a Projects Surveyor | SD | Recruit a projects surveyor for capital projects | 2025-06-01 | 2025-06-30 | 2025-06-30 | On schedule |  | Contractor Surveyor on site.